## Sheet1
Project | VAGO name | Project_type_VAGO | TEI_VAGO | TEI_Change_Per | TEI_Change_$ | Est exp to date_VAGO | Remaining exp_VAGO | Est completion date | Budget Year | Completion_date_VAGO | Agency | VAGO Agency | Project Location | VAGO Location | Program | VAGO Program Name | Sector | Vago Sector | Fixed Notes
Acquisition of Bendigo GovHub (Bendigo) | Acquisition of Bendigo GovHub | New | 120800000 | 0 | 0 |  |  | qtr 1 2022‑23 | 2021–22 | 2022-09-30 | Department of Treasury and Finance | Department of Treasury and Finance | Bendigo | Regional |  |  | GG | Culture, sport and community
Bendigo Law Courts Redevelopment (Bendigo) | Bendigo Law Courts Redevelopment | New | 152396000 | 0 | 0 | 0 | 132496000 | qtr 1 2022‑23 | 2019–20 | 2022-09-30 | Court Services Victoria | Court Services Victoria | Bendigo | Regional |  |  | GG | Justice and emergency services
Bendigo Law Courts Redevelopment (Bendigo) | Bendigo Law Courts Redevelopment | Existing | 152396000 | 0 | 0 | 23133000 | 30883000 | qtr 1 2022‑23 | 2021–22 | 2022-09-30 | Court Services Victoria | Court Services Victoria | Bendigo | Regional |  |  | GG | Justice and emergency services
Bendigo Hospital – Redevelopment (Bendigo) | Bendigo Hospital – Redevelopment | Existing | 129460000 | 0 | 0 | 83560000 | 31300000 | qtr 2 2016‑17 | 2014–15 | 2016-12-31 | Department of Health | Department of Health | Bendigo | Regional |  |  | GG | Health and human services | The TEI has changed to reflect the public private partnership contract with the remaining capital for State retained associated project costs. The revised TEI for this initiative includes Stage 1 Enabling Works funding of $55.000 million provided in 2009‑10.
Bendigo Hospital – Redevelopment (Bendigo) | Bendigo Hospital – Redevelopment | Existing | 129460000 | 0 | 0 | 97386000 | 16738000 | qtr 2 2016‑17 | 2016–17 | 2016-12-31 | Department of Health and Human Services | Department of Health | Bendigo | Regional |  |  | GG | Health and human services
Bendigo Hospital – Redevelopment (Bendigo) | Bendigo Hospital – Redevelopment | Existing | 129460000 | 0 | 0 | 97545000 | 16615000 | qtr 2 2016‑17 | 2015–16 | 2016-12-31 | Department of Health and Human Services | Department of Health | Bendigo | Regional |  |  | GG | Health and human services
Regional Rail Revival – Bendigo/Echuca Line Upgrade (Bendigo) | Regional Rail Revival – Bendigo/Echuca Line Upgrade | Existing | 175264000 | 0 | 0 | 30360000 | 70704000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Bendigo | Regional | Regional Rail Revival |  | PNFC | Transport | TEI has increased by $85.200 million due to scope variations and market conditions. TEI includes $158.680 million of Commonwealth funding and excludes $0.368 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Additional VLocity trains (regional various) | Additional VLocity trains | New | 340000000 | 0 | 0 | 0 | 161600000 | tbc | 2019–20 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Additional VLocity trains (regional various) | Additional VLocity trains | Existing | 340000000 | 0 | 0 | 127333000 | 85647000 | qtr 4 2023‑24 | 2021–22 | 2024-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional |  |  | PNFC | Transport
Continuing Towards Zero (regional various) | Continuing Towards Zero | New | 149200000 | 0 | 0 | 0 | 118000000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport
Continuing Towards Zero (regional various) | Continuing Towards Zero | Existing | 149200000 | 0 | 0 | 6000000 | 24999000 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Department of Transport | Department of Transport | Regional | Regional |  |  | GG | Transport | This initiative is funded by the Transport Accident Commission. The estimated completion date has been revised to quarter 4 2020‑21 due to extended community engagement.
TAC Victoria’s Road Safety Strategy, Towards Zero 2016‑2020 (TZ1) (statewide) | Continuing Towards Zero | Completed | 292863000 | 0.23467 | 55663000 | 291951000 |  | qtr 1 2022‑23 | 2021–22 | 2022-09-30 | Department of Transport | Department of Transport | Statewide | Statewide | Rural and Regional Roads Package |  | GG | Transport | TEI has increased by $1.864 million due to certain expenditure being reclassified as capital instead of operating in line with accounting standards. Project name changed from Road Safety Towards Zero in the 2019‑20 Budget.
TAC Victoria’s Road Safety Strategy, Towards Zero 2016‑2020 (TZ2) (regional various) | Continuing Towards Zero | Existing | 237200000 | 0.58981 | 88000000 | 172506000 | 22669000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Transport | Department of Transport | Regional various | Regional | Rural and Regional Roads Package |  | GG | Transport | TEI has increased by $88.000 million due to the addition of upgrades to eight metropolitan roads. The estimated completion date has been revised to quarter 2 2022‑23 to align with the delivery schedule of the Road Safety Program. Project was published as Continuing Towards Zero in the 2019‑20 Budget.
Hurstbridge Corridor Upgrade (non‑metro various) | Hurstbridge rail line upgrade | New | 135905000 | 0 | 0 | 1000000 | 127930000 | qtr 4 2018‑19 | 2016–17 | 2019-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Hurstbridge rail line upgrade (regional various) | Hurstbridge rail line upgrade | Existing | 135905000 | 0 | 0 | 25075000 | 10624000 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Hurstbridge rail line upgrade (metropolitan various) | Hurstbridge rail line upgrade | Completed | 135905000 | 0 | 0 | 135905000 | 0 | qtr 1 2020‑21 | 2019–20 | 2020-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Hurstbridge rail line upgrade (metropolitan various) | Hurstbridge rail line upgrade | Existing | 135905000 | 0 | 0 | 125283000 | 0 | qtr 1 2018-19 | 2018–19 | 2018-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised.
Major periodic maintenance on the regional rail network (regional various) | Major periodic maintenance on the regional rail network | New | 287913000 | 0 | 0 | 0 | 184533000 | qtr 4 2020-21 | 2017–18 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Major periodic maintenance on the regional rail network (regional various) | Major periodic maintenance on the regional rail network | Existing | 287913000 | 0 | 0 | 184913000 | 0 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport | The estimated completion date has been revised to quarter 4 2019‑20 to prioritise critical asset maintenance works.
Major periodic maintenance on the regional rail network (regional various) | Major periodic maintenance on the regional rail network | Existing | 287913000 | 0 | 0 | 103380000 | 103000000 | qtr 4 2020-21 | 2018–19 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Major periodic maintenance on the regional rail network (regional various) | Major periodic maintenance on the regional rail network | Completed | 287913000 | 0 | 0 | 287913000 |  | qtr 2 2020‑21 | 2021–22 | 2020-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional |  |  | PNFC | Transport
More regional trains (regional various) | More regional trains – Regional Network Development Plan | New | 287885000 | 0 | 0 | 3630000 | 247171000 | qtr 3 2018-19 | 2017–18 | 2019-03-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
More regional trains – Regional Network Development Plan (regional various) | More regional trains – Regional Network Development Plan | Existing | 228835000 | 0 | 0 | 157645000 | 66956000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport | This project was previously reported as More regional trains.
More regional trains (regional various) | More regional trains – Regional Network Development Plan | Existing | 228835000 | -0.20512 | -59050000 | 77207000 | 75640000 | qtr 4 2019-20 | 2017–18 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
More regional trains – Regional Network Development Plan (regional various) | More regional trains – Regional Network Development Plan | Existing | 226335000 | -0.010925 | -2500000 | 156192000 | 46102000 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport | TEI has reduced by $2.500 million due to savings.
More regional trains – Regional Network Development Plan (regional various) | More regional trains – Regional Network Development Plan | Existing | 224153000 | -0.0096406 | -2182000 | 200094000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional |  |  | PNFC | Transport | TEI has decreased by $2.182 million due to reprioritisation to High Capacity Metro Trains. The estimated completion date has been revised to quarter 4 2021‑22 to reflect a revised schedule of works.
New VLocity carriages for the regional network (non‑metro various) | New VLocity carriages for the regional network | New | 257078000 | 0 | 0 | 0 | 169682000 | qtr 1 2018‑19 | 2015–16 | 2018-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
New VLocity carriages for the regional network (non‑metro various) | New VLocity carriages for the regional network | Existing | 257078000 | 0 | 0 | 72094000 | 57155000 | qtr 1 2018‑19 | 2016–17 | 2018-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
New VLocity carriages for the regional network (regional various) | New VLocity carriages for the regional network | Existing | 257078000 | 0 | 0 | 130723000 | 102509000 | qtr 1 2018-19 | 2017–18 | 2018-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
New VLocity carriages for the regional network (regional various) | New VLocity carriages for the regional network | Existing | 256144000 | -0.0036331 | -934000 | 136024000 | 39704000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport | The estimated completion date has been revised. TEI excludes $0.934 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
New VLocity carriages for the regional network (regional various) | New VLocity carriages for the regional network | Existing | 252356000 | -0.014789 | -3788000 | 144791000 | 15400000 | qtr 4 2021‑22 | 2019–20 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport | The estimated completion date has been revised due to revised scope. TEI excludes $2.150 million due to savings, and $1.638 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards.
New VLocity carriages for the regional network (regional various) | New VLocity carriages for the regional network | Existing | 250602000 | -0.0069505 | -1754000 | 166357000 | 419000 | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional |  |  | PNFC | Transport | TEI has decreased by $34.560 million due to the creation of the E‑Class Tram Infrastructure Program (metropolitan various).
Princes Highway duplication project – Winchelsea to Colac (non‑metro various) | Princes Highway duplication project – Winchelsea to Colac | New | 349490000 | 0 | 0 | 0 | 304770000 | qtr 4 2018‑19 | 2014–15 | 2019-06-30 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Regional | Regional |  |  | GG | Transport | The TEI includes anticipated Commonwealth funding of $167.755 million. The TEI does not include planning funding of $12.000 million, of which $7.000 million was Commonwealth funding.
Princes Highway duplication project – Winchelsea to Colac (regional various) | Princes Highway duplication project – Winchelsea to Colac | Existing | 349193000 | 0 | 0 | 281830000 | 44063000 | qtr 2 2019‑20 | 2019–20 | 2019-12-31 | Department of Transport | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI includes $181.735 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2019‑20 due to design changes and archaeological discoveries.
Princes Highway duplication project – Winchelsea to Colac (non‑metro various) | Princes Highway duplication project – Winchelsea to Colac | Existing | 349490000 | 0 | 0 | 5058000 | 311012000 | qtr 4 2018‑19 | 2015–16 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI includes $181.735 million of Commonwealth funding.
Princes Highway duplication project – Winchelsea to Colac (non‑metro various) | Princes Highway duplication project – Winchelsea to Colac | Existing | 349490000 | 0 | 0 | 27363000 | 247590000 | qtr 4 2018‑19 | 2016–17 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI includes $181.735 million of Commonwealth funding.
Princes Highway duplication project – Winchelsea to Colac (regional various) | Princes Highway duplication project – Winchelsea to Colac | Existing | 349193000 | -8.3042e-05 | -29000 | 183177000 | 98263000 | qtr4 2018 -19 | 2018–19 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport | The estimated completion date has been revised. TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $181.735 million of Commonwealth funding. TEI includes $29.120 million of identified project savings.
Princes Highway duplication project – Winchelsea to Colac (regional various) | Princes Highway duplication project – Winchelsea to Colac | Existing | 349222000 | -0.00076683 | -268000 | 84493000 | 157930000 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI excludes corporate costs. TEI includes $181.735 million of Commonwealth funding.
Princes Highway duplication project – Winchelsea to Colac (regional various) | Princes Highway duplication project – Winchelsea to Colac | Completed | 349193000 | 0 | 0 | 317586000 |  | qtr 2 2021‑22 | 2021–22 | 2021-12-31 | Department of Transport | Department of Transport | Regional various | Regional |  |  | GG | Transport | TEI includes $181.735 million of Commonwealth funding.
Regional Rail Revival – Gippsland Rail Upgrade (regional various) | Regional Rail Revival – Gippsland Rail Upgrade | New | 435000000 | 0 | 0 | 0 | 421500000 | qtr 4 2021-22 | 2017–18 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Regional rail infrastructure and new regional trains (regional various) | Wyndham Vale Stabling Yard | New | 172900000 | 0 | 0 | 0 | 10800000 | tbc | 2018–19 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Wyndham Vale Stabling Yard (regional various) | Wyndham Vale Stabling Yard | Existing | 172900000 | 0 | 0 | 82936000 | 13389000 | qtr 3 2019‑20 | 2019–20 | 2020-03-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport | Project name changed from ’Regional rail infrastructure and new regional trains’ published in 2018-19 Budget.
Wyndham Vale Stabling Yard (regional various) | Wyndham Vale Stabling Yard | Completed | 164257000 | -0.049988 | -8643000 | 145205000 |  | qtr 4 2020‑21 | 2021–22 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional | Regional Rail Revival |  | PNFC | Transport | TEI has decreased by $8.643 million due to project savings.
Connections project (non‑metro various) | Connections project | Existing | 845106000 | 0 | 0 | 530543000 | 232964000 | ongoing | 2014–15 | 2099-06-30 | Goulburn–Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | Regional | Regional |  |  | PNFC | Water | Change in nature of expenditure between capital and operating expenditure.
Connections project (non‑metro various) | Connections project | Existing | 822836000 | -0.026352 | -22270000 | 595456000 | 123792000 | qtr 4 2017‑18 | 2015–16 | 2018-06-30 | Goulburn‑Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | Regional | Regional |  |  | PNFC | Water
Connections project (regional various) | Connections project | Existing | 1015038000 | 0.094549 | 87681000 | 775716000 | 108638000 | qtr 2 2020-21 | 2017–18 | 2020-12-31 | Goulburn-Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | Regional | Regional |  |  | PNFC | Water
Connections project (non‑metro various) | Connections project | Existing | 927357000 | 0.12703 | 104521000 | 716198000 | 133149000 | qtr 4 2017‑18 | 2016–17 | 2018-06-30 | Goulburn‑Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | Regional | Regional |  |  | PNFC | Water | TEI has increased compared to the 2015‑16 Budget due to a change in accounting treatment of capital and output expenditure.
Connections project (regional various) | Connections project | Existing | 1104678000 | 0.088312 | 89640000 | 902235000 | 51662000 | qtr 2 2020-21 | 2018–19 | 2020-12-31 | Goulburn Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | Regional | Regional |  |  | PNFC | Water | The capital component of the overall project TEI has increased from prior year, however this is offset with a decrease in output expenditure. Overall project forecast remains unchanged. This is in alignment with the Reset Delivery Plan and the Stage 1 Completion Plan.
Connections project (regional various) | Connections project | Existing | 1099986000 | -0.0042474 | -4692000 | 1053016000 | 0 | qtr 2 2020‑21 | 2019–20 | 2020-12-31 | Goulburn Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | Regional | Regional |  |  | PNFC | Water
Regional rail network major periodic maintenance (passenger and freight) (non‑metro various) | Regional rail network major periodic maintenance (passenger and freight) | Existing | 171865000 | 0 | 0 | 76125000 | 48460000 | qtr 4 2015‑16 | 2014–15 | 2016-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Regional rail network major periodic maintenance (passenger and freight) (non‑metro various) | Regional rail network major periodic maintenance (passenger and freight) | Existing | 171865000 | 0 | 0 | 123405000 | 0 | qtr 4 2015‑16 | 2015–16 | 2016-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Regional rolling stock (non‑metro various) | Regional rolling stock | Existing | 315150000 | 0 | 0 | 272989000 | 0 | qtr 4 2014‑15 | 2014–15 | 2015-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Regional rolling stock – new tranche (non‑metro various) | Regional rolling stock – new tranche | Existing | 261153000 | 0 | 0 | 150418000 | 70925000 | qtr 2 2017‑18 | 2014–15 | 2017-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Regional rolling stock – new tranche (non‑metro various) | Regional rolling stock – new tranche | Existing | 251153000 | 0 | 0 | 231337000 | 0 | qtr 2 2017‑18 | 2016–17 | 2017-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Regional rolling stock – new tranche (non‑metro various) | Regional rolling stock – new tranche | Existing | 251153000 | -0.038292 | -10000000 | 195887000 | 19816000 | qtr 2 2017‑18 | 2015–16 | 2017-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport | TEI has decreased by $10.000 million. This is due to project savings.
Murray Basin Rail Project (non‑metro various) | Murray Basin Rail Project | New | 220000000 | 0 | 0 | 0 | 209000000 | qtr 4 2017‑18 | 2014–15 | 2018-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  | MBRP | PNFC | Transport
Murray Basin Rail Project (non‑metro various) | Murray Basin Rail Project | Existing | 220000000 | 0 | 0 | 50500000 | 53500000 | qtr 2 2017‑18 | 2016–17 | 2017-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  | MBRP | PNFC | Transport | TEI represents the State Government’s funding commitment. Additional funds to complete the project is being sought from the Commonwealth.
Murray Basin Rail Project (non‑metro various) | Murray Basin Rail Project | Existing | 220000000 | 0 | 0 | 16000000 | 174000000 | qtr 4 2017‑18 | 2015–16 | 2018-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  | MBRP | PNFC | Transport | TEI is estimated to be between $180 million and $220 million. The TEI includes funding announced in Getting On With It. The business case is currently being finalised and will provide options for how best to progress the next stage.
Murray Basin Rail Project (regional various) | Murray Basin Rail Project | Existing | 426500000 | 0 | 0 | 399500000 | 0 | qtr 2 2018-19 | 2018–19 | 2018-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  | MBRP | PNFC | Transport | TEI includes $220.000 million of Commonwealth funding. The estimated completion date has been extended due to the delivery of the project aligning with delivery of Ballarat Line Upgrade.
Murray Basin Rail Project (regional various) | Murray Basin Rail Project | Existing | 567700000 | 0.33107 | 141200000 | 371873000 | 17398000 | tbc | 2019–20 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  | MBRP | PNFC | Transport | $20.200 million has been reallocated to this project from the Regional Rail Revival – (Murray Basin Rail Project). The TEI includes funding for the ‘Rail Infrastructure Upgrades from Maryborough and Ararat to Ballarat’, a $1.000 million contribution from GrainCorp, and $35.000 million of Commonwealth funding for Ballarat Line Upgrade Stage 2. These projects have been combined for reporting purposes and the estimated completion date is to be confirmed.
Murray Basin Rail Project (regional various) | Murray Basin Rail Project | Existing | 426500000 | 0.93864 | 206500000 | 80480000 | 110000000 | qtr 2 2018-19 | 2017–18 | 2018-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  | MBRP | PNFC | Transport | TEI increase due to addition of Commonwealth funding of $220.000 million. Stage 1 of the project is completed, with stage 2 and 3 in procurement. The completion date has been revised following the approval of Commonwealth funding.
Murray Basin Rail Project (regional various) | Murray Basin Rail Project | Existing | 794414000 | 0.39936 | 226714000 | 376757000 | 366184000 | tbc | 2021–22 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional |  |  | PNFC | Transport | TEI has increased by $244.000 million for the optimised scope package of the Murray Basin Rail Project, including $36.000 million of works from Regional Rail Maintenance – Sleeper and Ballast Replacement and Remediation, and includes an additional $195.200 million of Commonwealth funding. TEI excludes $17.286 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Ballarat rail upgrade (non‑metro various) | Ballarat Line Upgrade | New | 516724000 | 0 | 0 | 0 | 485721000 | qtr 4 2019‑20 | 2016–17 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional | Regional Public Transport |  | PNFC | Transport
Ballarat Line upgrade (regional various) | Ballarat Line Upgrade | Existing | 516724000 | 0 | 0 | 28074000 | 351845000 | qtr 4 2019-20 | 2017–18 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
Ballarat Line Upgrade Stage 1 (regional various) | Ballarat Line Upgrade | Existing | 549455000 | 0.063343 | 32731000 | 98076000 | 20563000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional | Regional Rail Revival (regional various) |  | PNFC | Transport | TEI includes $467.000 million of Commonwealth funding. TEI includes additional funding of $33.700 million to build a new train station at Toolern and excludes $0.969 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
Ballarat Line Upgrade Stage 1 (regional various) | Ballarat Line Upgrade | Existing | 545014000 | -0.0080826 | -4441000 | 370472000 | 16177000 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional | Regional Rail Revival |  | PNFC | Transport | TEI includes $467.000 million of Commonwealth funding, and excludes $4.441 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
Regional Rail Revival – Ballarat Line Upgrade Stage 1 (regional various) | Ballarat Line Upgrade | Completed | 631121000 | 0.15799 | 86107000 | 607785000 |  | qtr 3 2022‑23 | 2021–22 | 2023-03-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional | Regional Rail Revival |  | PNFC | Transport | TEI has increased by $93.000 million due to scope variations and market conditions, and decreased by $6.893 million due to savings. TEI includes $503.000 million of Commonwealth funding.
Geelong Line Upgrade – Waurn Ponds Duplication (Stage 1) (regional various) | Geelong Line Upgrade – Waurn Ponds Duplication (stage 1) | New | 110000000 | 0 | 0 | 4491000 | 64412000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional | Regional Rail Revival |  | PNFC | Transport | TEI includes $99.000 million of Commonwealth funding.
Gippsland Line Upgrade Stage 1 (regional various) | Regional Rail Revival – Gippsland Line Upgrade Stage 1 | Existing | 435000000 | 0 | 0 | 5000000 | 407600000 | qtr 4 2021-22 | 2018–19 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional | Regional Rail Revival (regional various) |  | PNFC | Transport | TEI includes $418.000 million of Commonwealth funding.
Gippsland Line Upgrade Stage 1 (regional various) | Regional Rail Revival – Gippsland Line Upgrade Stage 1 | Existing | 433938000 | -0.0024414 | -1062000 | 31335000 | 358216000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional | Regional Rail Revival |  | PNFC | Transport | TEI includes $418.000 million of Commonwealth funding, and excludes $1.062 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. The estimated completion date has been revised due to packaging of the Gippsland‑Shepparton‑Bendigo alliance.
Regional Rail Revival – Gippsland Line Upgrade Stage 1 (regional various) | Regional Rail Revival – Gippsland Line Upgrade Stage 1 | Existing | 531364000 | 0.22452 | 97426000 | 82643000 | 227191000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional | Regional Rail Revival |  | PNFC | Transport | TEI has increased by $97.800 million due to scope variations and market conditions. TEI includes $447.700 million of Commonwealth funding and excludes $1.436 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Major periodic maintenance (non‑metro various) | Major periodic maintenance | New | 141207000 | 0 | 0 | 23278000 | 0 | qtr 4 2016‑17 | 2016–17 | 2017-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional | Regional Public Transport |  | PNFC | Transport
More regional trains (non‑metro various) | More regional trains – New Vlocity Trains | New | 228835000 | 0 | 0 | 0 | 116016000 | qtr 4 2019‑20 | 2016–17 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional | Regional Public Transport |  | PNFC | Transport
More regional trains (regional various) | More regional trains – New Vlocity Trains | New | 287885000 | 0.25805 | 59050000 | 3630000 | 247171000 | qtr 3 2018-19 | 2017–18 | 2019-03-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
More regional trains (regional various) | More regional trains – New Vlocity Trains | Existing | 228835000 | -0.20512 | -59050000 | 77207000 | 75640000 | qtr 4 2019-20 | 2017–18 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport
More regional trains – New Vlocity Trains (regional various) | More regional trains – New Vlocity Trains | Existing | 276125000 | 0.20666 | 47290000 | 109563000 | 103405000 | qtr 4 2020-21 | 2018–19 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport | The estimated completion date has been revised. This project was previously reported as More regional trains. TEI has been decreased by $11.760 million due to savings in the VLocity train procurement.
More regional trains – New Vlocity Trains (regional various) | More regional trains – New Vlocity Trains | Existing | 270424000 | -0.020646 | -5701000 | 170817000 | 33535000 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional |  |  | PNFC | Transport | TEI has reduced by $5.701 million due to savings.
More regional trains – New Vlocity Trains (regional various) | More regional trains – New Vlocity Trains | Completed | 259424000 | -0.040677 | -11000000 | 238702000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional |  |  | PNFC | Transport | TEI has decreased by $11.000 million due to reprioritisation to High Capacity Metro Trains.
Princes Highway East – Traralgon to Sale duplication (non‑metro various) | Princes Highway East – Traralgon to Sale duplication | Existing | 175000000 | 0 | 0 | 95122000 | 35110000 | qtr 3 2015‑16 | 2014–15 | 2016-03-31 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Regional | Regional | Better Roads – Rural Arterial Roads projects |  | GG | Transport | Project TEI includes $140.000 million of Commonwealth funding.
Princes Highway East – Traralgon to Sale duplication (regional various) | Princes Highway East – Traralgon to Sale duplication | Completed | 259067000 | 0 | 0 | 245849000 | 0 | qtr 4 2021‑22 | 2019–20 | 2022-06-30 | Department of Transport | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI includes $210.000 million of Commonwealth funding.
Princes Highway East – Traralgon to Sale duplication (non‑metro various) | Princes Highway East – Traralgon to Sale duplication | Existing | 260000000 | 0 | 0 | 166280000 | 62817000 | qtr 4 2018‑19 | 2016–17 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI includes $210.000 million of Commonwealth funding.
Princes Highway East – Traralgon to Sale duplication (non‑metro various) | Princes Highway East – Traralgon to Sale duplication | Existing | 260000000 | 0.48571 | 85000000 | 128103000 | 83834000 | qtr 4 2018‑19 | 2015–16 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional | Better Roads – Rural Arterial Roads projects |  | GG | Transport | TEI has increased by $85.000 million. This is due to an increase in project scope to include duplication east of Traralgon, east of Rosedale and west of Fulham. Project TEI includes $210.000 million of Commonwealth funding.
Princes Highway East – Traralgon to Sale duplication (regional various) | Princes Highway East – Traralgon to Sale duplication | Existing | 259284000 | -0.0027538 | -716000 | 198576000 | 28677000 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI includes $210.000 million of Commonwealth funding.
Princes Highway East – Traralgon to Sale duplication (regional various) | Princes Highway East – Traralgon to Sale duplication | Existing | 259067000 | -0.00083692 | -217000 | 237179000 | 11888000 | qtr 4 2018-19 | 2018–19 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $210.000 million Commonwealth funding.
Princes Highway West – stage 1 Waurn Ponds to Winchelsea (non‑metro various) | Princes Highway West – stage 1 Waurn Ponds to Winchelsea | Existing | 171000000 | 0 | 0 | 101309000 | 47855000 | qtr 4 2014‑15 | 2014–15 | 2015-06-30 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Regional | Regional | Better Roads – Rural Arterial Roads projects |  | GG | Transport | The TEI has decreased by $49.000 million due to lower than anticipated construction costs. This project includes $85.500 million of Commonwealth funding.
Warrnambool Line Upgrade (regional various) | Regional Rail Revival – Warrnambool Line Upgrade – Stage 2 | Existing | 114000000 | 0 | 0 | 15636000 | 42377000 | qtr 4 2021‑22 | 2019–20 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional | Regional | Regional Rail Revival | Regional Rail Revival | PNFC | Transport | TEI includes $104.000 million of Commonwealth funding.
Regional Rail Revival – Warrnambool Line Upgrade – Stage 2 (regional various) | Regional Rail Revival – Warrnambool Line Upgrade – Stage 2 | Existing | 260000000 | 1.2807 | 146000000 | 2746000 | 220059000 | qtr 1 2024‑25 | 2021–22 | 2024-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional | Regional Rail Revival |  | PNFC | Transport | Initiative funded in the 2020‑21 Budget. TEI includes $208.000 million of Commonwealth funding.
Western Highway duplication – Ballarat to Stawell (non‑metro various) | Western Highway duplication – Ballarat to Stawell | Existing | 505000000 | 0 | 0 | 225050000 | 162750000 | qtr 3 2015‑16 | 2014–15 | 2016-03-31 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Regional | Regional | Better Roads – Rural Arterial Roads projects |  | GG | Transport | Project TEI includes $404.000 million of Commonwealth funding.
Western Highway duplication – Ballarat to Stawell (non‑metro various) | Western Highway duplication – Ballarat to Stawell | Existing | 662300000 | 0 | 0 | 429815000 | 183115000 | qtr 3 2018‑19 | 2016–17 | 2019-03-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI includes $501.300 million of Commonwealth funding.
Western Highway duplication – Ballarat to Stawell (non‑metro various) | Western Highway duplication – Ballarat to Stawell | Existing | 662300000 | 0.31149 | 157300000 | 318596000 | 241022000 | qtr 4 2017‑18 | 2015–16 | 2018-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional | Better Roads – Rural Arterial Roads projects |  | GG | Transport | TEI has increased by $157.300 million. This is due to an increase in project scope to include Buangor to Ararat duplication. Project TEI includes $501.300 million of Commonwealth funding.
Western Highway duplication – Ballarat to Stawell (regional various) | Western Highway duplication – Ballarat to Stawell | Existing | 656357000 | 1.5236e-06 | 1000 | 512068000 | 104629000 | qtr 2 2021‑22 | 2019–20 | 2021-12-31 | Department of Transport | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI includes $499.380 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2021‑22 due to a change in scope.
Western Highway duplication – Ballarat to Stawell (regional various) | Western Highway duplication – Ballarat to Stawell | Existing | 656356000 | -0.0046722 | -3081000 | 490630000 | 157263000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport | The estimated completion date has been revised. TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $499.380 million of Commonwealth funding.
Western Highway duplication – Ballarat to Stawell (regional various) | Western Highway duplication – Ballarat to Stawell | Existing | 659437000 | -0.0043228 | -2863000 | 468958000 | 150550000 | qtr 3 2018-19 | 2017–18 | 2019-03-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Regional | Regional |  |  | GG | Transport | TEI excludes corporate costs. TEI includes $501.300 million of Commonwealth funding.
Western Highway duplication – Ballarat to Stawell (regional various) | Western Highway duplication – Ballarat to Stawell | Existing | 656357000 | 0 | 0 | 565967000 | 75390000 | tbc | 2021–22 | 2089-06-30 | Department of Transport | Department of Transport | Regional various | Regional | Urban Congestion Package |  | GG | Transport | TEI includes $499.380 million of Commonwealth funding. The estimated completion date is to be confirmed due to legal challenges.
Additional X’Trapolis Metropolitan Trains (metropolitan various) | Additional X’Trapolis Metropolitan Trains | New | 103501000 | 0 | 0 | 28079000 | 26522000 | qtr 2 2019-20 | 2018–19 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Additional X’Trapolis Metropolitan Trains (metropolitan various) | Additional X’Trapolis Metropolitan Trains | Existing | 103501000 | 0 | 0 | 47949000 | 4306000 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been extended to quarter 4 2019‑20 to accommodate the updated delivery schedule of the Digital Train Radio System.
Additional X’Trapolis Metropolitan Trains (metropolitan various) | Additional X’Trapolis Metropolitan Trains | Completed | 103501000 | 0 | 0 | 98464000 |  | qtr 4 2020‑21 | 2021–22 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport
Conventional signalling upgrade – Caulfield to Dandenong (metro various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | New | 360000000 | 0 | 0 | 0 | 315000000 | qtr 2 2018‑19 | 2015–16 | 2018-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | Existing | 608281000 | 0 | 0 | 550170000 | 0 | qtr 2 2019-20 | 2018–19 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Conventional signalling upgrade – Caulfield to Dandenong (metro various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | Existing | 360000000 | 0 | 0 | 45000000 | 213000000 | qtr 4 2018‑19 | 2016–17 | 2019-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | Existing | 608281000 | 0.68967 | 248281000 | 305480000 | 58110000 | qtr 2 2018-19 | 2017–18 | 2018-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) TEI incorporates $248.281 million for power and associated infrastructure works initially reported as part of High-capacity metro trains. The publication title is updated since 2016-17 Budget Paper No. 4.
Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | Existing | 608121000 | -0.00026304 | -160000 | 561183000 | 0 | qtr 2 2019‑20 | 2019–20 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI excludes $0.160 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | Completed | 608121000 | 0 | 0 | 589631000 |  | qtr 2 2020‑21 | 2021–22 | 2020-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport
Cranbourne Line Duplication planning and development (metropolitan various) | Cranbourne Line Duplication planning and development | New | 750000000 | 0 | 0 | 0 | 737800000 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Cranbourne Line Duplication (metropolitan various) | Cranbourne Line Duplication planning and development | Existing | 765000000 | 0.02 | 15000000 | 411999000 | 115440000 | qtr 1 2023‑24 | 2021–22 | 2023-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport | TEI has increased by $15.000 million through additional Growth Areas Infrastructure Contribution funding due to the addition of a shared user path to the project scope. Estimated completion date has been revised to reflect a revised schedule of works.
Cranbourne Pakenham and Sunbury Line Upgrades (metropolitan various) | Cranbourne Pakenham and Sunbury Line Upgrades | New | 539540000 | 0 | 0 | 113104000 | 51368000 | qtr 2 2019-20 | 2018–19 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Cranbourne Pakenham and Sunbury Line Upgrades(metropolitan various) | Cranbourne Pakenham and Sunbury Line Upgrades | Existing | 539540000 | 0 | 0 | 456926000 | 0 | qtr 2 2019‑20 | 2019–20 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Cranbourne Pakenham and Sunbury Line Upgrades (metropolitan various) | Cranbourne Pakenham and Sunbury Line Upgrades | Completed | 539390000 | -0.00027801 | -150000 | 532968000 |  | qtr 2 2020‑21 | 2021–22 | 2020-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport | TEI excludes $0.150 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Cranbourne‑Pakenham rail corridor project (metro various) | Cranbourne‑Pakenham rail corridor project | New | 2500000000 | 0 | 0 | 5000000 | 2475000000 | 2018‑19 | 2014–15 | 2018-07-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport
Cranbourne‑Pakenham rail corridor project (metro various) | Cranbourne‑Pakenham rail corridor project | Discontinued | 0 | -1 | -2500000000 | 0 | 0 | Discontinued | 2015–16 |  | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | Project has ceased and been replaced by the Conventional signalling upgrade – Caulfield to Dandenong, Level Crossing Removal Program, and High‑capacity metro trains.
East West Link – Western section (metro) | East West Link – Western section | New | 10000000000 | 0 | 0 | 4000000 | 9896000000 | 2022‑23 | 2014–15 | 2022-07-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | The TEI includes Commonwealth funding of $1.500 billion. The capital cost of this project is estimated to be between $8 billion and $10 billion.
Hurstbridge Line Upgrade Stage 2 (metropolitan various) | Hurstbridge Line Upgrade Stage 2 | New | 530000000 | 0 | 0 | 0 | 508500000 | tbc | 2019–20 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The completion date is subject to the completion of planning for the project.
Hurstbridge Line Upgrade Stage 2 (metropolitan various) | Hurstbridge Line Upgrade Stage 2 | Existing | 536986000 | 0.013181 | 6986000 | 115224000 | 30043000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport | TEI has increased by $7.000 million due to additional scope. TEI excludes $0.014 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
M80 Ring Road upgrade (north and west metropolitan region) | M80 Ring Road upgrade | New | 673077000 | 0 | 0 | 0 | 639423000 | qtr 3 2020-21 | 2017–18 | 2021-03-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | TEI includes $336.538 million of Commonwealth funding for the capital component of this initiative.
M80 Ring Road upgrade (north and west metropolitan region) | M80 Ring Road upgrade | Existing | 673077000 | 0 | 0 | 66244000 | 553993000 | qtr 3 2022‑23 | 2019–20 | 2023-03-31 | Department of Transport | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | TEI includes $336.540 million of Commonwealth funding. The estimated completion date has been revised to quarter 3 2022‑23 due to procurement timing.
M80 Ring Road upgrade (north and west metropolitan region) | M80 Ring Road upgrade | Existing | 673077000 | 0 | 0 | 26093000 | 498205000 | qtr 3 2020-21 | 2018–19 | 2021-03-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | TEI includes $336.540 million of Commonwealth funding for the capital component of this initiative.
M80 Ring Road upgrade (north and west metropolitan region) | M80 Ring Road upgrade | Existing | 668257000 | -0.0071611 | -4820000 | 319014000 | 232895000 | qtr 3 2022‑23 | 2021–22 | 2023-03-31 | Department of Transport | Department of Transport | North and west metropolitan region | Metropolitan |  |  | GG | Transport | TEI has decreased by $4.820 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. TEI includes $336.540 million of Commonwealth funding.
Melbourne Metro Rail Project (metro various) | Metro Tunnel | New | 11000000000 | 0 | 0 | 40000000 | 10837600000 | 2026 | 2015–16 | 2026-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The TEI includes funding announced in Getting On With It.
Melbourne Metro Tunnel (metro various) | Metro Tunnel | Existing | 10900000000 | -0.0090909 | -100000000 | 244420000 | 9873500000 | qtr 4 2025‑26 | 2016–17 | 2026-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The TEI includes funding announced as part of the 2015‑16 Budget Information Paper Getting On With It. This amount excludes financing costs.
Metro Tunnel (metropolitan various) | Metro Tunnel | Existing | 10992524000 | -0.003488 | -38476000 | 1628769000 | 8793037000 | qtr 2 2025-26 | 2018–19 | 2025-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised. TEI excludes $73.476 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. The TEI excludes financing costs. The TEI includes $35.000 million for High Capacity Signalling Equipment on board new trains allocated in 2017-18 Budget Update.
Metro Tunnel (metropolitan various) | Metro Tunnel | Existing | 11031000000 | 0.012018 | 131000000 | 929391000 | 9246097000 | qtr 4 2025-26 | 2017–18 | 2026-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI has increased by $131.000 million due to a change in project scope. This includes a reallocation of the High Capacity Signalling Trial (HCST) funding provided in the 2015-16 Budget to support HCS implementation on the Metro Tunnel project.
Metro Tunnel (metropolitan various) | Metro Tunnel | Existing | 10883144000 | -0.0099504 | -109380000 | 4460097000 | 4832050000 | qtr 2 2025‑26 | 2019–20 | 2025-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI excludes $109.380 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. TEI excludes financing costs.
Metro Tunnel (metropolitan various) | Metro Tunnel | Existing | 12255144000 | 0.12607 | 1372000000 | 7518633000 | 2876125000 | qtr 2 2025‑26 | 2021–22 | 2025-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport | TEI has increased by $1 372.000 million due to additional scope. TEI excludes $182.856 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. TEI excludes financing costs.
Melbourne Rail Link (metro various) | Melbourne Rail Link | New | 11000000000 | 0 | 0 | 0 | 10960000000 | from 2023‑24 | 2014–15 | 2023-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | Includes the remaining funding from the Melbourne Metro Rail Tunnel.
Melbourne Rail Link (metro various) | Melbourne Rail Link | Discontinued | 0 | -1 | -11000000000 | 0 | 0 | Discontinued | 2015–16 |  | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Metro Level Crossing Blitz program (metro various) | Metro Level Crossing Blitz program | New | 68810000 | 0 | 0 | 42336000 | 1527000 | qtr 4 2016‑17 | 2015–16 | 2017-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport
Metro Level Crossing Blitz program (metro various) | Metro Level Crossing Blitz program | Existing | 68810000 | 0 | 0 | 63670000 | 0 | qtr 4 2016‑17 | 2016–17 | 2017-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport
More E-Class trams and infrastructure (metropolitan various) | More E-Class trams and infrastructure | New | 215462000 | 0 | 0 | 0 | 187292000 | qtr 3 2018-19 | 2017–18 | 2019-03-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
More E-Class trams and infrastructure (metropolitan various) | More E-Class trams and infrastructure | Existing | 215462000 | 0 | 0 | 20366000 | 122070000 | qtr 4 2020-21 | 2018–19 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised.
More E‑Class trams and infrastructure (metropolitan various) | More E-Class trams and infrastructure | Existing | 215462000 | 0 | 0 | 56358000 | 89752000 | qtr 4 2021‑22 | 2019–20 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised to quarter 4 2021‑22 as works are progressing to secure land holdings for the power substations.
New E‑Class trams (metro various) | New E‑Class trams | New | 294770000 | 0 | 0 | 0 | 257470000 | qtr 2 2018‑19 | 2015–16 | 2018-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
New E-Class trams (metropolitan various) | New E‑Class trams | Existing | 294770000 | 0 | 0 | 75550000 | 149830000 | qtr 2 2019-20 | 2017–18 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The estimated project completion date reflects the revised scope of the project in line with the network development strategy.
New E‑Class trams (metropolitan various) | New E‑Class trams | Existing | 280204000 | 0 | 0 | 160836000 | 82865000 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised to quarter 4 2020‑21 as works are progressing to secure land holdings for the power substations.
New E‑Class trams (metro various) | New E‑Class trams | Existing | 294770000 | 0 | 0 | 26700000 | 206720000 | qtr 2 2018‑19 | 2016–17 | 2018-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
New E-Class trams (metropolitan various) | New E‑Class trams | Existing | 280204000 | -0.049415 | -14566000 | 116714000 | 34259000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI has reduced by $14.566 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
New E‑Class trams (metropolitan various) | New E‑Class trams | Completed | 146041000 | -0.4788 | -134163000 | 146040000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport | TEI has decreased by $120.270 million due to movement of scope to the E‑Class Tram Infrastructure Program, and by $13.893 million due to reprioritisation to High Capacity Metro Trains.
New Trams (metropolitan various) | New Trams | New | 144720000 | 0 | 0 | 0 | 76200000 | tbc | 2019–20 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
New Trams (metropolitan various) | New Trams | Existing | 110160000 | -0.23881 | -34560000 | 61002000 | 17350000 | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport
New trains for Sunbury (metropolitan various) | New trains for Sunbury | New | 2050365000 | 0 | 0 | 0 | 1848299000 | qtr 2 2024‑25 | 2019–20 | 2024-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
New trains for Sunbury (metropolitan various) | New trains for Sunbury | Existing | 1972995000 | -0.037735 | -77370000 | 371007000 | 1327816000 | qtr 2 2024‑25 | 2021–22 | 2024-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport | TEI has decreased by $61.500 million due to other corridor works, and excludes $15.870 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Suburban Roads Upgrade (metropolitan various) | Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade | New | 2268800000 | 0 | 0 | 2770000 | 2208800000 | qtr 2 2022-23 | 2018–19 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | Yan Yean Road upgrade – Stage 2, will be delivered as part of this initiative. TEI includes estimated PPP finance lease liabilities.
Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade (metropolitan) | Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade | Existing | 2268800000 | 0 | 0 | 63430000 | 1964208000 | qtr 2 2023‑24 | 2019–20 | 2023-12-31 | Department of Transport | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | TEI includes estimated PPP financial liabilities. TEI includes $1,140 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2023‑24. Yan Yean Road has been funded under this initiative but will be delivered separately to the PPP.
Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade (statewide) | Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade | Existing | 2208943000 | -0.026383 | -59857000 | 268734000 | 1420209000 | qtr 2 2025‑26 | 2021–22 | 2025-12-31 | Department of Transport | Department of Transport | Statewide | Statewide | Rural and Regional Roads Package |  | GG | Transport | TEI has decreased by $59.858 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. TEI includes $1,140.000 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2025‑26 in line with public commitments.
Western Roads upgrade (metropolitan various) | Western Roads upgrade | New | 936810000 | 0 | 0 | 120114000 | 771271000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | TEI includes estimated PPP finance lease liability. This was previously reported as Western Suburbs Roads Package.
Western Roads upgrade (metropolitan various) | Western Roads upgrade | Existing | 936810000 | 0 | 0 | 718604000 | 0 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Department of Transport | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | TEI includes estimated PPP financial liability.
Western Roads upgrade (metropolitan various) | Western Roads upgrade | Completed | 986810000 | 0.053373 | 50000000 | 943147000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Transport | Department of Transport | Metropolitan various | Metropolitan | Rural and Regional Roads Package |  | GG | Transport | TEI has increased by $50.000 million.
40 New trains for Melbourne commuters – stage 1 (metro various) | 40 New trains for Melbourne commuters – stage 1 | Existing | 210360000 | 0 | 0 | 147146000 | 2559000 | qtr 4 2015‑16 | 2014–15 | 2016-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
40 New trains for Melbourne commuters – stage 1 (metro various) | 40 New trains for Melbourne commuters – stage 1 | Existing | 207360000 | -0.014261 | -3000000 | 185672000 | 5694000 | qtr 4 2015‑16 | 2015–16 | 2016-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI has decreased by $3.000 million. This is due to project savings.
Bayside rail improvements (metro various) | Bayside rail improvements | Existing | 115000000 | 0 | 0 | 10000000 | 37400000 | qtr 4 2016‑17 | 2014–15 | 2017-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI has been increased by $15.000 million due to a change in project scope.
Bayside rail improvements (metropolitan various) | Bayside rail improvements | Existing | 115000000 | 0 | 0 | 110094000 | 0 | qtr 4 2017-18 | 2017–18 | 2018-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The project completion date has been revised to include the additional scope of the X’Trapolis Train Maintenance facility at Newport with completion expected in 2017-18.
Bayside rail improvements (metropolitan various) | Bayside rail improvements | Existing | 115000000 | 0 | 0 | 113395000 | 0 | qtr 2 2018-19 | 2018–19 | 2018-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised. The estimated completion date has been revised due to additional scope at the Newport Maintenance Facility.
Bayside rail improvements (metropolitan various) | Bayside rail improvements | Existing | 115000000 | 0 | 0 | 111995000 | 0 | qtr 2 2019‑20 | 2019–20 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised to quarter 2 2019‑20 to integrate train operational requirements, including at the Newport Maintenance Facility.
Bayside rail improvements (metro various) | Bayside rail improvements | Existing | 115000000 | 0 | 0 | 69287000 | 12334000 | qtr 4 2016‑17 | 2015–16 | 2017-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Bayside rail improvements (metro various) | Bayside rail improvements | Existing | 115000000 | 0 | 0 | 102666000 | 0 | qtr 4 2016‑17 | 2016–17 | 2017-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Bayside rail improvements (metropolitan various) | Bayside rail improvements | Completed | 115000000 | 0 | 0 | 115000000 |  | qtr 3 2020‑21 | 2021–22 | 2021-03-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport
East West Link – Eastern section (metro various) | East West Link – Eastern section | Existing | 8000000000 | 0 | 0 | 191000000 | 7519000000 | qtr 2 2019‑20 | 2014–15 | 2019-12-31 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | Project previously reported as East West Link – Stage 1 (metro various).
Keeping Victorians moving (metropolitan) | Keeping Victorians moving | Existing | 174629000 | 0 | 0 | 56156000 | 18622000 | qtr 4 2023‑24 | 2021–22 | 2024-06-30 | Department of Transport | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | Initiative funded in the 2020-21 Budget. TEI has decreased by $1.320 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
M80 Upgrade (metro various) | M80 Upgrade | Existing | 864610000 | 0 | 0 | 844214000 | 14088000 | qtr 2 2014‑15 | 2014–15 | 2014-12-31 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | Funding provided by the Commonwealth. TEI has decreased by $35.390 million due to lower than anticipated construction costs.
Melbourne strategic assessment (metro various) | Melbourne strategic assessment | Existing | 334300000 | 0 | 0 | 25170000 | 304130000 | qtr 2 2053‑54 | 2014–15 | 2053-12-31 | Department of Environment and Primary Industries | Department of Environment, Land, Water and Planning | Metropolitan | Metropolitan |  |  | GG | Environment
Melbourne strategic assessment (metro various) | Melbourne strategic assessment | Existing | 334300000 | 0 | 0 | 21693000 | 307607000 | qtr 2 2053‑54 | 2015–16 | 2053-12-31 | Department of Environment, Land, Water and Planning | Department of Environment, Land, Water and Planning | Metropolitan | Metropolitan |  |  | GG | Environment
Melbourne strategic assessment (metro various) | Melbourne strategic assessment | Existing | 334300000 | 0 | 0 | 27316000 | 296984000 | qtr 2 2053‑54 | 2016–17 | 2053-12-31 | Department of Environment Land Water and Planning | Department of Environment, Land, Water and Planning | Metropolitan | Metropolitan |  |  | GG | Environment
Melbourne strategic assessment (metropolitan various) | Melbourne strategic assessment | Existing | 334300000 | 0 | 0 | 30368000 | 293932000 | qtr 2 2053-54 | 2017–18 | 2053-12-31 | Department of Environment, Land, Water and Planning | Department of Environment, Land, Water and Planning | Metropolitan | Metropolitan |  |  | GG | Environment
Melbourne strategic assessment (metropolitan various) | Melbourne strategic assessment | Existing | 330900000 | 0 | 0 | 36914000 | 283986000 | qtr 2 2053‑54 | 2019–20 | 2053-12-31 | Department of Environment, Land, Water and Planning | Department of Environment, Land, Water and Planning | Metropolitan | Metropolitan |  |  | GG | Environment
Melbourne strategic assessment (metropolitan various) | Melbourne strategic assessment | Existing | 330900000 | -0.010171 | -3400000 | 27425000 | 293475000 | qtr 2 2053-54 | 2018–19 | 2053-12-31 | Department of Environment, Land, Water and Planning | Department of Environment, Land, Water and Planning | Metropolitan | Metropolitan |  |  | GG | Environment | The TEI has been revised from $334.300 million to $330.900 million. The decrease is the result of $3.400 million reclassified to output.
Metropolitan rail infrastructure renewal program (metro various) | Metropolitan rail infrastructure renewal program | Existing | 748695000 | 0 | 0 | 283624000 | 338205000 | qtr 4 2017‑18 | 2014–15 | 2018-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2012‑13 to 2017‑18. The TEI has reduced, as this is a rolling program of works and the TEI varies from year to year.
Metropolitan rail infrastructure renewal program (metro various) | Metropolitan rail infrastructure renewal program | Existing | 844454000 | 0.1279 | 95759000 | 264535000 | 452189000 | qtr 4 2019‑20 | 2015–16 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2013‑14 to 2019‑20. The TEI has increased, as this is a rolling program of works and the TEI varies from year to year.
Metropolitan rail infrastructure renewal program (metro various) | Metropolitan rail infrastructure renewal program | Existing | 821647000 | -0.027008 | -22807000 | 249225000 | 452656000 | qtr 4 2020‑21 | 2016–17 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2014‑15 to 2020‑21. The TEI has increased, as this is a rolling program of works and the TEI varies from year to year.
Metropolitan rail infrastructure renewal program (metropolitan various) | Metropolitan rail infrastructure renewal program | Existing | 699891000 | -0.14819 | -121756000 | 247236000 | 339696000 | qtr 4 2021-22 | 2017–18 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2015-16 to 2020-21. As this is a rolling program of works, the TEI varies from year to year.
Metropolitan rail infrastructure renewal program (metropolitan various) | Metropolitan rail infrastructure renewal program | Existing | 1528938000 | 1.1845 | 829047000 | 297420000 | 960960000 | qtr 4 2024-25 | 2018–19 | 2025-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2016-17 to 2024-25, including funding provided in the 2017-18 Budget Update for the management of the new train and tram franchise agreement that commenced on 30 November 2017.
Metropolitan rail infrastructure renewal program (metropolitan various) | Metropolitan rail infrastructure renewal program | Existing | 1489361000 | -0.025885 | -39577000 | 441697000 | 772800000 | qtr 4 2024‑25 | 2019–20 | 2025-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI has been reduced by $4.450 million due to savings, and $35.127 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. As a rolling program of works, the TEI varies from year to year. TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2016‑17 to 2024‑25, including funding provided in the 2017‑18 Budget Update for the management of the new train and tram franchise agreement that commenced on 30 November 2017.
Metropolitan rail infrastructure renewal program (metropolitan various) | Metropolitan rail infrastructure renewal program | Existing | 1625080000 | 0.091126 | 135719000 | 681600000 | 682370000 | qtr 4 2025‑26 | 2021–22 | 2026-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport | As a rolling program of works, the TEI varies from year to year. TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2018‑19 to 2025‑26.
Metropolitan rolling stock (metro various) | Metropolitan rolling stock | Existing | 1175317000 | 0 | 0 | 1092139000 | 42428000 | qtr 4 2015‑16 | 2014–15 | 2016-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Metropolitan rolling stock (metro various) | Metropolitan rolling stock | Existing | 1175317000 | 0 | 0 | 1111712000 | 22346000 | qtr 4 2015‑16 | 2015–16 | 2016-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
New stations in growth areas (metro various) | New stations in growth areas | Existing | 188500000 | 0 | 0 | 164783000 | 0 | qtr 4 2014‑15 | 2014–15 | 2015-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
New stations in growth areas (metro various) | New stations in growth areas | Existing | 183500000 | -0.026525 | -5000000 | 163160000 | 26000 | qtr 4 2015‑16 | 2015–16 | 2016-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI has decreased by $5.000 million. This is due to project savings.
New trains for Melbourne commuters (metro various) | New trains for Melbourne commuters | Existing | 178068000 | 0 | 0 | 28863000 | 52032000 | qtr 4 2015‑16 | 2014–15 | 2016-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
New trains for Melbourne commuters (metro various) | New trains for Melbourne commuters | Existing | 145068000 | -0.18532 | -33000000 | 108862000 | 8521000 | qtr 4 2015‑16 | 2015–16 | 2016-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI has decreased by $33.000 million. This is due to project savings.
Tram procurement and supporting infrastructure (metro various) | Tram procurement and supporting infrastructure | Existing | 804456000 | 0 | 0 | 242646000 | 326905000 | qtr 4 2017‑18 | 2014–15 | 2018-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Tram procurement and supporting infrastructure (metropolitan various) | Tram procurement and supporting infrastructure | Existing | 804456000 | 0 | 0 | 673724000 | 25514000 | qtr 2 2018-19 | 2017–18 | 2018-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The project completion date has been revised to reflect the impact of the unavailability of suitable land to support the tram traction power upgrade project.
Tram procurement and supporting infrastructure (metropolitan various) | Tram procurement and supporting infrastructure | Existing | 804456000 | 0 | 0 | 648564000 | 38824000 | qtr 2 2019-20 | 2018–19 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised.
Tram procurement and supporting infrastructure (metro various) | Tram procurement and supporting infrastructure | Existing | 804456000 | 0 | 0 | 421273000 | 207504000 | qtr 4 2017‑18 | 2015–16 | 2018-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Tram procurement and supporting infrastructure (metro various) | Tram procurement and supporting infrastructure | Existing | 804456000 | 0 | 0 | 605094000 | 40087000 | qtr 4 2017‑18 | 2016–17 | 2018-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Tram procurement and supporting infrastructure (metropolitan various) | Tram procurement and supporting infrastructure | Existing | 804205000 | -0.00031201 | -251000 | 700787000 | 34486000 | qtr 4 2021‑22 | 2019–20 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI has reduced by $0.250 million due to savings. The estimated completion date has been revised to quarter 4 2021‑22 due to remediation works and the availability of land for substation sites.
Tram procurement and supporting infrastructure (metropolitan various) | Tram procurement and supporting infrastructure | Completed | 344162000 | -0.57205 | -460043000 | 344162000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan | Regional Rail Revival |  | PNFC | Transport | TEI has decreased by $448.828 million due to movement of scope to the E‑Class Tram Infrastructure Program, and by $11.216 million due to reprioritisation to High Capacity Metro Trains.
28 more high capacity metro trains (metro various) | 28 more high capacity metro trains | New | 875000000 | 0 | 0 | 0 | 0 | qtr1 2023‑24 | 2016–17 | 2023-09-30 | Victorian Rail Track (VicTrack) | Department of Transport | Metropolitan | Metropolitan |  | High Capacity Metro Trains | PNFC | Transport | The TEI is additional to funding of $1.301 billion in the 2015‑16 Budget. The new trains and depot will be procured as a public private partnership and the final financial impacts will be confirmed following the conclusion of the procurement process.
75 by 2025 (Level Crossing Removal) (metropolitan various) | 75 by 2025 (Level Crossing Removal) | New | 6550000000 | 0 | 0 | 0 | 6319979000 | qtr 2 2025‑26 | 2019–20 | 2025-12-31 | Department of Transport | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport
75 by 2025 (Level Crossing Removal) (metropolitan various) | 75 by 2025 (Level Crossing Removal) | Existing | 6550000000 | 0 | 0 | 1481496000 | 3073650000 | qtr 2 2025‑26 | 2021–22 | 2025-12-31 | Department of Transport | Department of Transport | Metropolitan various | Metropolitan |  | LXRP | GG | Transport
High‑capacity metro trains (metro various) | High Capacity Metro Trains | New | 1301000000 | 0 | 0 | 0 | 1279078000 | qtr 4 2021‑22 | 2015–16 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  | High Capacity Metro Trains | PNFC | Transport | Includes procurement of 37 high capacity metropolitan trains, new maintenance depot and associated network upgrades. New trains and depot to be procured as a public private partnership. The total estimated investment includes estimated capital costs only.
High Capacity Metro Trains (metro various) | High Capacity Metro Trains | Existing | 1301000000 | 0 | 0 | 27303000 | 1238606000 | qtr 4 2021‑22 | 2016–17 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  | High Capacity Metro Trains | PNFC | Transport
High Capacity Metro Trains (metropolitan various) | High Capacity Metro Trains | Existing | 2176000000 | 0 | 0 | 595958000 | 1284018000 | qtr 1 2023‑24 | 2019–20 | 2023-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  | High Capacity Metro Trains | PNFC | Transport | TEI includes financing costs.
High Capacity Metro Trains (metropolitan various) | High Capacity Metro Trains | Existing | 2176000000 | 0.67256 | 875000000 | 96720000 | 2007916000 | qtr 1 2023-24 | 2018–19 | 2023-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  | High Capacity Metro Trains | PNFC | Transport | TEI includes state costs, state contributions and financing costs. TEI reflects combined funding of $1 301.000 million in the 2015‑16 Budget and funding of $875.000 million in the 2016-17 Budget.
High Capacity Metro Trains (metropolitan various) | High Capacity Metro Trains | Existing | 2243476000 | 0.031009 | 67476000 | 1354488000 | 564866000 | qtr 1 2023‑24 | 2021–22 | 2023-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  | High Capacity Metro Trains | PNFC | Transport
Level Crossing Removal Program (metro various) | Level Crossing Removal Program | New | 6000000000 | 0 | 0 | 3000000 | 0 | qtr 2 2022‑23 | 2015–16 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport | The TEI includes funding announced in Getting On With It, February 2015. TEI relates to funding for the full eight year program. Funding will be released progressively as planning for packages of work is completed and projects released to market for tender. Includes the remaining funding for Metro Level Crossing Blitz (metro various).
Level Crossing Removal Program (metro various) | Level Crossing Removal Program | Existing | 6000000000 | 0 | 0 | 302700000 | 5061300000 | qtr 2 2022‑23 | 2016–17 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport | The TEI includes funding approved as part of the Getting On With It Initiative. Funding will be released progressively as planning for packages of work are completed and projects released to market for tender.
Level Crossing Removal Program (metropolitan various) | Level Crossing Removal Program | Existing | 6759019000 | -0.00038216 | -2584000 | 3958293000 | 1785573000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Department of Transport | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport | TEI includes $151.000 million of Commonwealth funding for Main Road St Albans, and excludes $119.753 million recognised as operating instead of capital in line with accounting standards.
Level Crossing Removal Program (metropolitan various) | Level Crossing Removal Program | Existing | 6878756000 | 0.14646 | 878756000 | 1942250000 | 3764260000 | qtr 2 2022-23 | 2017–18 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport | Estimated total cost of the program to remove 50 level crossings across metropolitan Melbourne. TEI includes the cost of the 10 level crossings removed, which were previously listed separately under the initiative titled ‘Level crossing removal projects’ in 2016-17 Budget Paper No. 4. TEI includes $151.000 million of Commonwealth funding for Main Road (St. Albans)
Level Crossing Removal Program (metropolitan various) | Level Crossing Removal Program | Existing | 6761603000 | -0.017031 | -117153000 | 3464267000 | 2371117000 | qtr 2 2022-23 | 2018–19 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport | TEI excludes $117.153 million now recognised as operating instead of capital in line with accounting standards. TEI includes the cost of level crossings removed to date, including four which were previously listed separately under the initiative titled Level crossing removal projects in 2017‑18 Budget Paper No. 4. TEI includes $151.000 million of Commonwealth funding for Main Road (St. Albans).
Level Crossing Removal Program (metropolitan various) | Level Crossing Removal Program | Existing | 6759019000 | 0 | 0 | 5472003000 | 663637000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Transport | Department of Transport | Metropolitan various | Metropolitan |  |  | GG | Transport | TEI includes $151.000 million of Commonwealth funding for Main Road St Albans, and excludes $119.753 million reclassified as operating instead of capital in line with accounting standards.
Metropolitan Network Modernisation Program (metropolitan various) | Metropolitan Network Modernisation Program | New | 1392221000 | 0 | 0 | 458453000 | 640982000 | qtr 2 2022-23 | 2017–18 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport | These comprise a range of network improvements, such as station works, power and other infrastructure upgrades and future proofing works, that are being delivered jointly with the Level Crossing Removal Program.
Metropolitan Network Modernisation Program (metropolitan various) | Metropolitan Network Modernisation Program | Existing | 1392221000 | 0 | 0 | 802075000 | 381199000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Department of Transport | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport | These works comprise a range of network improvements, such as station works, power, signalling and other infrastructure upgrades and future‑proofing works, that are being delivered jointly with the Level Crossing Removal Program.
Metropolitan Network Modernisation Program (metropolitan various) | Metropolitan Network Modernisation Program | Existing | 1392221000 | 0 | 0 | 707670000 | 493787000 | qtr 2 2022-23 | 2018–19 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport | These works comprise a range of network improvements, such as station works, power, signalling and other infrastructure upgrades and future-proofing works, that are being delivered jointly with the Level Crossing Removal Program.
Metropolitan Network Modernisation Program (metropolitan various) | Metropolitan Network Modernisation Program | Existing | 1392221000 | 0 | 0 | 1121616000 | 142201000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Transport | Department of Transport | Metropolitan various | Metropolitan |  |  | GG | Transport | These works comprise a range of network improvements, such as station works, power, signalling and other infrastructure upgrades and future‑proofing works, that are being delivered jointly with the Level Crossing Removal Program.
Monash Freeway upgrade – EastLink to Clyde Road (metropolitan various) | Monash Freeway upgrade – EastLink to Clyde Road | New | 282978000 | 0 | 0 | 126261000 | 32154000 | qtr 2 2018-19 | 2017–18 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan | West Gate Tunnel Project (metropolitan various) | West Gate Tunnel Whole(metropolitan various) | GG | Transport | TEI excludes corporate costs.
Monash Freeway upgrade – EastLink to Clyde Road (metropolitan various) | Monash Freeway upgrade – EastLink to Clyde Road | Completed | 282879000 | 0 | 0 | 263173000 | 0 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Department of Transport | Department of Transport | Metropolitan | Metropolitan | West Gate Tunnel Project | West Gate Tunnel Whole(metropolitan various) | GG | Transport
Monash Freeway upgrade – EastLink to Clyde Road (metropolitan various) | Monash Freeway upgrade – EastLink to Clyde Road | Existing | 282879000 | -0.00034985 | -99000 | 253828000 | 0 | qtr 2 2018-19 | 2018–19 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan | West Gate Tunnel Project | West Gate Tunnel Whole(metropolitan various) | GG | Transport
West Gate Tunnel (metropolitan various) | West Gate Tunnel | New | 6344432000 | 0 | 0 | 279761000 | 5774286000 | qtr 2 2022-23 | 2018–19 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan | West Gate Tunnel Project | West Gate Tunnel Whole(metropolitan various) | GG | Transport
West Gate Tunnel (metropolitan various) | West Gate Tunnel | Existing | 6301924000 | -0.0067 | -42508000 | 2529738000 | 2170407000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Department of Transport | Department of Transport | Metropolitan | Metropolitan | West Gate Tunnel Project | West Gate Tunnel Whole(metropolitan various) | GG | Transport | TEI excludes $42.508 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
West Gate Tunnel Project – West Gate Tunnel (metropolitan various) | West Gate Tunnel | Existing | 6288273000 | -0.0021662 | -13651000 | 3668736000 | 2064181000 | tbc | 2021–22 | 2089-06-30 | Department of Transport | Department of Transport | Metropolitan various | Metropolitan | Urban Congestion Package | West Gate Tunnel Whole(metropolitan various) | GG | Transport | TEI excludes $56.470 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. Transurban has advised the ASX that it no longer believes the project can be completed in 2023.
Carlton redevelopment – 246 units/ sites (North‑West metropolitan) | Carlton redevelopment – 246 units/ sites | Existing | 146570000 | 0 | 0 | 144064000 | 2000000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Director of Housing | Director of Housing | Metropolitan | Metropolitan |  |  | PNFC | Health and human services | The project’s estimated completion date has been extended to quarter 2 2022‑23 due to poor pre‑sales of the private apartments.
Carlton redevelopment – 246 units/sites (North-West metro) | Carlton redevelopment – 246 units/ sites | Existing | 146401000 | 0 | 0 | 143966000 | 87000 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Director of Housing | Director of Housing | Metropolitan | Metropolitan |  |  | PNFC | Health and human services
Carlton redevelopment – 246 units/sites (North‑West metro) | Carlton redevelopment – 246 units/ sites | Existing | 146401000 | 0 | 0 | 141186000 | 2990000 | qtr 4 2018‑19 | 2016–17 | 2019-06-30 | Director of Housing | Director of Housing | Metropolitan | Metropolitan |  |  | PNFC | Health and human services
Carlton redevelopment – 246 units/sites (North‑West metro) | Carlton redevelopment – 246 units/ sites | Existing | 146401000 | -0.00014342 | -21000 | 138871000 | 6880000 | qtr 4 2018‑19 | 2015–16 | 2019-06-30 | Director of Housing | Director of Housing | Metropolitan | Metropolitan |  |  | PNFC | Health and human services
Carlton redevelopment – 246 units/sites (North-West metropolitan) | Carlton redevelopment – 246 units/ sites | Existing | 146570000 | 0.0011544 | 169000 | 144170000 | 1500000 | qtr 4 2018-19 | 2018–19 | 2019-06-30 | Director of Housing | Director of Housing | Metropolitan | Metropolitan |  |  | PNFC | Health and human services | The project TEI has increased to $146.57 million due to latent site conditions.
Carlton redevelopment – 246 units/ sites (Carlton) | Carlton redevelopment – 246 units/ sites | Existing | 146422000 | 0 | 0 | 139632000 | 5350000 | qtr 2 2018‑19 | 2014–15 | 2018-12-31 | Director of Housing | Director of Housing | Carlton | Metropolitan |  |  | PNFC | Health and human services
Carlton redevelopment – 246 units/sites (North‑West metropolitan) | Carlton redevelopment – 246 units/ sites | Existing | 145793000 | -0.0053012 | -777000 | 143952000 | 900000 | qtr 4 2022‑23 | 2021–22 | 2023-06-30 | Director of Housing | Director of Housing | North-west metropolitan | Metropolitan |  |  | PNFC | Health and human services
Level crossing removal projects (metro various) | Level crossing removal projects | Existing | 659319000 | 0 | 0 | 344766000 | 67753000 | qtr 4 2016‑17 | 2016–17 | 2017-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport | TEI represents funding provided for level crossing removals Blackburn Road (Blackburn), Burke Road (Glen Iris), Main Road (St Albans) and North Road (Ormond). Burke Road (Glen Iris) level crossing removal is expected to be completed before 30 June 2016. TEI includes $151.000 million of Commonwealth funding for Main Road (St Albans).
Level crossing removal projects (metro various) | Level crossing removal projects | Existing | 659319000 | 0.4417 | 202000000 | 34892000 | 325505000 | qtr 4 2016‑17 | 2015–16 | 2017-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  | LXRP | GG | Transport | Includes level crossing removals at Blackburn Road (Blackburn), Burke Road (Glen Iris) and North Road (Ormond). TEI includes $151.000 million of Commonwealth funding for Main Road (St Albans) previously reported within Regional Rail Link. Project renamed from Metro Level Crossing Blitz Program.
Metro Level Crossing Blitz program | Level crossing removal projects | New | 457319000 | 0 | 0 | 0 | 422919000 | qtr 4 2017‑18 | 2014–15 | 2018-06-30 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Unspecified | Unspecified |  | LXRP | GG | Transport
Nine additional X’Trapolis trains (metropolitan various) | Nine additional X’Trapolis trains | Existing | 175000000 | 0 | 0 | 130800000 | 0 | qtr 4 2018-19 | 2018–19 | 2019-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport
Nine additional X’Trapolis trains (metropolitan various) | Nine additional X’Trapolis trains | Completed | 174637000 | -0.0020743 | -363000 | 147553000 | 0 | qtr 4 2021‑22 | 2019–20 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan | Metropolitan |  |  | PNFC | Transport | TEI has reduced by $0.363 million due to savings.
Nine additional X’Trapolis trains (statewide) | Nine additional X’Trapolis trains | New | 175000000 | 0 | 0 | 63000000 | 49000000 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Statewide | Statewide |  |  | PNFC | Transport
CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport (metropolitan various) | CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport | Completed | 496588000 | 0.00018933 | 94000 | 428663000 | 0 | qtr 4 2020-21 | 2018–19 | 2021-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | TEI for project has changed as a result of corporate cost adjustment. TEI includes $200.000 million Commonwealth funding.
CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport (metropolitan various) | CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport | Existing | 496494000 | -0.00086532 | -430000 | 286695000 | 61655000 | qtr 4 2017-18 | 2017–18 | 2018-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | The estimated completion date has been extended. TEI excludes corporate costs. TEI includes $200.000 million of Commonwealth funding and covers the total funding of the state delivered components of the project.
CityLink‑Tulla widening project – CityLink Tunnel to Melbourne Airport (metro various) | CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport | Existing | 496924000 | 0.82157 | 224124000 | 73605000 | 190415000 | qtr 2 2017‑18 | 2016–17 | 2017-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Metropolitan | Metropolitan |  |  | GG | Transport | TEI includes $200.000 million of Commonwealth funding and covers the total funding of the state delivered components of the project.
CityLink-Tulla widening project – Tullamarine Freeway widening (Tullamarine) | CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport | New | 272800000 | 0 | 0 | 27400000 | 199800000 | qtr 2 2018‑19 | 2015–16 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Tullamarine | Metropolitan |  |  | GG | Transport | State Government contribution (including anticipated Commonwealth Government funding of $200 million) to widen the Tullamarine Freeway between Bulla Road and Melbourne Airport. This project is part of the broader $1.3 billion CityLink-Tulla widening project funded by Transurban in conjunction with the State and Commonwealth Governments.
New youth justice facility (metropolitan) | New youth justice facility | Existing | 419651000 | 0.50732 | 141242000 | 184134000 | 16438000 | qtr 1 2022‑23 | 2021–22 | 2022-09-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Metropolitan | Metropolitan |  |  | GG | Justice and emergency services | TEI has increased by $141.242 million compared with the 2019‑20 Budget due to funding provided in the 2020‑21 Budget for additional project scope. The TEI excludes $10.291 million of certain expenditure reclassified as operating instead of capital in line with accounting standards. The estimated completion date has been revised to quarter 1 2022‑23 to reflect a revised project schedule.
New youth justice facility (Werribee) | New youth justice facility | New | 288700000 | 0 | 0 | 1000000 | 260700000 | qtr 4 2020-21 | 2017–18 | 2021-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Werribee | Metropolitan |  |  | GG | Justice and emergency services
New youth justice facility (Cherry Creek) | New youth justice facility | Existing | 278409000 | 0 | 0 | 41228000 | 90000000 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Cherry Creek | Regional |  |  | GG | Justice and emergency services
New youth justice facility (Cherry Creek) | New youth justice facility | Existing | 278409000 | -0.035646 | -10291000 | 17123000 | 192181000 | qtr 4 2020-21 | 2018–19 | 2021-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Cherry Creek | Regional |  |  | GG | Justice and emergency services | TEI has reduced due to $10.291 million having been transferred to output funding for this initiative.
Ballarat Base Hospital expansion and redevelopment (Ballarat) | Ballarat Health Services expansion and redevelopment | New | 461600000 | 0 | 0 | 0 | 460800000 | qtr 4 2025-26 | 2018–19 | 2026-06-30 | Department of Health and Human Services | Department of Health | Ballarat | Regional |  |  | GG | Health and human services
Ballarat Health Services expansion and redevelopment (Ballarat) | Ballarat Health Services expansion and redevelopment | Existing | 461600000 | 0 | 0 | 800000 | 455000000 | qtr 4 2025‑26 | 2019–20 | 2026-06-30 | Department of Health and Human Services | Department of Health | Ballarat | Regional |  |  | GG | Health and human services
Ballarat Health Services expansion and redevelopment and the new Central Energy Plant (Ballarat) | Ballarat Health Services expansion and redevelopment and the new Central Energy Plant | Existing | 541600000 | 0 | 0 | 3500000 | 528100000 | qtr 2 2027‑28 | 2021–22 | 2027-12-31 | Department of Health | Department of Health | Ballarat | Regional |  |  | GG | Health and human services | TEI includes $80.000 million reallocated from Guaranteeing Future Energy Supply (Melbourne). The estimated completion date has been revised to quarter 2 2027‑28 due to COVID‑19 restrictions on work sites impacting overall program. The project’s cashflow has been revised in line with a revised project schedule.
Barwon Heads Road upgrade (Barwon Heads) | Barwon Heads Road upgrade | New | 318300000 | 0 | 0 | 0 | 317900000 | tbc | 2019–20 | 2089-06-30 | Department of Transport | Department of Transport | Barwon Heads | Regional |  |  | GG | Transport
Barwon Heads Road upgrade (Barwon Heads) | Barwon Heads Road upgrade | Existing | 365000000 | 0.14672 | 46700000 | 24131000 | 255559000 | qtr 4 2023‑24 | 2021–22 | 2024-06-30 | Department of Transport | Department of Transport | Barwon Heads | Regional |  |  | GG | Transport | TEI has increased by $46.700 million due to market escalation and includes $292.000 million of Commonwealth funding.
Building a better hospital for Melbourne’s inner west (Footscray) | Building a better hospital for Melbourne’s inner west | New | 1495000000 | 0 | 0 | 0 | 0 | qtr 4 2024‑25 | 2019–20 | 2025-06-30 | Department of Health and Human Services | Department of Health | Footscray | Metropolitan |  |  | GG | Health and human services | Cash flows to be confirmed. TEI includes $65 million provided in previous budgets and excludes financing costs.
Building a better hospital for Melbourne’s inner west (Footscray) | Building a better hospital for Melbourne’s inner west | Existing | 1495000000 | 0 | 0 | 88468000 | 1392585000 | qtr 4 2024‑25 | 2021–22 | 2025-06-30 | Department of Health | Department of Health | Footscray | Metropolitan |  |  | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Building a world‑class Geelong Performing Arts Centre (Geelong) | Building a world‑class Geelong Performing Arts Centre | New | 128000000 | 0 | 0 | 0 | 112480000 | qtr 4 2022‑23 | 2019–20 | 2023-06-30 | Other public non-financial corporations | Development Victoria | Geelong | Regional |  |  | PNFC | Culture, sport and community
Building a world‑class Geelong Performing Arts Centre (Geelong) | Building a world‑class Geelong Performing Arts Centre | Existing | 140000000 | 0.09375 | 12000000 | 32820000 | 36339000 | qtr 2 2023‑24 | 2021–22 | 2023-12-31 | Other public non-financial corporations | Development Victoria | Geelong | Regional |  |  | PNFC | Culture, sport and community | Initiative funded in the 2020‑21 Budget. The estimated completion date has been revised to quarter 2 2023‑24 to reflect additional project scope.
Geelong City Deal (Geelong) | Geelong City Deal | New | 139216000 | 0 | 0 | 0 | 128423000 | qtr 2 2022-23 | 2018–19 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Jobs, Precincts and Regions | Geelong | Regional |  |  | GG | Culture, sport and community | This is the Victorian Government’s share of the Geelong City Deal. This initiative is listed as a whole of government initiative in Budget Paper No. 3.
Geelong City Deal (Geelong) | Geelong City Deal | Existing | 312316000 | 1.2434 | 173100000 | 4600000 | 269923000 | qtr 4 2021‑23 | 2019–20 | 2023-06-30 | Department of Jobs, Precincts and Regions | Department of Jobs, Precincts and Regions | Geelong | Regional |  |  | GG | Culture, sport and community | This is the Victorian and Commonwealth Government’s share of the Geelong City Deal. Delays in expenditure partially due to negotiations with Commonwealth.
Geelong City Deal (Geelong) | Geelong City Deal | Existing | 292316000 | -0.064038 | -20000000 | 16233000 | 211486000 | qtr 4 2025‑26 | 2021–22 | 2026-06-30 | Department of Jobs, Precincts and Regions | Department of Jobs, Precincts and Regions | Geelong | Regional |  |  | GG | Culture, sport and community | TEI has decreased by $20.000 million compared with the 2019‑20 Budget, due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. The estimated completion date has been revised to quarter 4 2025‑26 due to the updated work schedule and delay in negotiations with the Commonwealth.
Geelong Hospital – major upgrade (Geelong) | Geelong Hospital – major upgrade | New | 118170000 | 0 | 0 | 69465000 | 5493000 | qtr 2 2015‑16 | 2015–16 | 2015-12-31 | Department of Health and Human Services | Department of Health | Geelong | Regional |  |  | GG | Health and human services | The TEI of this initiative has changed to reflect additional improvements at Geelong Hospital including relocation of the current helipad to the rooftop of the acute services tower block.
Geelong Hospital – major upgrade (Geelong) | Geelong Hospital – major upgrade | Completed | 118170000 | 0 | 0 | 114362000 | 0 | qtr 4 2018‑19 | 2019–20 | 2019-06-30 | Department of Health and Human Services | Department of Health | Geelong | Regional |  |  | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Geelong Hospital – major upgrade (Geelong) | Geelong Hospital – major upgrade | Existing | 118170000 | 0 | 0 | 112620000 | 0 | qtr 2 2018-19 | 2018–19 | 2018-12-31 | Department of Health and Human Services | Department of Health | Geelong | Regional |  |  | GG | Health and human services | The estimated completion date has been revised to reflect project delivery and cashflows approved by Government.
Geelong Hospital – major upgrade (Geelong) | Geelong Hospital – major upgrade | Existing | 118170000 | 0 | 0 | 97019000 | 11297000 | qtr 1 2018‑19 | 2016–17 | 2018-09-30 | Department of Health and Human Services | Department of Health | Geelong | Regional |  |  | GG | Health and human services | The project completion date has been revised to reflect the additional separate scope funded in 2014‑15.
Geelong Hospital – major upgrade (Geelong) | Geelong Hospital – major upgrade | Existing | 118170000 | 0 | 0 | 98183000 | 11487000 | qtr 1 2018-19 | 2017–18 | 2018-09-30 | Department of Health and Human Services | Department of Health | Geelong | Regional |  |  | GG | Health and human services
Kardinia Park Stadium Stage 5 redevelopment (Geelong) | Kardinia Park Stadium Stage 5 redevelopment | Existing | 141238000 | 0 | 0 | 10190000 | 96209000 | qtr 4 2022‑23 | 2021–22 | 2023-06-30 | Other public non-financial corporations | Kardinia Park Stadium Trust | Geelong | Regional |  |  | PNFC | Culture, sport and community | Initiative funded in the 2020‑21 Budget. TEI has reduced by $0.323 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Building emergency departments kids and families can count on (statewide) | Building emergency departments kids and families can count on | New | 102400000 | 0 | 0 |  | 85676000 | qtr 1 2024‑25 | 2021–22 | 2024-09-30 | Department of Health | Department of Health | Statewide | Statewide |  |  | GG | Health and human services | TEI includes $40.000 million of Commonwealth funding and $5.940 million announced in the 2019‑20 Budget. TEI has decreased by $3.220 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Building new homes to fight homelessness (statewide) | Building new homes to fight homelessness | New | 209099000 | 0 | 0 | 0 | 175639000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Director of Housing | Director of Housing | Statewide | Statewide |  |  | PNFC | Health and human services
Building new homes to fight homelessness (statewide) | Building new homes to fight homelessness | Existing | 209100000 | 4.7824e-06 | 1000 | 94037000 |  | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Director of Housing | Director of Housing | Statewide | Statewide |  |  | PNFC | Health and human services
Car Parks for Commuters (statewide) | Car Parks for Commuters | New | 150000000 | 0 | 0 | 0 | 137500000 | qtr 4 2022‑23 | 2019–20 | 2023-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Statewide | Statewide |  |  | PNFC | Transport
Car Parks for Commuters Program (statewide) | Car Parks for Commuters | Existing | 485617000 | 2.2374 | 335617000 | 89920000 | 233293000 | qtr 2 2024‑25 | 2021–22 | 2024-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Statewide | Statewide |  |  | PNFC | Transport | The Car Parks for Commuter and Train station car parking programs have been consolidated into one initiative as this will be managed as a single car parking program to streamline reporting and maximise program efficiencies. TEI has increased by $263.817 million due to additional funding announced in the 2020‑21 Budget, funding provided by the Infrastructure Planning and Acceleration Fund, the Growth Areas Infrastructure Contribution funding and contributions from the Commonwealth Government. The estimated completion date has been revised to quarter 2 2024‑25 to reflect a revised project scope.
Community Safety Statement (statewide) | Community Safety Statement | New | 390564000 | 0 | 0 | 0 | 283880000 | various | 2017–18 | 2089-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | The TEI includes $6.300 million of funding redirected from the Public Safety – Police Response initiative for the purchase of land for the Specialist Training Facility.
Community Safety Statement (statewide) | Community Safety Statement | Existing | 315056000 | -0.038185 | -12508000 | 251760000 |  | various | 2021–22 | 2089-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | TEI has reduced by $12.508 million due to funds being redirected to the Road Safety Capability initiative and a revised project scope.
Community Safety Statement (statewide) | Community Safety Statement | Existing | 327564000 | -0.097282 | -35300000 | 126506000 | 70762000 | various | 2019–20 | 2089-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | TEI has been revised due to changes in project scope, with additional resources allocated to police operations.
Community Safety Statement (statewide) | Community Safety Statement | Existing | 362864000 | -0.070923 | -27700000 | 39476000 | 236358000 | various | 2018–19 | 2089-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | TEI has reduced due to $27.700 million having been redirected to output funding to correctly reflect the expenditure for the BlueConnect project. A number of components were initially planned to be purchased (capital expenditure) but have been changed to a lease arrangement (output expenditure). Cash flow has been revised in line with project schedule. Cash flow has been revised in line with project schedule.
Corrections system expansion (statewide) | Corrections system expansion | New | 140760000 | 0 | 0 | 19460000 | 73950000 | qtr 4 2016‑17 | 2014–15 | 2017-06-30 | Department of Justice | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | Includes previously approved funding of $19.460 million.
Corrections system expansion (statewide) | Corrections system expansion | Existing | 108360000 | -0.23018 | -32400000 | 21410000 | 25900000 | qtr 4 2016‑17 | 2015–16 | 2017-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | The TEI includes previously approved funding of $19.460 million and reflects a reprioritisation of $22.400 million to Critical infrastructure and services.
Enabling a high quality, efficient public pathology system (statewide) | Enabling a high quality, efficient public pathology system | New | 116500000 | 0 | 0 | 10500000 | 87500000 | qtr 4 2024‑25 | 2021–22 | 2025-06-30 | Department of Health | Department of Health | Statewide | Statewide |  |  | GG | Health and human services
Expanding mental health treatment facilities for Victoria’s youth (statewide) | Expanding mental health treatment facilities for Victoria’s youth | New | 141000000 | 0 | 0 |  | 139000000 | qtr 4 2024‑25 | 2021–22 | 2025-06-30 | Department of Health | Department of Health | Statewide | Statewide |  |  | GG | Health and human services
Men’s prison system capacity (statewide) | Men’s prison system capacity | New | 1255372000 | 0 | 0 | 37000000 | 728918000 | qtr 4 2022‑23 | 2019–20 | 2023-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services
Men’s prison system capacity (statewide) | Men’s prison system capacity | Existing | 804668000 | -0.35902 | -450704000 | 78005000 | 302938000 | qtr 4 2022‑23 | 2021–22 | 2023-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | TEI has reduced by $450.704 million compared with the 2019‑20 Budget due to $429.080 million being provided to the Chisholm Road prison project (non – metro various) and $21.624 million for revised scope of works. The project’s cashflow has been revised in line with a revised project schedule.
Metropolitan and regional restoration and maintenance (statewide) | Metropolitan and regional restoration and maintenance | New | 195200000 | 0 | 0 | 0 | 87200000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport | TEI consolidates both the metropolitan and regional components. Budget Paper No. 3 reports these components separately.
Metropolitan and regional restoration and maintenance (statewide) | Metropolitan and regional restoration and maintenance | Existing | 195200000 | 0 | 0 | 100440000 | 1896000 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Department of Transport | Department of Transport | Statewide | Statewide |  |  | GG | Transport
Metropolitan and regional restoration and maintenance (statewide) | Metropolitan and regional restoration and maintenance | Existing | 194643000 | -0.0028535 | -557000 | 168946000 | 8197000 | qtr 4 2022‑23 | 2021–22 | 2023-06-30 | Department of Transport | Department of Transport | Statewide | Statewide |  |  | GG | Transport | TEI has decreased by $0.557 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. The estimated completion date has been extended to quarter 4 2022‑23 due to issues relating to ground access, detailed design complications and delays in procurement for a small number of projects.
Network Transition Plan – Phase A (Statewide) | Network Transition Plan – Phase A | New | 255838000 | 0 | 0 | 118773000 | 22029000 | qtr 2 2019-20 | 2018–19 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Statewide | Statewide |  |  | PNFC | Transport | TEI includes an additional $33.518 million for power and platform and substation works, funded from savings on other projects.
Network Transition Plan – Phase A (Statewide) | Network Transition Plan – Phase A | Existing | 255838000 | 0 | 0 | 236091000 | 0 | qtr 2 2019‑20 | 2019–20 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Statewide | Statewide |  |  | PNFC | Transport
New metropolitan trains (statewide) | New metropolitan trains | New | 985849000 | 0 | 0 |  |  | qtr 2 2026‑27 | 2021–22 | 2026-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Statewide | Statewide |  |  | PNFC | Transport | Cashflows not reported at this time due to the commercial sensitivity of the procurement process.
Public Safety – Police Response (statewide) | Public Safety – Police Response | New | 149066000 | 0 | 0 | 0 | 90837000 | qtr 4 2020‑21 | 2016–17 | 2021-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services
Public Safety – Police Response (statewide) | Public Safety – Police Response | Existing | 121956000 | 0 | 0 | 117807000 | 0 | various | 2019–20 | 2089-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services
Public Safety – Police Response (statewide) | Public Safety – Police Response | Existing | 137766000 | -0.075805 | -11300000 | 30805000 | 39894000 | various | 2017–18 | 2089-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | TEI has reduced by $11.300 million due to: the transfer of $5.000 million from capital to output funding to correctly reflect the nature of expenditure for the Intelligence Capability component; and the redirection of $6.300 million funding for land purchase for the Specialist Training Facility to the Community Safety Statement package. The estimated completion dates for the major components are: Intelligence Capability (quarter 4, 2018-19), Mobile Technology (quarter 4, 2018-19), Specialist Equipment (quarter 2, 2017-18) and Body Worn Cameras (quarter 3, 2019-20).
Public Safety – Police Response (statewide) | Public Safety – Police Response | Existing | 121956000 | -0.11476 | -15810000 | 78713000 | 4149000 | various | 2018–19 | 2089-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | TEI has reduced due to $17.710 million having been redirected to output funding for the Intelligence Capability project and $1.900 million having been redirected from output funding for the Mobile Technology Rollout project to correctly reflect the nature of the expenditure. Cash flow has been revised in line with project schedule. The estimated completion dates for the major components are: Intelligence Capability (quarter 4, 2018-19), Mobile Technology (quarter 4, 2018-19), Specialist Equipment (quarter 1, 2018-19) and Body Worn Cameras (quarter 4, 2018-19).
Public housing renewal program (statewide) | Public housing renewal program | New | 185000000 | 0 | 0 | 5000000 | 120000000 | ongoing | 2017–18 | 2099-06-30 | Director of Housing | Director of Housing | Statewide | Statewide |  |  | PNFC | Health and human services | The final budget and cashflow will be available following execution of a project development agreement with the private sector. This is anticipated to be executed by March 2018.
Public housing renewal program (statewide) | Public housing renewal program | Existing | 185000000 | 0 | 0 | 6800000 | 162474000 | various | 2018–19 | 2089-06-30 | Director of Housing | Director of Housing | Statewide | Statewide |  |  | PNFC | Health and human services
Public housing renewal program (statewide) | Public housing renewal program | Existing | 185000000 | 0 | 0 | 23065000 | 151679000 | qtr 4 2028‑29 | 2019–20 | 2029-06-30 | Director of Housing | Director of Housing | Statewide | Statewide |  |  | PNFC | Health and human services
Public housing renewal program (statewide) | Public housing renewal program | Existing | 185000000 | 0 | 0 | 42367000 | 95164000 | qtr 4 2023‑24 | 2021–22 | 2024-06-30 | Director of Housing | Director of Housing | Statewide | Statewide |  |  | PNFC | Health and human services | Estimated completion date has been extended to quarter 4 2023‑24 to reflect project scope revision.
Regional rail sustainability (statewide) | Regional rail sustainability Statewide | New | 464600000 | 0 | 0 |  | 331600000 | qtr 4 2024‑25 | 2021–22 | 2025-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Statewide | Statewide |  |  | PNFC | Transport
Road Safety (statewide) | Road Safety Towards Zero | New | 266000000 | 0 | 0 | 0 | 217000000 | qtr 4 2020‑21 | 2016–17 | 2021-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport | Initiative is to be funded and delivered by the Transport Accident Commission.
Road Safety Towards Zero (statewide) | Road Safety Towards Zero | Existing | 266000000 | 0 | 0 | 15000000 | 179500000 | qtr 4 2020-21 | 2017–18 | 2021-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport | Project name changed from Road Safety (statewide) published in the 2016-17 Budget.
Road Safety Towards Zero (statewide) | Road Safety Towards Zero | Existing | 266000000 | 0 | 0 | 103773000 | 119535000 | qtr 4 2020-21 | 2018–19 | 2021-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport | Initiative is funded by the Transport Accident Commission.
Road Safety Towards Zero (statewide) | Road Safety Towards Zero | Existing | 290999000 | 0.093981 | 24999000 | 250955000 | 8353000 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Department of Transport | Department of Transport | Statewide | Statewide |  |  | GG | Transport | TEI has increased by $25.000 million due to funding transferred from the Road Safety Strategy 2013‑22 (statewide) program. Initiative is funded by the Transport Accident Commission.
Road Safety Strategy (statewide) | Road Safety | New | 329986000 | 0 | 0 | 226400000 | 46994000 | qtr 4 2024‑25 | 2021–22 | 2025-06-30 | Department of Transport | Department of Transport | Statewide | Statewide |  |  | GG | Transport | TEI includes $183.300 million of Commonwealth funding and funding from the Transport Accident Commission.
Rolling stock maintenance and disposal programs (statewide) | Rolling stock maintenance and disposal programs | New | 125118000 | 0 | 0 |  | 80631000 | qtr 1 2025‑26 | 2021–22 | 2025-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Statewide | Statewide |  |  | PNFC | Transport
Ten new community hospitals to give patients the best care (statewide) | Ten new community hospitals to give patients the best care | New | 675000000 | 0 | 0 | 112892000 | 526247000 | qtr 4 2024‑25 | 2021–22 | 2025-06-30 | Department of Health | Department of Health | Statewide | Statewide |  |  | GG | Health and human services | TEI includes $2.000 million provided in the 2019‑20 Budget, $66.147 million provided in the 2020‑21 Budget and $51.353 million from the Infrastructure Planning and Acceleration Fund.
Women’s prison system capacity (statewide) | Women’s prison system capacity | New | 188900000 | 0 | 0 | 0 | 173900000 | qtr 4 2021‑22 | 2019–20 | 2022-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services
Women’s prison system capacity (statewide) | Women’s prison system capacity | Existing | 188900000 | 0 | 0 | 21129000 | 86362000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Justice and Community Safety | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | The estimated completion date has been revised to quarter 2 2022‑23 to reflect a revised schedule of works.
A pathway to more acute mental health beds: Responding to the Royal Commission into Victoria’s Mental Health System interim report (statewide) | A pathway to more acute mental health beds | Existing | 492200000 | 0 | 0 | 17250000 | 218795000 | qtr 3 2023‑24 | 2021–22 | 2024-03-31 | Department of Health | Department of Health | Statewide | Statewide |  |  | GG | Health and human services | Initiative funded in the 2020‑21 Budget.
Big Housing Build (statewide) | Big Housing Build | Existing | 2999000000 | 0 | 0 | 375000000 | 981000000 | qtr 4 2026‑27 | 2021–22 | 2027-06-30 | Director of Housing | Director of Housing | Statewide | Statewide |  |  | PNFC | Health and human services | New initiative in the 2020‑21 Budget. This initiative includes the transfer of the Markham Avenue estate redevelopment (Ashburton) project. The TEI includes $2.708 billion currently held in contingency.
Big Housing Build physical improvements (statewide) | Big Housing Build physical improvements | Existing | 184000000 | 0 | 0 | 37300000 | 110000000 | qtr 4 2026‑27 | 2021–22 | 2027-06-30 | Director of Housing | Director of Housing | Statewide | Statewide |  |  | PNFC | Health and human services | TEI reflects four years of funding consistent with the 2020‑21 Budget. The Director of Housing has been provided with ongoing capital funding for this initiative.
Building confidence in corrections – Construction/asset enhancement (statewide) | Building confidence in corrections – Construction/asset enhancement | Existing | 108736000 | 0 | 0 | 89704000 | 2000000 | qtr 2 2014‑15 | 2014–15 | 2014-12-31 | Department of Justice | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services
Building confidence in corrections – Construction/asset enhancement (statewide) | Building confidence in corrections – Construction/asset enhancement | Existing | 108736000 | 0 | 0 | 106736000 | 0 | qtr 1 2015‑16 | 2015–16 | 2015-09-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services
Building works stimulus (statewide) | Building works stimulus | Existing | 155000000 | 0 | 0 | 70400000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Director of Housing | Director of Housing | Statewide | Statewide |  |  | PNFC | Health and human services | Initiative funded in the Building Works package announced in May 2020.
Emergency services high‑priority infrastructure (statewide) | Emergency services high‑priority infrastructure | Existing | 120846000 | 0 | 0 | 92515000 |  | qtr 4 2022‑23 | 2021–22 | 2023-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | TEI includes $22.600 million approved in the 2017‑18 Budget, $3.011 million approved in the 2017‑18 Budget Update, $7.800 million approved in the 2018‑19 Budget, $21.100 million approved in the 2019‑20 Budget for the Victorian State Emergency Services facilities, and includes $66.335 million approved for additional works since the 2020‑21 Budget. The estimated completion date has been revised to quarter 4 2022‑23 to reflect the inclusion of additional projects, with construction of some projects to be completed in the first half of 2023.
Improving hospital services – sub‑acute (statewide) | Improving hospital services – sub‑acute | Existing | 186900000 | 0 | 0 | 174400000 | 0 | qtr 4 2014‑15 | 2014–15 | 2015-06-30 | Department of Health | Department of Health | Statewide | Statewide |  |  | GG | Health and human services | This initiative is being delivered as an integrated project with additional funding provided from the Commonwealth’s Health and Hospital Fund – Round 3.
Increase Prison Capacity (statewide) | Increase Prison Capacity | Existing | 241814000 | 0 | 0 | 142626000 | 29308000 | qtr 2 2017‑18 | 2014–15 | 2017-12-31 | Department of Justice | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | This initiative includes additional prison beds and new male prison. The TEI reflects reprioritisation of funding to Prison capacity expansion and the application of public private partnership policy.
Increase Prison Capacity (statewide) | Increase Prison Capacity | Existing | 256132000 | 0 | 0 | 236585000 | 5000000 | qtr 2 2017-18 | 2017–18 | 2017-12-31 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services
Increase Prison Capacity (statewide) | Increase Prison Capacity | Completed | 253632000 | -0.0097606 | -2500000 | 236337000 | 0 | qtr 2 2018-19 | 2018–19 | 2018-12-31 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | TEI has reduced due to $2.500 million having been transferred to output funding for this initiative.
Increase Prison Capacity (statewide) | Increase Prison Capacity | Existing | 246414000 | 0.019023 | 4600000 | 161807000 | 22607000 | qtr 2 2017‑18 | 2015–16 | 2017-12-31 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | This initiative includes additional prison beds and the new male prison. The TEI reflects previously reprioritised funding, the application of public private partnership policy and a reprioritisation of $5.400 million to Critical infrastructure and services in the current budget.
Increase Prison Capacity (statewide) | Increase Prison Capacity | Existing | 256132000 | 0.039438 | 9718000 | 233525000 | 13307000 | qtr 2 2017‑18 | 2016–17 | 2017-12-31 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services | This initiative includes $9.152 million reprioritised funding from the Building confidence in corrections asset initiative, with $0.217 million redirected to Critical infrastructure and services.
Meeting Ambulance Response Times (statewide) | Meeting Ambulance Response Times | Existing | 169356000 | 0 | 0 | 104204000 | 39887000 | qtr 4 2022‑23 | 2021–22 | 2023-06-30 | Department of Health | Department of Health | Statewide | Statewide |  |  | GG | Health and human services | TEI includes additional funding of $59.700 million provided in the 2020‑21 Budget. This project merges with the Ambulance Stations Build and Upgrade Program (Melbourne).
Pavement Maintenance and Renewal Program (statewide) | Pavement Maintenance and Renewal Program | Existing | 100249000 | 0 | 0 | 89377000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Transport | Department of Transport | Statewide | Statewide |  |  | GG | Transport | This initiative combines Metropolitan road maintenance (metropolitan various) and Regional road maintenance (regional various). TEI has decreased by $4.050 million due to savings. The estimated completion date has been extended to quarter 4 2021‑22 due to issues including ground access and complexities in detailed design.
Regional Rail Link (various) | Regional Rail Link | Existing | 4101813000 | 0 | 0 | 3264813000 | 259984000 | qtr 4 2014‑15 | 2014–15 | 2015-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Statewide | Statewide |  |  | PNFC | Transport | TEI revised by $705.331 million based on current project delivery progress. Scope of project expanded to include removal of level crossing at Main Road, St Albans. Estimated completion date reflects the original scope of the project excluding Main Road, St Albans level crossing removal. The estimated completion date for Main Road, St Albans is quarter 4, 2016‑17.
Road maintenance blitz (statewide) | Road maintenance blitz | Existing | 108699000 | 0 | 0 | 7000000 | 3500000 | qtr 4 2022‑23 | 2021–22 | 2023-06-30 | Department of Transport | Department of Transport | Statewide | Statewide |  |  | GG | Transport | Initiative funded in the 2020‑21 Budget.
Road restoration and road surface replacement (statewide) | Road restoration and road surface replacement | Completed | 122812000 | 0 | 0 | 120015000 | 0 | qtr 4 2018-19 | 2018–19 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport
State Coronial Services redevelopment (statewide) | State Coronial Services redevelopment | Existing | 102676000 | 0 | 0 | 90013000 | 0 | qtr 2 2014‑15 | 2014–15 | 2014-12-31 | Department of Justice | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services
State Coronial Services redevelopment (statewide) | State Coronial Services redevelopment | Existing | 114359000 | 0.11379 | 11683000 | 111225000 | 0 | qtr 2 2015‑16 | 2015–16 | 2015-12-31 | Department of Justice and Regulation | Department of Justice and Community Safety | Statewide | Statewide |  |  | GG | Justice and emergency services
Targeted Road restoration (statewide) | Targeted Road restoration | Existing | 90000000 | 0 | 0 | 30000000 | 30000000 | qtr 4 2015‑16 | 2014–15 | 2016-06-30 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Statewide | Statewide |  |  | GG | Transport
Targeted Road restoration (statewide) | Targeted Road restoration | Existing | 140000000 | 0.55556 | 50000000 | 86820000 | 445000 | qtr 4 2015‑16 | 2015–16 | 2016-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport | Includes previously reported Arterial road restoration (statewide).
Rail Infrastructure Upgrades from Maryborough and Ararat to Ballarat (statewide) | Rail Infrastructure Upgrades from Maryborough and Ararat to Ballarat | New | 130000000 | 0 | 0 | 0 | 0 | qtr 2 2019-20 | 2018–19 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Statewide | Statewide |  | MBRP | PNFC | Transport | TEI includes $35.000 million of Commonwealth funding, and $10.000 million redirected from savings from other projects. This project forms part of the Regional Rail Revival program.
New schools construction (statewide) | New school construction | New | 491565000 | 0 | 0 |  | 310489000 | qtr 3 2023‑24 | 2021–22 | 2024-03-31 | Department of Education and Training | Department of Education and Training | Statewide | Statewide | School education |  | GG | Education and Training
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | New | 79750000 | 0 | 0 | 0 | 74412000 | qtr 4 2017‑18 | 2015–16 | 2018-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide | Better Roads – statewide |  | GG | Transport | Total package of $90.000 million includes $10.250 million in output funding.
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | Completed | 102543000 | 0 | 0 | 98093000 |  | qtr 4 2020‑21 | 2021–22 | 2021-06-30 | Department of Transport | Department of Transport | Statewide | Statewide |  |  | GG | Transport
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | Existing | 79750000 | 0 | 0 | 13259000 | 36154000 | qtr 2 2018‑19 | 2016–17 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | Existing | 102543000 | 0.24361 | 20087000 | 97386000 | 253000 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Department of Transport | Department of Transport | Statewide | Statewide |  |  | GG | Transport | TEI has increased by $20.083 million due to the complexity of delivering the project scope. The estimated completion date has been revised to quarter 4 2019‑20 due to extended community consultation and interface with other projects.
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | Existing | 80597000 | 0.010621 | 847000 | 38119000 | 11392000 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport | The estimated completion date has been extended. TEI excludes corporate costs. TEI includes additional funding of $1.210 million for new project approved within this program.
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | Existing | 82456000 | 0.023065 | 1859000 | 76159000 | 0 | qtr 4 2018-19 | 2018–19 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport | TEI includes additional funding of $1.859 million to deliver projects within the scope of the program.
Ready for school: Kinder for every three‑year‑old 2019‑20 (statewide) | Ready for school: Kinder for every three‑year‑old 2019‑20 | Existing | 282965000 | 0 | 0 | 35962000 | 190704000 | qtr 4 2022‑23 | 2021–22 | 2023-06-30 | Department of Education and Training | Department of Education and Training | Statewide | Statewide | Early childhood development |  | GG | Education and Training
Relocatable Buildings Program 2020‑21 (statewide) | Relocatable Buildings Program 2020‑21 | Completed | 113324000 | 0 | 0 | 113324000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Education and Training | Department of Education and Training | Statewide | Statewide | School education |  | GG | Education and Training | Initiative funded in the Building Works package announced in May 2020. TEI includes reclassification of certain expenditure as operating instead of capital in line with accounting standards.
Relocatable Buildings Program – providing relocatable buildings to meet growing demand (statewide) | Relocatable Buildings Program – providing relocatable buildings to meet growing demand | New | 101273000 | 0 | 0 | 0 | 0 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Department of Education and Training | Department of Education and Training | Statewide | Statewide | School education |  | GG | Education and Training
Relocatable Buildings Program – providing relocatable buildings to meet growing demand (statewide) | Relocatable Buildings Program – providing relocatable buildings to meet growing demand | New | 105330000 | 0.04006 | 4057000 |  |  | qtr 1 2022‑23 | 2021–22 | 2022-09-30 | Department of Education and Training | Department of Education and Training | Statewide | Statewide | School education |  | GG | Education and Training
Road Safety Strategy 2013‑22 (statewide) | Road Safety Strategy 2013-22 | Existing | 541169000 | 0 | 0 | 52941000 | 410228000 | qtr 2 2022‑23 | 2014–15 | 2022-12-31 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Statewide | Statewide | Transport Accident Commission |  | GG | Transport | TEI has increased by $41.169 million as a result of a reassessment of the mix of projects between capital and operating based on recent trends. However, the overall program spend remains the same.
Road Safety Strategy 2013-22 (statewide) | Road Safety Strategy 2013-22 | Existing | 711333000 | 0 | 0 | 397300000 | 131913000 | qtr 2 2022-23 | 2018–19 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport | Initiative is funded by the Transport Accident Commission.
Road Safety Strategy 2013‑22 (statewide) | Road Safety Strategy 2013-22 | Existing | 710643000 | 0 | 0 | 203798000 | 414828000 | qtr 2 2022‑23 | 2016–17 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport
Road Safety Strategy 2013-22 (statewide) | Road Safety Strategy 2013-22 | Existing | 711333000 | 0.00097095 | 690000 | 282873000 | 310517000 | qtr 2 2022-23 | 2017–18 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide |  |  | GG | Transport | Initiative is to be funded by the Transport Accident Commission. TEI has increased by $0.690 million. This is due to a reassessment of the estimated mix of projects between capital and output. The total program spend remains the same.
Road Safety Strategy 2013‑2022 (statewide) | Road Safety Strategy 2013-22 | Existing | 629553000 | -0.052009 | -34539000 | 594175000 | 20378000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Transport | Department of Transport | Statewide | Statewide |  |  | GG | Transport | TEI has decreased by $25.710 million reallocated to Targeted Road Safety works, $7.900 million reallocated to Road Safety Strategy (statewide), and $0.929 million reallocated to minor projects. Initiative is funded by the Transport Accident Commission.
Road Safety Strategy 2013‑2022 (statewide) | Road Safety Strategy 2013-22 | Existing | 664092000 | -0.066412 | -47241000 | 564933000 | 54875000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Department of Transport | Department of Transport | Statewide | Statewide |  |  | GG | Transport | TEI has reduced by $47.241 million, with $25.000 million transferred to the Road Safety Toward Zero program and $22.241 million to Active Transport program. Initiative is funded by the Transport Accident Commission.
Road Safety Strategy 2013‑22 (statewide) | Road Safety Strategy 2013-22 | Existing | 710643000 | 0.31316 | 169474000 | 138379000 | 497299000 | qtr 2 2022‑23 | 2015–16 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Statewide | Statewide | Transport Accident Commission |  | GG | Transport | TEI has increased by $169.474 million. This is due to a reassessment of the estimated mix of projects between capital and output. The total program spend remains the same.
Trade training centres – government schools (statewide) | Trade training centres – government schools | Existing | 248160000 | 0 | 0 | 209729000 | 19000000 | qtr 2 2016‑17 | 2014–15 | 2016-12-31 | Department of Education and Early Childhood Development | Department of Education and Training | Statewide | Statewide | Commonwealth funding |  | GG | Education and Training | TEI increase is due to increased Commonwealth funding.
Trade training centres – government schools (statewide) | Trade training centres – government schools | Completed | 252838000 | 0 | 0 | 252838000 | 0 | qtr 3 2019-20 | 2018–19 | 2020-03-31 | Department of Education and Training | Department of Education and Training | Statewide | Statewide |  |  | GG | Education and Training
Trade training centres – government schools (statewide) (various) | Trade training centres – government schools | Existing | 248160000 | 0 | 0 | 238160000 | 0 | qtr 4 2016‑17 | 2016–17 | 2017-06-30 | Department of Education and Training | Department of Education and Training | Statewide | Statewide | Commonwealth funding |  | GG | Education and Training
Trade training centres – government schools (statewide) | Trade training centres – government schools | Existing | 248160000 | 0 | 0 | 226500000 | 3660000 | qtr 2 2016‑17 | 2015–16 | 2016-12-31 | Department of Education and Training | Department of Education and Training | Statewide | Statewide | Commonwealth funding |  | GG | Education and Training
Trade training centres – government schools (statewide) | Trade training centres – government schools | Existing | 252838000 | 0.018851 | 4678000 | 243160000 | 0 | qtr 4 2017-18 | 2017–18 | 2018-06-30 | Department of Education and Training | Department of Education and Training | Statewide | Statewide | Commonwealth funding |  | GG | Education and Training | TEI includes co-contribution from TAFE.
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | New | 106300000 | 0 | 0 | 0 | 105900000 | qtr 4 2019‑20 | 2015–16 | 2020-06-30 | Department of Health and Human Services | Department of Health | Berwick | Metropolitan |  |  | GG | Health and human services | The TEI includes funding held in contingency pending completion of business planning and development.
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | Completed | 139780000 | 0 | 0 | 120678000 |  | qtr 4 2020‑21 | 2021–22 | 2021-06-30 | Department of Health | Department of Health | Berwick | Metropolitan |  |  | GG | Health and human services | Expenditure excludes financing costs. The project’s cashflow has been revised in line with a revised project schedule.
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | Existing | 139780000 | 0 | 0 | 120277000 | 0 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Department of Health and Human Services | Department of Health | Berwick | Metropolitan |  |  | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | Existing | 106300000 | 0 | 0 | 400000 | 103900000 | qtr 4 2019‑20 | 2016–17 | 2020-06-30 | Department of Health and Human Services | Department of Health | Berwick | Metropolitan |  |  | GG | Health and human services
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | Existing | 139780000 | -0.00092917 | -130000 | 58743000 | 3612000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Department of Health and Human Services | Department of Health | Berwick | Metropolitan |  |  | GG | Health and human services
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | Existing | 139910000 | 0.31618 | 33610000 | 5507000 | 81534000 | qtr 4 2019-20 | 2017–18 | 2020-06-30 | Department of Health and Human Services | Department of Health | Berwick | Metropolitan |  |  | GG | Health and human services | The TEI for this project has increased by $28.610 million to provide an additional 64 multi-day beds and includes a funding contribution of $5.000 million from Monash University for accommodation space.
Caulfield rationalisation works (metropolitan various) | Caulfield rationalisation works | New | 240076000 | 0 | 0 | 269000 | 193040000 | qtr 4 2025‑26 | 2021–22 | 2026-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport
Tram infrastructure upgrades (metropolitan various) | Tram infrastructure upgrades | New | 367555000 | 0 | 0 |  | 367048000 | qtr 4 2025‑26 | 2021–22 | 2026-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport
E‑Class Tram Infrastructure Program (metropolitan various) | E‑Class Tram Infrastructure Program | Existing | 735294000 | 0 | 0 | 451950000 | 96174000 | qtr 4 2025‑26 | 2021–22 | 2026-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport | The enabling infrastructure components of the E‑Class tram program published separately in the 2019‑20 Budget have been consolidated into one initiative to improve program management and transparency.
Metropolitan road and intersection upgrades (metropolitan various) | Metropolitan road and intersection upgrades | Existing | 117001000 | 0 | 0 |  | 83396000 | qtr 4 2023‑24 | 2021–22 | 2024-06-30 | Department of Transport | Department of Transport | Metropolitan various | Metropolitan |  |  | GG | Transport | Initiative funded in the 2020‑21 Budget.
Next Generation Trams (metropolitan various) | Next Generation Trams | Existing | 1483292000 | 0 | 0 | 78807000 | 1139312000 | qtr 4 2028‑29 | 2021–22 | 2029-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan |  |  | PNFC | Transport | Initiative funded in the 2020‑21 Budget.
School upgrades – growth for 2022 (metropolitan various) | School upgrades – growth for 2022 | Existing | 130106000 | 0 | 0 | 16910000 | 29174000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Education and Training | Department of Education and Training | Metropolitan various | Metropolitan | School education |  | GG | Education and Training | Initiative funded in the Building Works package announced in May 2020.
Suburban Rail Loop Initial and Early Works (metropolitan various) | Suburban Rail Loop Initial and Early Works | Existing | 2359705000 | 0 | 0 | 240304000 | 1566352000 | qtr 4 2024‑25 | 2021–22 | 2025-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Metropolitan various | Metropolitan | Regional Rail Revival |  | PNFC | Transport | TEI excludes $90.295 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. Estimated completion date is only for initial and early works program (pre‑construction activities).
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | City Loop fire and safety (upgrade stage 2) and intruder alarm | New | 132863000 | 0 | 0 | 0 | 128460000 | qtr 4 2019‑20 | 2016–17 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Metropolitan |  |  | PNFC | Transport
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | City Loop fire and safety (upgrade stage 2) and intruder alarm | Existing | 151743000 | 0 | 0 | 41176000 | 89343000 | tbc | 2019–20 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Metropolitan |  |  | PNFC | Transport | The main delivery contractor has been put into administration, and work is progressing to assess the impact to cost and schedule.
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | City Loop fire and safety (upgrade stage 2) and intruder alarm | Existing | 132863000 | 0 | 0 | 4403000 | 81984000 | qtr 4 2019-20 | 2017–18 | 2020-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Metropolitan |  |  | PNFC | Transport
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | City Loop fire and safety (upgrade stage 2) and intruder alarm | Existing | 151743000 | 0.1421 | 18880000 | 24719000 | 70488000 | qtr 2 2019-20 | 2018–19 | 2019-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised. TEI has decreased by $4.894 million due to reallocation of capital to operating funding. TEI has increased by $23.774 million to meet additional scope and design requirements.
Fishermans Bend Innovation Precinct at the former General Motors Holden Site – Stage 1 (Melbourne) | Fishermans Bend Innovation Precinct at the former General Motors Holden Site – Stage 1 | New | 179443000 | 0 | 0 |  | 156071000 | qtr 4 2023‑24 | 2021–22 | 2024-06-30 | Department of Jobs, Precincts and Regions | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | GG | Culture, sport and community
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | New | 100000000 | 0 | 0 | 1000000 | 76600000 | qtr 4 2018‑19 | 2015–16 | 2019-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Metropolitan |  |  | PNFC | Transport | The TEI includes funding announced in Getting On With It.
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | Completed | 100000000 | 0 | 0 | 100000000 |  | qtr 4 2020‑21 | 2021–22 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Metropolitan |  |  | GG | Transport
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | Existing | 100000000 | 0 | 0 | 98753000 | 0 | qtr 1 2019‑20 | 2019–20 | 2019-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised to quarter 1 2019‑20 to implement signage and pathing improvements.
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | Existing | 100000000 | 0 | 0 | 84709000 | 9891000 | qtr 2 2018-19 | 2018–19 | 2018-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised. The estimated completion date has been brought forward due to acceleration of works.
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | Existing | 100000000 | 0 | 0 | 12400000 | 43760000 | qtr 4 2018‑19 | 2016–17 | 2019-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Metropolitan |  |  | PNFC | Transport
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | Existing | 100000000 | 0 | 0 | 43733000 | 36267000 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Metropolitan |  |  | PNFC | Transport
Melbourne Arts Precinct transformation (Melbourne) | Melbourne Arts Precinct transformation | New | 101500000 | 0 | 0 | 26738000 | 2000000 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Department of Jobs, Precincts and Regions | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | GG | Culture, sport and community | This project incorporates the Reimagining Arts Centre Melbourne project and the National Gallery of Victoria Contemporary initiative. This project also incorporates the previously published Arts Centre Melbourne critical works project.
Melbourne Arts Precinct transformation (Melbourne) | Melbourne Arts Precinct transformation | Existing | 101423000 | -0.00075862 | -77000 | 101423000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Jobs, Precincts and Regions | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | GG | Culture, sport and community | This initiative relates to project planning and design activities for the precinct, including the Reimagining Arts Centre Melbourne project and the National Gallery of Victoria Contemporary initiative. TEI has reduced by $0.077 million due to minor project savings realised in 2018‑19. 2020‑21 funding will be provided to Development Victoria for delivery of this project. The estimated completion date has been revised due to the impact of COVID‑19.
Melbourne Park Redevelopment – Stage 3 (Melbourne) | Melbourne Park Redevelopment – Stage 3 | New | 271555000 | 0 | 0 | 0 | 253450000 | qtr 4 2020-21 | 2017–18 | 2021-06-30 | Department of Health and Human Services | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | GG | Culture, sport and community | The TEI includes funding of $40.000 million from the Melbourne and Olympic Parks Trust.
Melbourne Park redevelopment stage three (Melbourne) | Melbourne Park Redevelopment – Stage 3 | Existing | 271555000 | 0 | 0 | 80786000 | 82462000 | qtr 4 2021‑22 | 2019–20 | 2022-06-30 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | PNFC | Culture, sport and community | The TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust. The estimated completion date has been revised.
Melbourne Park redevelopment stage three (Melbourne) | Melbourne Park Redevelopment – Stage 3 | Existing | 271555000 | 0 | 0 | 18105000 | 190769000 | qtr 4 2020-21 | 2018–19 | 2021-06-30 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | PNFC | Culture, sport and community | The TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust.
Melbourne Park redevelopment stage three (Melbourne) | Melbourne Park Redevelopment – Stage 3 | Existing | 296027000 | 0.090118 | 24472000 | 281522000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | PNFC | Culture, sport and community | TEI has increased by $24.472 million compared with the 2019‑20 Budget due to additional contribution of $20.500 million from Melbourne and Olympic Parks Trust and $3.972 million from Tennis Australia.
Melbourne Park Redevelopment – stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | New | 366141000 | 0 | 0 | 5060000 | 330282000 | qtr 4 2019‑20 | 2014–15 | 2020-06-30 | Other public non‑financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | PNFC | Culture, sport and community | TEI includes anticipated Commonwealth funding of $27.99 million and a contribution of $40.00 million from the Melbourne and Olympic Parks Trust.
Melbourne Park redevelopment stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Completed | 338121000 | 0 | 0 | 338121000 |  | qtr 3 2020‑21 | 2021–22 | 2021-03-31 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | PNFC | Culture, sport and community | The project completion date has been revised due to project completed ahead of schedule.
Melbourne Park Redevelopment – stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Existing | 338151000 | 0 | 0 | 87000000 | 155548000 | qtr 2 2019‑20 | 2016–17 | 2019-12-31 | Other public non‑financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | PNFC | Culture, sport and community
Melbourne Park redevelopment stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Existing | 338121000 | 0 | 0 | 326551000 | 0 | qtr 2 2020‑21 | 2019–20 | 2020-12-31 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | PNFC | Culture, sport and community | TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust.
Melbourne Park redevelopment stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Existing | 338121000 | -8.5761e-05 | -29000 | 259470000 | 11570000 | qtr 2 2020-21 | 2018–19 | 2020-12-31 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | PNFC | Culture, sport and community | The TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust. This project was originally captured under Budget Paper No. 4, Chapter 2 in the 2017-18 Budget.
Melbourne Park Redevelopment – stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Existing | 338151000 | -0.076446 | -27990000 | 21760000 | 251151000 | qtr 4 2019‑20 | 2015–16 | 2020-06-30 | Other public non‑financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | PNFC | Culture, sport and community | TEI has reduced by $27.990 million due to clarification of funding sources.
Melbourne Park redevelopment stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Existing | 338150000 | -2.9573e-06 | -1000 | 169570000 | 63540000 | qtr 2 2019-20 | 2017–18 | 2019-12-31 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | PNFC | Culture, sport and community
Prison capacity expansion (Melbourne) | Prison capacity expansion | New | 143228000 | 0 | 0 | 50513000 | 16132000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Melbourne | Metropolitan |  |  | GG | Justice and emergency services | TEI includes $30.100 million from the Corrections System Expansion, $6.800 million from Corrections Remand upgrade and $0.750 million from Corrections Annual Provisions.
Prison capacity expansion (Melbourne) | Prison capacity expansion | Existing | 124356000 | -0.13176 | -18872000 | 73329000 | 1000000 | qtr 2 2020‑21 | 2019–20 | 2020-12-31 | Department of Justice and Community Safety | Department of Justice and Community Safety | Melbourne | Metropolitan |  |  | GG | Justice and emergency services | TEI, cash flow and timing has been revised in line with a revised project scope.
Prison capacity expansion (Melbourne) | Prison capacity expansion | Completed | 116965000 | -0.059434 | -7391000 | 115655000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Melbourne | Metropolitan |  |  | GG | Justice and emergency services
Melbourne Arts Precinct Transformation Phase One (Melbourne) | Melbourne Arts Precinct transformation Phase One | Existing | 1409534000 | 0 | 0 |  | 1324399000 | qtr 2 2028‑29 | 2021–22 | 2028-12-31 | Department of Jobs, Precincts and Regions | Department of Jobs, Precincts and Regions | Melbourne | Metropolitan |  |  | GG | Culture, sport and community | Initiative funded in the 2020‑21 Budget.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 165000000 | 0 | 0 | 30200000 | 111500000 | qtr 2 2017‑18 | 2014–15 | 2017-12-31 | Department of Health | Department of Health | Melbourne | Metropolitan |  |  | GG | Health and human services | This initiative includes funds allocated in 2012‑13 of $2.000 million for the planning and development of this project.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 201000000 | 0 | 0 | 155542000 | 0 | qtr 2 2019-20 | 2018–19 | 2019-12-31 | Department of Health and Human Services | Department of Health | Melbourne | Metropolitan |  |  | GG | Health and human services | The estimated completion date has been revised to reflect project delivery and cashflows approved by Government.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 165000000 | 0 | 0 | 45800000 | 87900000 | qtr 2 2018‑19 | 2015–16 | 2018-12-31 | Department of Health and Human Services | Department of Health | Melbourne | Metropolitan |  |  | GG | Health and human services | This initiative includes funds allocated in 2012‑13 of $2.000 million for the planning and development of this project.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 201000000 | 0 | 0 | 103452000 | 33548000 | qtr 2 2018-19 | 2017–18 | 2018-12-31 | Department of Health and Human Services | Department of Health | Melbourne | Metropolitan |  |  | GG | Health and human services
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 306707000 | 0.1171 | 32150000 | 239166000 | 40696000 | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Health | Department of Health | Melbourne | Metropolitan |  |  | GG | Health and human services | TEI has increased by $32.150 million compared with the 2019‑20 Budget as approved by Government. The project’s cashflow and estimated completion date have been revised in line with a revised project schedule.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 274557000 | 0.36596 | 73557000 | 199588000 | 13030000 | qtr 2 2021‑22 | 2019–20 | 2021-12-31 | Department of Health and Human Services | Department of Health | Melbourne | Metropolitan |  |  | GG | Health and human services | The project’s TEI has increased to reflect the additional joint funding between the department and the Royal Victorian Eye and Ear Hospital. The cashflow has been revised in line with a revised project schedule.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 201000000 | 0.21818 | 36000000 | 77100000 | 63800000 | qtr 2 2018‑19 | 2016–17 | 2018-12-31 | Department of Health and Human Services | Department of Health | Melbourne | Metropolitan |  |  | GG | Health and human services | The TEI for this project has increased due to an additional $31.400 million provided in 2016‑17 (including a $10.000 million contribution from the health service) in order to complete the project. The health service has also separately funded $4.600 million for the addition of a new Education Centre, bringing the combined TEI to $201.000 million.
Port capacity expansion project (Melbourne) | Port Capacity Expansion project | Existing | 641298000 | -0.28111 | -250775000 | 416929000 | 0 | na | 2015–16 | 2099-06-30 | Port of Melbourne Corporation | Port of Melbourne Corporation | Melbourne | Metropolitan |  |  | PNFC | Transport | Due to the Port of Melbourne lease transaction, the budget does not take into account any Port of Melbourne Corporation financial data beyond 2015‑16.
Port capacity expansion project (Melbourne) | Port Capacity Expansion project | Discontinued | 0 | -1 | -598109000 | 0 | 0 | Discontinued | 2017–18 |  | Victorian Ports Corporation (Melbourne) | Port of Melbourne Corporation | Melbourne | Metropolitan |  |  | PNFC | Transport
Port capacity expansion project (Melbourne) | Port Capacity Expansion project | Existing | 598109000 | -0.067346 | -43189000 | 456886000 | 0 | ongoing | 2016–17 | 2099-06-30 | Port of Melbourne Corporation | Port of Melbourne Corporation | Melbourne | Metropolitan |  |  | PNFC | Transport
Port Capacity Expansion project | Port Capacity Expansion project | Existing | 892073000 | 0 | 0 | 144223000 | 420924000 | qtr 4 2016‑17 | 2014–15 | 2017-06-30 | Port of Melbourne Corporation | Port of Melbourne Corporation | Unspecified | Unspecified |  |  | PNFC | Transport
Delivering more hospital beds for Melbourne’s East (Angliss Hospital Expansion Stage 2) (Ferntree Gully) | Delivering more hospital beds for Melbourne’s East | New | 103420000 | 0 | 0 |  | 103164000 | qtr 4 2026‑27 | 2021–22 | 2027-06-30 | Department of Health | Department of Health | Ferntree Gully | Metropolitan |  |  | GG | Health and human services | TEI includes $4.556 million announced in the 2019‑20 Budget.
Drysdale bypass (Drysdale) | Drysdale bypass | New | 102560000 | 0 | 0 | 0 | 98140000 | qtr 4 2019‑20 | 2016–17 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Drysdale | Regional |  |  | GG | Transport | Balance of election commitment was delivered in the 2015‑16 Budget.
Drysdale bypass (Drysdale) | Drysdale bypass | Completed | 117377000 | 0 | 0 | 117377000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Transport | Department of Transport | Drysdale | Regional |  |  | GG | Transport
Drysdale bypass (Drysdale) | Drysdale bypass | Existing | 117377000 | 0 | 0 | 66563000 | 7311000 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Department of Transport | Department of Transport | Drysdale | Regional |  |  | GG | Transport
Drysdale bypass (Drysdale) | Drysdale bypass | Existing | 102377000 | -0.0017843 | -183000 | 8878000 | 74440000 | qtr 4 2019-20 | 2017–18 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Drysdale | Regional |  |  | GG | Transport | TEI excludes corporate costs.
Drysdale bypass (Drysdale) | Drysdale bypass | Existing | 117377000 | 0.14652 | 15000000 | 22018000 | 60479000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Drysdale | Regional |  |  | GG | Transport | TEI has increased by $15.000 million due to market conditions, and is funded by savings achieved on other projects.
Expanding and improving bed‑based forensic mental health services: Thomas Embling Hospital (Fairfield) | Expanding and improving bed‑based forensic mental health services: Thomas Embling Hospital | New | 349560000 | 0 | 0 | 6380000 | 314625000 | qtr 4 2024‑25 | 2021–22 | 2025-06-30 | Department of Health | Department of Health | Fairfield | Metropolitan |  |  | GG | Health and human services | TEI includes $9.000 million reallocated from Forensic Mental Health Bed‑based Services Expansion (Fairfield).
Frankston Line stabling (Seaford) | Frankston Line stabling | New | 187400000 | 0 | 0 | 0 | 116600000 | tbc | 2017–18 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Seaford | Metropolitan |  |  | PNFC | Transport
Frankston Line stabling (Seaford) | Frankston Line stabling | Existing | 236685000 | 0.26299 | 49285000 | 34065000 | 69313000 | qtr 3 2019-20 | 2018–19 | 2020-03-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Seaford | Metropolitan |  |  | PNFC | Transport | TEI includes additional funding of $49.285 million to address site contamination and risk provisions.
Frankston Line stabling (Kananook) | Frankston Line stabling | Completed | 239983000 | 0.013943 | 3300000 | 222180000 |  | qtr 4 2020‑21 | 2021–22 | 2021-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Kananook | Regional |  |  | PNFC | Transport | TEI has increased by $3.300 million due to reprioritisation from other projects.
Frankston Line stabling (Kananook) | Frankston Line stabling | Existing | 236683000 | -8.45e-06 | -2000 | 109994000 | 2616000 | qtr 3 2019‑20 | 2019–20 | 2020-03-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Kananook | Regional |  |  | PNFC | Transport | TEI excludes $0.002 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards.
Goulburn Valley Health redevelopment (Shepparton) | Goulburn Valley Health redevelopment – planning and development | New | 168525000 | 0 | 0 | 0 | 163525000 | qtr 4 2020‑21 | 2016–17 | 2021-06-30 | Department of Health and Human Services | Department of Health | Shepparton | Regional |  |  | GG | Health and human services | Additional funding of $1.000 million was provided in 2015‑16 for planning and development, bringing the Government’s contribution to $169.525 million.
Goulburn Valley Health redevelopment – planning and development (Shepparton) | Goulburn Valley Health redevelopment – planning and development | Existing | 171234000 | 0 | 0 | 63349000 | 27749000 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Department of Health and Human Services | Department of Health | Shepparton | Regional |  |  | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Goulburn Valley Health redevelopment (Shepparton) | Goulburn Valley Health redevelopment – planning and development | Existing | 229349000 | 0.33939 | 58115000 | 178907000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Health | Department of Health | Shepparton | Regional |  |  | GG | Health and human services | TEI has increased by $58.115 million compared with the 2019‑20 Budget as approved by Government. The project’s cashflow has been revised in line with a revised project schedule.
Goulburn Valley Health redevelopment – planning and development (Shepparton) | Goulburn Valley Health redevelopment – planning and development | Existing | 171234000 | 0.0041577 | 709000 | 19485000 | 98749000 | qtr 4 2020-21 | 2018–19 | 2021-06-30 | Department of Health and Human Services | Department of Health | Shepparton | Regional |  |  | GG | Health and human services | Additional funding of $1.709 million was provided in 2017-18 through internal prioritisation.
Goulburn Valley Health redevelopment – planning and development (Shepparton) | Goulburn Valley Health redevelopment – planning and development | Existing | 170525000 | 0.011868 | 2000000 | 4649000 | 136477000 | qtr 4 2020-21 | 2017–18 | 2021-06-30 | Department of Health and Human Services | Department of Health | Shepparton | Regional |  |  | GG | Health and human services
Shepparton line upgrade – Stage 2 (Shepparton) | Regional Rail Revival – Shepparton Corridor Upgrade – Stage 2 | New | 312909000 | 0 | 0 | 0 | 307909000 | qtr 4 2021-22 | 2018–19 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Shepparton | Regional |  |  | PNFC | Transport
Shepparton Corridor Upgrade – Stage 2 (Shepparton) | Regional Rail Revival – Shepparton Corridor Upgrade – Stage 2 | Existing | 312487000 | -0.0013486 | -422000 | 10384000 | 283603000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Shepparton | Regional |  |  | PNFC | Transport | TEI excludes $0.422 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. Project name changed from ’Shepparton Line Upgrade – Stage 2’ published in 2018-19 Budget. The estimated completion date has been revised due to the packaging of the Gippsland‑Shepparton‑Bendigo alliance.
Regional Rail Revival – Shepparton Corridor Upgrade – Stage 2 (Shepparton) | Regional Rail Revival – Shepparton Corridor Upgrade – Stage 2 | Existing | 314118000 | 0.0052194 | 1631000 | 43517000 | 153201000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Shepparton | Regional | Regional Rail Revival |  | PNFC | Transport | TEI includes $2.312 million reprioritised from Regional Rail Revival and excludes $1.103 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. Estimated completion date has been revised to reflect a revised schedule of works.
Greater Shepparton Secondary College 2020‑21 (Shepparton) | Greater Shepparton Secondary College 2020‑21 | Existing | 119000000 | 0 | 0 | 100352000 | 29000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Education and Training | Department of Education and Training | Shepparton | Regional | School education |  | GG | Education and Training | Initiative funded in the Building Works package announced in May 2020.
Regional Rail Revival – Shepparton Line Upgrade – Stage 3 (Shepparton) | Regional Rail Revival – Shepparton Line Upgrade – Stage 3 | Existing | 400000000 | 0 | 0 | 5090000 | 337344000 | qtr 4 2023‑24 | 2021–22 | 2024-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Shepparton | Regional | Regional Rail Revival |  | PNFC | Transport | Initiative funded in the 2020‑21 Budget. TEI includes $320.000 million of Commonwealth funding.
Hall Road Upgrade (Skye) | Hall Road Upgrade | New | 169000000 | 0 | 0 | 0 | 168600000 | tbc | 2019–20 | 2089-06-30 | Department of Transport | Department of Transport | Skye | Metropolitan |  |  | GG | Transport
Hall Road Upgrade (Skye) | Hall Road Upgrade | Existing | 282504000 | 0.67162 | 113504000 | 9072000 | 214554000 | qtr 1 2024‑25 | 2021–22 | 2024-09-30 | Department of Transport | Department of Transport | Skye | Metropolitan |  |  | GG | Transport | TEI has increased by $113.504 million. TEI includes $141.252 million of Commonwealth funding.
Western Port Highway (Skye) | Western Port Highway | Existing | 113649000 | 0 | 0 | 6290000 | 8072000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Transport | Department of Transport | Skye | Metropolitan | Urban Congestion Package |  | GG | Transport | TEI has increased by $59.349 million. TEI includes $57.500 million of Commonwealth funding.
Lara Prison precinct expansion (Bacchus Marsh) | Chisholm Road prison project | New | 689450000 | 0 | 0 | 10373000 | 623728000 | qtr 4 2021-22 | 2018–19 | 2022-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | Bacchus Marsh | Regional |  |  | GG | Justice and emergency services
Chisholm Road prison project (Chisholm Road) | Chisholm Road prison project | New | 689450000 | 0 | 0 | 36199000 | 400215000 | qtr 4 2021‑22 | 2019–20 | 2022-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | Chisholm Road | Regional |  |  | GG | Justice and emergency services | Previously known as Lara Prison precinct expansion published in 2018‑19 budget papers. Cash flow has been revised in line with a revised project schedule.
Chisholm Road prison project (non‑metropolitan) | Chisholm Road prison project | Existing | 1118530000 | 0.62235 | 429080000 | 636689000 | 21437000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Justice and Community Safety | Department of Justice and Community Safety | Non-metropolitan | Regional |  |  | GG | Justice and emergency services | TEI has increased compared with the 2019‑20 Budget due to $429.080 million being provided from the Men’s Prison System Capacity (statewide) to deliver a further 548 beds. The project’s cashflow has been revised in line with a revised project schedule. The estimated completion date has been revised to quarter 2 2022‑23 to reflect a revised project schedule.
M80 Upgrade – EJ Whitten Bridge to Sunshine Avenue (Sunshine North) | M80 Upgrade – EJ Whitten Bridge to Sunshine Avenue | New | 150000000 | 0 | 0 | 0 | 110000000 | qtr 4 2017‑18 | 2015–16 | 2018-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Sunshine North | Metropolitan |  |  | GG | Transport
M80 upgrade – Sunshine Avenue to Calder Fwy (Sunshine North) | M80 Ring Road upgrade Sunshine Avenue to Calder Freeway | New | 300000000 | 0 | 0 | 3015000 | 171600000 | qtr 2 2018‑19 | 2016–17 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Sunshine North | Metropolitan |  |  | GG | Transport | TEI includes $150 million of Commonwealth funding.
M80 Ring Road upgrade Sunshine Avenue to Calder Freeway (Sunshine North) | M80 Ring Road upgrade Sunshine Avenue to Calder Freeway | Completed | 293762000 | 0 | 0 | 172416000 | 0 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Department of Transport | Department of Transport | Sunshine North | Metropolitan |  |  | GG | Transport | TEI includes $150.000 million of Commonwealth funding.
M80 Ring Road upgrade Sunshine Avenue to Calder Freeway (Sunshine North) | M80 Ring Road upgrade Sunshine Avenue to Calder Freeway | Existing | 294118000 | -0.019607 | -5882000 | 66873000 | 144926000 | qtr 2 2018-19 | 2017–18 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Sunshine North | Metropolitan |  |  | GG | Transport | TEI excludes corporate costs. TEI includes $150.000 million of Commonwealth funding. Project name changed from M80 Upgrade Sunshine Avenue to Calder Freeway (Sunshine North) published in 2016-17 budget papers.
M80 Ring Road upgrade Sunshine Avenue to Calder Freeway (Sunshine North) | M80 Ring Road upgrade Sunshine Avenue to Calder Freeway | Existing | 293762000 | -0.0012104 | -356000 | 158079000 | 115314000 | qtr 2 2018-19 | 2018–19 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Sunshine North | Metropolitan |  |  | GG | Transport | TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $150.000 million of Commonwealth funding.
Melbourne Airport Rail | Melbourne Airport Rail | New | 680680000 | 0 | 0 | 10000000 | 620680000 | tbc | 2019–20 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Unspecified | Unspecified |  |  | PNFC | Transport | This funding represents the Commonwealth contribution to the project. The Government has made a substantial provision in the Victorian Transport Fund for this project. The project is in its planning phase.
North East Link | North East Link Whole | New | 15640286000 | 0 | 0 | 0 | 0 | qtr 4 2026‑27 | 2019–20 | 2027-06-30 | Department of Transport | Department of Transport | Unspecified | Unspecified |  |  | GG | Transport | TEI includes $143.765 million in funding announced in previous budgets and excludes $150.011 million due to certain expenditure being recognised as expensed State costs (rather than capitalised) in accordance with relevant accounting standards. TEI excludes financing costs. Funding profile is not reported at this time due to commercial sensitivity of the live tender process.
North East Link (from Greensborough) | North East Link Whole | Existing | 15440602000 | -0.012767 | -199684000 |  |  | qtr 4 2026‑27 | 2021–22 | 2027-06-30 | Department of Transport | Department of Transport | Greensborough | Metropolitan |  |  | GG | Transport | TEI excludes $349.695 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. TEI excludes financing costs. Funding profile is not reported at this time due to commercial sensitivity of the live tender process.
Suburban Rail Loop | Suburban Rail Loop | New | 250000000 | 0 | 0 | 0 | 0 | tbc | 2019–20 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Unspecified | Unspecified |  |  | PNFC | Transport | Funding is for detailed planning and development activities.
Melbourne Exhibition Centre – stage 2 development (Southbank) | Melbourne Exhibition Centre Stage 2 Development | New | 168700000 | 0 | 0 | 71000000 | 0 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Jobs, Precincts and Regions | Southbank | Metropolitan |  |  | GG | Culture, sport and community | TEI reflects State capital construction component only.
Melbourne Exhibition Centre Stage 2 Development (Southbank) | Melbourne Exhibition Centre Stage 2 Development | Completed | 168700000 | 0 | 0 | 168700000 | 0 | qtr 1 2018‑19 | 2019–20 | 2018-09-30 | Department of Jobs, Precincts and Regions | Department of Jobs, Precincts and Regions | Southbank | Metropolitan |  |  | GG | Culture, sport and community | The estimated completion date has been revised. TEI reflects the state capital construction component only.
Melbourne Exhibition Centre – stage 2 development (Southbank) | Melbourne Exhibition Centre Stage 2 Development | Existing | 168700000 | 0 | 0 | 168700000 | 0 | qtr 4 2017-18 | 2018–19 | 2018-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Jobs, Precincts and Regions | Southbank | Metropolitan |  |  | GG | Culture, sport and community | The estimated completion date has been revised. TEI reflects the state capital construction component only.
Mernda rail extension project (Mernda) | Mernda rail extension project | New | 587714000 | 0 | 0 | 12466000 | 475448000 | qtr 2 2018‑19 | 2016–17 | 2018-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Mernda | Metropolitan |  |  | PNFC | Transport | $9.000 million in development funding was provided in the 2015‑16 Budget.
Mernda rail extension project (Mernda) | Mernda rail extension project | Existing | 596714000 | 0.015314 | 9000000 | 149824000 | 104050000 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Mernda | Metropolitan |  |  | PNFC | Transport | TEI increase of $9.000 million reflects project development funding provided in the 2015-16 Budget. The completion date reflects the scheduled program of works after the award of the contract in November 2016.
Mernda rail extension project (Mernda) | Mernda rail extension project | Existing | 604114000 | 0.012401 | 7400000 | 468101000 | 2349000 | qtr 1 2018-19 | 2018–19 | 2018-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Mernda | Metropolitan |  |  | PNFC | Transport | The estimated completion date has been revised. TEI includes additional funding of $7.400 million for Hawkstowe Station under GAIC.
Mernda rail extension project (Mernda) | Mernda rail extension project | Completed | 603027000 | -0.0017993 | -1087000 | 591538000 | 0 | qtr 1 2020‑21 | 2019–20 | 2020-09-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Mernda | Metropolitan |  |  | PNFC | Transport | TEI has been reduced by $0.024 million due to savings and $1.063 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards.
Monash Freeway upgrade – Stage 2 (South-East Melbourne) | Monash Freeway upgrade – Stage 2 | New | 684424000 | 0 | 0 | 1442000 | 665582000 | qtr 4 2022-23 | 2018–19 | 2023-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | South-East Melbourne | Metropolitan |  |  | GG | Transport | TEI includes Commonwealth funding of $483.800 million for the capital component of this initiative.
Monash Freeway upgrade – Stage 2 (South East Melbourne) | Monash Freeway upgrade – Stage 2 | Existing | 684424000 | 0 | 0 | 35313000 | 441984000 | qtr 4 2022‑23 | 2019–20 | 2023-06-30 | Department of Transport | Department of Transport | South-East Melbourne | Metropolitan |  |  | GG | Transport | TEI includes $483.800 million of Commonwealth funding.
Monash Freeway upgrade – Stage 2 (South‑east Melbourne) | Monash Freeway upgrade – Stage 2 | Existing | 1037852000 | 0.51639 | 353428000 | 435794000 | 301837000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Transport | Department of Transport | South-East Melbourne | Metropolitan |  |  | GG | Transport | TEI has increased by $351.499 million due to market escalation and $1.900 million in developer contributions. TEI includes $667.600 million of Commonwealth funding. TEI excludes $16.002 million due to certain expenditure reclassified as operating instead of capital in line with accounting standards. The estimated completion date has been brought forward to quarter 2 2022‑23 due to contract award based on an accelerated program.
Mordialloc Bypass (Braeside) | Mordialloc Freeway | New | 300000000 | 0 | 0 | 0 | 296700000 | qtr 4 2022-23 | 2017–18 | 2023-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Braeside | Metropolitan |  |  | GG | Transport
Mordialloc Freeway (Braeside) | Mordialloc Freeway | Existing | 375000000 | 0 | 0 | 57651000 | 107423000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Department of Transport | Department of Transport | Braeside | Metropolitan |  |  | GG | Transport
Mordialloc Freeway (Braeside) | Mordialloc Freeway | Existing | 375000000 | 0.25 | 75000000 | 14300000 | 309600000 | qtr 2 2022-23 | 2018–19 | 2022-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Braeside | Metropolitan |  |  | GG | Transport | TEI includes a further $75.000 million for additional scope approved in the 2018-19 Budget.
Mordialloc Freeway (Braeside) | Mordialloc Freeway | Existing | 522246000 | 0.39266 | 147246000 | 402547000 | 13811000 | qtr 2 2021‑22 | 2021–22 | 2021-12-31 | Department of Transport | Department of Transport | Braeside | Metropolitan |  |  | GG | Transport | TEI has increased by $148.246 million due to increased scope and market escalation. TEI excludes $1.000 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards. The estimated completion date has been brought forward to quarter 2 2021‑22 due to contract award based on an accelerated program.
New Wyndham Law Court Development (Werribee) | New Wyndham Law Court Development | Existing | 271128000 | 0 | 0 | 2000000 | 251128000 | qtr 1 2024‑25 | 2021–22 | 2024-09-30 | Court Services Victoria | Court Services Victoria | Werribee | Metropolitan |  |  | GG | Justice and emergency services | Initiative funded in the 2020‑21 Budget.
North East Link (from Greensborough) | North East Link Planning | New | 100000000 | 0 | 0 | 19993000 | 0 | qtr 4 2026-27 | 2017–18 | 2027-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Greensborough | Metropolitan |  |  | GG | Transport
North East Link (from Greensborough) | North East Link Planning | Existing | 143765000 | 0.43765 | 43765000 | 20665000 | 0 | qtr 4 2026-27 | 2018–19 | 2027-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Greensborough | Metropolitan |  |  | GG | Transport | TEI has increased by $104.000 million due to approval of additional funding to progress procurement and planning approvals, offset by a $60.235 million decrease due to certain expenditure being recognised as operating instead of capital in line with accounting standards
Northern Hospital inpatient expansion – Stage 2 (Epping) | Northern Hospital inpatient expansion – Stage 2 | New | 162672000 | 0 | 0 | 0 | 156000000 | qtr 4 2020-21 | 2017–18 | 2021-06-30 | Department of Health and Human Services | Department of Health | Epping | Metropolitan |  |  | GG | Health and human services
Northern Hospital inpatient expansion – Stage 2 (Epping) | Northern Hospital inpatient expansion – Stage 2 | Existing | 162672000 | 0 | 0 | 148000000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Health | Department of Health | Epping | Metropolitan |  |  | GG | Health and human services | The project’s cashflow and estimated completion date have been revised in line with a revised project schedule.
Northern Hospital inpatient expansion – Stage 2 (Epping) | Northern Hospital inpatient expansion – Stage 2 | Existing | 162672000 | 0 | 0 | 26268000 | 86404000 | qtr 1 2021‑22 | 2019–20 | 2021-09-30 | Department of Health and Human Services | Department of Health | Epping | Metropolitan |  |  | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Northern Hospital inpatient expansion – Stage 2 (Epping) | Northern Hospital inpatient expansion – Stage 2 | Existing | 162672000 | 0 | 0 | 2472000 | 130200000 | qtr 4 2020-21 | 2018–19 | 2021-06-30 | Department of Health and Human Services | Department of Health | Epping | Metropolitan |  |  | GG | Health and human services
O'Herns Road upgrade (Epping) | O’Herns Road upgrade | New | 77750000 | 0 | 0 | 0 | 70350000 | qtr 4 2018‑19 | 2016–17 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Epping | Metropolitan |  |  | GG | Transport | The TEI represents total value of the project and is subject to matching Commonwealth Government funding.
O’Herns Road upgrade (Epping) | O’Herns Road upgrade | Existing | 102803000 | 0.32132 | 25000000 | 35391000 | 7613000 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Department of Transport | Department of Transport | Epping | Metropolitan | Urban Congestion Package |  | GG | Transport | TEI has increased by $25.000 million due to market escalation. TEI includes $25.801 million of Commonwealth funding. The estimated completion date has been revised to quarter 4 2020‑21 due to environmental approvals.
Urban Congestion Package – O’Herns Road upgrade (Epping) | O’Herns Road upgrade | Existing | 113715000 | 0.10614 | 10912000 | 110715000 |  | qtr 1 2021‑22 | 2021–22 | 2021-09-30 | Department of Transport | Department of Transport | Epping | Metropolitan | Urban Congestion Package |  | GG | Transport | TEI has increased by $6.412 million due to increased scope funded by a developer contribution and $4.500 million due to utility relocation and COVID‑19 impacts. TEI includes $25.801 million of Commonwealth funding. The estimated completion date has been extended to quarter 1 2021‑22 due to COVID‑19 and utility relocation impacts.
O’Herns Road upgrade (Epping) | O’Herns Road upgrade | Existing | 77786000 | 0.00046302 | 36000 | 2591000 | 54655000 | qtr 2 2019-20 | 2017–18 | 2019-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Epping | Metropolitan |  |  | GG | Transport | The estimated completion date has been extended. TEI excludes corporate costs. TEI includes $25.800 million of Commonwealth funding.
O’Herns Road upgrade (Epping) | O’Herns Road upgrade | Existing | 77803000 | 0.00021855 | 17000 | 13878000 | 28368000 | qtr 2 2019-20 | 2018–19 | 2019-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Epping | Metropolitan | Urban Congestion Package |  | GG | Transport | TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes additional funding of $0.017 million for revised scope within this program. TEI includes $25.801 million of Commonwealth funding.
Melbourne Wholesale Markets – redevelopment (Epping) | Melbourne Wholesale Markets redevelopment | Existing | 492418000 | 0 | 0 | 414394000 | 0 | qtr 4 2014‑15 | 2014–15 | 2015-06-30 | Department of State Development, Business and Innovation | Department of Environment, Land, Water and Planning | Epping | Metropolitan |  |  | GG | Culture, sport and community | TEI has increased by $39.000 million from the 2013‑14 Budget to facilitate current contracted obligations for construction works prior to return of these funds by the Melbourne Market Authority via a debt facility.
Melbourne Wholesale Markets redevelopment (Epping) | Melbourne Wholesale Markets redevelopment | Existing | 484436000 | -0.01621 | -7982000 | 437436000 | 0 | qtr 1 2015‑16 | 2015–16 | 2015-09-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Environment, Land, Water and Planning | Epping | Metropolitan |  |  | GG | Culture, sport and community | TEI is reduced by $7.982 million. This is due to the transfer of funds from capital to output funding. Project has a revised estimated completion date.
Streamlining Hoddle Street (Richmond) | Streamlining Hoddle Street | New | 56210000 | 0 | 0 | 0 | 44970000 | qtr 4 2018‑19 | 2016–17 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Richmond | Metropolitan |  |  | GG | Transport | Balance of election commitment was delivered in the 2015‑16 Budget.
Streamlining Hoddle Street (Richmond) | Streamlining Hoddle Street | Completed | 108554000 | 0 | 0 | 95182000 | 0 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Department of Transport | Department of Transport | Richmond | Metropolitan |  |  | GG | Transport
Streamlining Hoddle Street (Richmond) | Streamlining Hoddle Street | Existing | 56180000 | -0.00053371 | -30000 | 7357000 | 12676000 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Richmond | Metropolitan |  |  | GG | Transport | TEI excludes corporate costs.
Streamlining Hoddle Street (Richmond) | Streamlining Hoddle Street | Existing | 108554000 | 0.93225 | 52374000 | 45117000 | 11240000 | qtr 4 2018-19 | 2018–19 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Richmond | Metropolitan |  |  | GG | Transport | TEI for project has changed as a result of corporate cost not being reported against this project. TEI has increased by $52.610 million funded by savings achieved on other projects.
Thompsons Road duplication (Lyndhurst) | Thompsons Road duplication | New | 148300000 | 0 | 0 | 0 | 117600000 | qtr 4 2018‑19 | 2016–17 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Lyndhurst | Metropolitan |  |  | GG | Transport | Balance of election commitment was delivered in the 2015‑16 Budget.
Thompsons Road duplication (Lyndhurst) | Thompsons Road duplication | Completed | 123243000 | 0 | 0 | 122979000 | 0 | qtr 4 2020‑21 | 2019–20 | 2021-06-30 | Department of Transport | Department of Transport | Lyndhurst | Metropolitan |  |  | GG | Transport
Thompsons Road duplication (Lyndhurst) | Thompsons Road duplication | Existing | 123243000 | -0.16825 | -24930000 | 58495000 | 17523000 | qtr 4 2018-19 | 2018–19 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Lyndhurst | Metropolitan |  |  | GG | Transport | TEI has reduced by $24.930 million due to identified project savings.
Thompsons Road duplication (Lyndhurst) | Thompsons Road duplication | Existing | 148173000 | -0.00085637 | -127000 | 29475000 | 73013000 | qtr 4 2018-19 | 2017–18 | 2019-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Lyndhurst | Metropolitan |  |  | GG | Transport | TEI excludes corporate costs.
Victorian Heart Hospital (Clayton) | Victorian Heart Hospital | New | 135000000 | 0 | 0 | 0 | 135000000 | tbc | 2016–17 | 2089-06-30 | Department of Health and Human Services | Department of Health | Clayton | Metropolitan |  |  | GG | Health and human services | Additional funding of $15.000 million was provided in 2015‑16 for planning and development, bringing the Government’s contribution to $150.000 million. Final project TEI and completion date will be determined following completion of business planning and development, and confirmation of funding contributions from project partners.
Victorian Heart Hospital (Clayton) | Victorian Heart Hospital | Existing | 564000000 | 0 | 0 | 166267000 | 163853000 | qtr 2 2022‑23 | 2021–22 | 2022-12-31 | Department of Health | Department of Health | Clayton | Metropolitan |  |  | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Victorian Heart Hospital (Clayton) | Victorian Heart Hospital | Existing | 543000000 | 3.0222 | 408000000 | 12868000 | 511000000 | qtr 2 2022-23 | 2018–19 | 2022-12-31 | Department of Health and Human Services | Department of Health | Clayton | Metropolitan |  |  | GG | Health and human services | TEI includes contributions from Monash University of $65.000 million and funding provided in 2017‑18 and in the 2017-18 Budget. The estimated completion date has been revised to reflect the final project scope and timelines approved by Government.
Victorian Heart Hospital (Clayton) | Victorian Heart Hospital | Existing | 564000000 | 0.038674 | 21000000 | 71773000 | 420000000 | qtr 2 2022‑23 | 2019–20 | 2022-12-31 | Department of Health and Human Services | Department of Health | Clayton | Metropolitan |  |  | GG | Health and human services | The project’s TEI has increased by $21.000 million to reflect change design requirements by Monash University. The cashflow has been revised in line with a new project schedule.
Monash Children’s Hospital (Clayton) | Monash Children's Hospital | Existing | 250000000 | 0 | 0 | 18500000 | 184500000 | qtr 2 2016‑17 | 2014–15 | 2016-12-31 | Department of Health | Department of Health | Clayton | Metropolitan |  |  | GG | Health and human services | This initiative includes funds allocated in 2011‑12 and 2012‑13 for the planning and development of this project.
Monash Children's Hospital (Clayton) | Monash Children's Hospital | Existing | 250000000 | 0 | 0 | 45600000 | 94400000 | qtr 2 2016‑17 | 2015–16 | 2016-12-31 | Department of Health and Human Services | Department of Health | Clayton | Metropolitan |  |  | GG | Health and human services | This initiative includes funds allocated in 2011‑12 and 2012‑13 for the planning and development of this project.
Monash Children’s Hospital (Clayton) | Monash Children's Hospital | Existing | 271855000 | 0.052987 | 13680000 | 247195000 | 22037000 | qtr 4 2017-18 | 2017–18 | 2018-06-30 | Department of Health and Human Services | Department of Health | Clayton | Metropolitan |  |  | GG | Health and human services
Monash Children’s Hospital (Clayton) | Monash Children's Hospital | Completed | 271860000 | 1.8392e-05 | 5000 | 270309000 | 0 | qtr 4 2018-19 | 2018–19 | 2019-06-30 | Department of Health and Human Services | Department of Health | Clayton | Metropolitan |  |  | GG | Health and human services
Monash Children’s Hospital (Clayton) | Monash Children's Hospital | Existing | 258175000 | 0.0327 | 8175000 | 163563000 | 0 | qtr 2 2016‑17 | 2016–17 | 2016-12-31 | Department of Health and Human Services | Department of Health | Clayton | Metropolitan |  |  | GG | Health and human services | The TEI for this project includes $3.800 million for the MCH Helipad, reported as a separate project in the 2015‑16 budget. The TEI has also increased due to $4.375 million in additional funding provided by Monash University for accommodation space.
Western Women’s and Children’s Hospital (St Albans) | Joan Kirner Women’s and Children’s Hospital | New | 200000000 | 0 | 0 | 0 | 185270000 | qtr 4 2019‑20 | 2015–16 | 2020-06-30 | Department of Health and Human Services | Department of Health | St Albans | Metropolitan |  |  | GG | Health and human services
Joan Kirner Women’s and Children’s Hospital (St Albans) | Joan Kirner Women’s and Children’s Hospital | Completed | 200000000 | 0 | 0 | 200000000 |  | qtr 4 2020‑21 | 2021–22 | 2021-06-30 | Department of Health | Department of Health | St Albans | Metropolitan |  |  | GG | Health and human services
Joan Kirner Women’s and Children’s Hospital (St Albans) | Joan Kirner Women’s and Children’s Hospital | Existing | 200000000 | 0 | 0 | 4765000 | 166053000 | qtr 4 2019‑20 | 2016–17 | 2020-06-30 | Department of Health and Human Services | Department of Health | St Albans | Metropolitan |  |  | GG | Health and human services
Joan Kirner Women’s and Children’s Hospital (St Albans) | Joan Kirner Women’s and Children’s Hospital | Existing | 200000000 | 0 | 0 | 102124000 | 2507000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Department of Health and Human Services | Department of Health | St Albans | Metropolitan |  |  | GG | Health and human services
Joan Kirner Women’s and Children’s Hospital (St Albans) | Joan Kirner Women’s and Children’s Hospital | Existing | 200000000 | 0 | 0 | 184897000 | 0 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Department of Health and Human Services | Department of Health | St Albans | Metropolitan |  |  | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule. Construction of the hospital is now complete and is scheduled to open in May 2019.
Joan Kirner Women’s and Children’s Hospital (St. Albans) | Joan Kirner Women’s and Children’s Hospital | Existing | 200000000 | 0 | 0 | 20655000 | 66662000 | qtr 4 2019-20 | 2017–18 | 2020-06-30 | Department of Health and Human Services | Department of Health | St Albans | Metropolitan |  |  | GG | Health and human services
Wonthaggi Hospital expansion (Wonthaggi) | Wonthaggi Hospital emergency department expansion | New | 115000000 | 0 | 0 | 0 | 113000000 | qtr 4 2022-23 | 2018–19 | 2023-06-30 | Department of Health and Human Services | Department of Health | Wonthaggi | Regional |  |  | GG | Health and human services
Wonthaggi Hospital emergency department expansion (Wonthaggi) | Wonthaggi Hospital emergency department expansion | Existing | 115000000 | 0 | 0 | 2000000 | 83000000 | qtr 4 2022‑23 | 2019–20 | 2023-06-30 | Department of Health and Human Services | Department of Health | Wonthaggi | Regional |  |  | GG | Health and human services
Wonthaggi Hospital emergency department expansion (Wonthaggi) | Wonthaggi Hospital emergency department expansion | Existing | 115000000 | 0 | 0 | 18645000 | 36355000 | qtr 4 2022‑23 | 2021–22 | 2023-06-30 | Department of Health | Department of Health | Wonthaggi | Regional |  |  | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Yan Yean Road duplication (Plenty) | Yan Yean Road duplication – Stage 1 | New | 126160000 | 0 | 0 | 0 | 113540000 | qtr 4 2019‑20 | 2016–17 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Plenty | Metropolitan |  |  | GG | Transport | Balance of election commitment was delivered in the 2015‑16 Budget.
Yan Yean Road duplication – Stage 1 (Plenty) | Yan Yean Road duplication – Stage 1 | Completed | 125958000 | 0 | 0 | 125958000 |  | qtr 1 2021‑22 | 2021–22 | 2021-09-30 | Department of Transport | Department of Transport | Plenty | Metropolitan | Urban Congestion Package |  | GG | Transport
Yan Yean Road duplication – Stage 1 (Plenty) | Yan Yean Road duplication – Stage 1 | Existing | 125958000 | 0 | 0 | 117737000 | 1966000 | qtr 4 2019‑20 | 2019–20 | 2020-06-30 | Department of Transport | Department of Transport | Plenty | Metropolitan |  |  | GG | Transport
Yan Yean Road duplication (Plenty) | Yan Yean Road duplication – Stage 1 | Existing | 125827000 | -0.0026395 | -333000 | 12662000 | 75284000 | qtr 4 2019-20 | 2017–18 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Plenty | Metropolitan |  |  | GG | Transport | TEI excludes corporate costs.
Yan Yean Road duplication – Stage 1 (Plenty) | Yan Yean Road duplication – Stage 1 | Existing | 125958000 | 0.0010411 | 131000 | 53975000 | 27543000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Plenty | Metropolitan |  |  | GG | Transport | TEI for project has changed as a result of corporate cost not being reported against this project.
Box Hill Hospital – Redevelopment (Box Hill) | Box Hill Hospital – Redevelopment | Existing | 447500000 | 0 | 0 | 302800000 | 35700000 | qtr 2 2015‑16 | 2014–15 | 2015-12-31 | Department of Health | Department of Health | Box Hill | Metropolitan |  |  | GG | Health and human services
Box Hill Hospital – Redevelopment (Box Hill) | Box Hill Hospital – Redevelopment | Existing | 447500000 | 0 | 0 | 429891000 | 9037000 | qtr 4 2016‑17 | 2016–17 | 2017-06-30 | Department of Health and Human Services | Department of Health | Box Hill | Metropolitan |  |  | GG | Health and human services | The project completion date has been revised to reflect the separate ICT component of the project.
Box Hill Hospital – Redevelopment (Box Hill) | Box Hill Hospital – Redevelopment | Existing | 447500000 | 0 | 0 | 411800000 | 0 | qtr 2 2015‑16 | 2015–16 | 2015-12-31 | Department of Health and Human Services | Department of Health | Box Hill | Metropolitan |  |  | GG | Health and human services
Building a world class hospital for Frankston families (Frankston) | Building a world class hospital for Frankston families | Existing | 605260000 | 0 | 0 | 18000000 | 543934000 | qtr 4 2024‑25 | 2021–22 | 2025-06-30 | Department of Health | Department of Health | Frankston | Metropolitan |  |  | GG | Health and human services | Initiative funded in the 2020‑21 Budget. The TEI has increased by $43.260 million due to revised project scope. The estimated completion date has been revised to quarter 4 2024‑25 due to COVID‑19 restrictions on work sites impacting overall program. The project’s cashflow has been revised in line with a revised project schedule.
Dingley Bypass between Warrigal Road to Westall Road (Dingley) | Dingley Bypass between Warrigal Road to Westall Road | Existing | 155700000 | 0 | 0 | 41103000 | 82002000 | qtr 1 2016‑17 | 2014–15 | 2016-09-30 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Dingley | Metropolitan |  |  | GG | Transport
Dingley Bypass between Warrigal Road to Westall Road (Dingley) | Dingley Bypass between Warrigal Road to Westall Road | Existing | 155700000 | 0 | 0 | 83659000 | 26139000 | qtr 1 2016‑17 | 2015–16 | 2016-09-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Dingley | Metropolitan |  |  | GG | Transport
Echuca-Moama bridge (Echuca) | Rural and Regional Roads Package – Echuca‑Moama bridge | Existing | 134903000 | 0 | 0 | 7692000 | 74423000 | qtr 4 2021-22 | 2017–18 | 2022-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Echuca | Regional |  |  | GG | Transport | TEI includes $46.000 million of Commonwealth funding and excludes contribution from New South Wales.
Echuca-Moama bridge (Echuca) | Rural and Regional Roads Package – Echuca‑Moama bridge | Existing | 134903000 | 0 | 0 | 13975000 | 96542000 | qtr 4 2021-22 | 2018–19 | 2022-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Echuca | Regional | Rural and Regional Roads Package |  | GG | Transport | TEI includes $46.000 million of Commonwealth funding and excludes contribution from New South Wales.
Echuca‑Moama bridge (Echuca) | Rural and Regional Roads Package – Echuca‑Moama bridge | Existing | 134903000 | 0 | 0 | 33414000 | 69354000 | qtr 4 2021‑22 | 2019–20 | 2022-06-30 | Department of Transport | Department of Transport | Echuca | Regional | Rural and Regional Roads Package |  | GG | Transport | TEI includes $46.000 million of Commonwealth funding and excludes contribution from New South Wales.
Rural and Regional Roads Package – Echuca‑Moama bridge (Echuca) | Rural and Regional Roads Package – Echuca‑Moama bridge | Existing | 173254000 | 0.28429 | 38351000 | 126645000 | 23892000 | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Transport | Department of Transport | Echuca | Regional | Rural and Regional Roads Package |  | GG | Transport | TEI has increased by $38.351 million due to market escalation and includes $74.674 million of Commonwealth funding. TEI excludes $5.360 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards, and excludes funding contributions from New South Wales and the Commonwealth portion for New South Wales.
Great Ocean Road renewal (regional various) | Great Ocean Road renewal | Existing | 255000000 | 0 | 0 | 15000000 | 190000000 | qtr 4 2024‑25 | 2021–22 | 2025-06-30 | Department of Transport | Department of Transport | Regional various | Regional |  |  | GG | Transport | Initiative funded in the 2020‑21 Budget.
Princes Highway East Duplication Stage 3 (regional various) | Princes Highway East Duplication Stage 3 | Existing | 236433000 | 0 | 0 | 10035000 | 152177000 | qtr 4 2023‑24 | 2021–22 | 2024-06-30 | Department of Transport | Department of Transport | Regional various | Regional |  |  | GG | Transport | TEI excludes $16.867 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Regional Rail Sustainability (regional various) | Regional Rail Sustainability Regional | Completed | 105600000 | 0 | 0 | 97300000 |  | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional |  |  | PNFC | Transport | Initiative funded in the 2020‑21 Budget.
Water efficiency project (regional various) | Water efficiency project | Existing | 1231458000 | 0 | 0 | 1138713000 | 55556000 | qtr 4 2023‑24 | 2021–22 | 2024-06-30 | Goulburn Murray Rural Water Corporation | Goulburn Murray Rural Water Corporation | Regional various | Regional |  |  | PNFC | Water | Project was previously named ‘Connections project (regional various)’ in the 2019‑20 Budget but has since had its name changed to reflect a new project strategy.
Regional Rail Revival – Warrnambool and Geelong Line Upgrade (regional various) | Regional Rail Revival – Warrnambool and Geelong Line Upgrade | Existing | 250189000 | 0 | 0 | 218326000 |  | qtr 2 2021‑22 | 2021–22 | 2021-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional | Regional Rail Revival |  | PNFC | Transport | TEI has increased by $137.800 million due to scope variations and market conditions. TEI includes $226.345 million of Commonwealth funding and excludes $1.611 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.
Regional Rail Revival – Waurn Ponds Track Duplication – Stage 2 (regional various) | Regional Rail Revival – Waurn Ponds Track Duplication – Stage 2 | Existing | 899200000 | 0 | 0 | 31691000 | 823639000 | qtr 2 2024‑25 | 2021–22 | 2024-12-31 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Regional various | Regional | Regional Rail Revival |  | PNFC | Transport
Heidelberg redevelopment – 600 units/ sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0 | 0 | 12386000 | 128614000 | qtr 4 2021‑22 | 2014–15 | 2022-06-30 | Director of Housing | Director of Housing | Heidelberg | Metropolitan |  |  | PNFC | Health and human services
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0 | 0 | 100589000 | 59411000 | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Director of Housing | Director of Housing | Heidelberg | Metropolitan |  |  | PNFC | Health and human services
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0 | 0 | 30608000 | 115683000 | qtr 4 2022‑23 | 2015–16 | 2023-06-30 | Director of Housing | Director of Housing | Heidelberg | Metropolitan |  |  | PNFC | Health and human services
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0 | 0 | 75625000 | 68375000 | qtr 4 2022-23 | 2018–19 | 2023-06-30 | Director of Housing | Director of Housing | Heidelberg | Metropolitan |  |  | PNFC | Health and human services
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0 | 0 | 86974000 | 51972000 | qtr 4 2022‑23 | 2019–20 | 2023-06-30 | Director of Housing | Director of Housing | Heidelberg | Metropolitan |  |  | PNFC | Health and human services | The project’s cashflow has been revised due to town planning permit issues and inclement weather conditions. The project’s TEI remains unchanged.
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0 | 0 | 49219000 | 94781000 | qtr 4 2022‑23 | 2016–17 | 2023-06-30 | Director of Housing | Director of Housing | Heidelberg | Metropolitan |  |  | PNFC | Health and human services
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0 | 0 | 63214000 | 76204000 | qtr 4 2022-23 | 2017–18 | 2023-06-30 | Director of Housing | Director of Housing | Heidelberg | Metropolitan |  |  | PNFC | Health and human services
Latrobe Regional Hospital redevelopment – Stage 3A (Traralgon) | Latrobe Regional Hospital redevelopment – Stage 3A | Existing | 217000000 | 0 | 0 | 8608000 | 156392000 | qtr 4 2023‑24 | 2021–22 | 2024-06-30 | Department of Health | Department of Health | Traralgon | Regional |  |  | GG | Health and human services | Initiative funded in the 2020‑21 budget. The project’s cashflow has been revised in line with a revised project schedule.
Modernisation of metropolitan Melbourne Public Sector Residential Aged Care Services Strategy: Stage 3 Kingston Project (Cheltenham) | Modernisation of metropolitan Melbourne Public Sector Residential Aged Care Services Strategy: Stage 3 Kingston Project | Existing | 134630000 | 0 | 0 | 103000 | 130227000 | qtr 4 2025‑26 | 2021–22 | 2026-06-30 | Department of Health | Department of Health | Cheltenham | Metropolitan |  |  | GG | Health and human services | Initiative funded in the 2020‑21 Budget.
Port of Hastings development (Hastings) | Port of Hastings development | Existing | 110000000 | 0 | 0 | 20000000 | 60000000 | qtr 4 2016‑17 | 2014–15 | 2017-06-30 | Port of Hastings Development Authority | Port of Hastings Development Authority | Hastings | Regional |  |  | PNFC | Transport
Port of Hastings development (Hastings) | Port of Hastings development | Discontinued | 0 | -1 | -110000000 | 0 | 0 | Discontinued | 2015–16 |  | Port of Hastings Development Authority | Port of Hastings Development Authority | Hastings | Regional |  |  | PNFC | Transport | Relevant remaining components of the project have been transferred from capital to output funding.
Warrnambool Base Hospital Redevelopment (incl Warrnambool Logistics Hub) (Warrnambool) | Warrnambool Base Hospital Redevelopment | Existing | 384200000 | 0 | 0 | 3300000 | 357200000 | qtr 4 2025‑26 | 2021–22 | 2026-06-30 | Department of Health | Department of Health | Warrnambool | Regional |  |  | GG | Health and human services | Initiative funded in the 2020‑21 Budget.
Chandler Highway Bridge duplication (Alphington/Kew) | Chandler Highway upgrade | New | 110000000 | 0 | 0 | 0 | 107850000 | qtr 2 2018‑19 | 2015–16 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Alphington, Kew | Metropolitan | Better Roads – Metropolitan (including outer metropolitan) |  | GG | Transport
Chandler Highway upgrade (Alphington, Kew) | Chandler Highway upgrade | Existing | 100015000 | 0 | 0 | 91801000 | 529000 | qtr 1 2019‑20 | 2019–20 | 2019-09-30 | Department of Transport | Department of Transport | Alphington, Kew | Metropolitan |  |  | GG | Transport | The estimated completion date has been revised to quarter 1 2019‑20 due to unexpected asbestos.
Chandler Highway upgrade (Alphington, Kew) | Chandler Highway upgrade | Existing | 110000000 | 0 | 0 | 4020000 | 90779000 | qtr 2 2018‑19 | 2016–17 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Alphington, Kew | Metropolitan |  |  | GG | Transport
Chandler Highway upgrade (Alphington, Kew) | Chandler Highway upgrade | Completed | 125415000 | 0.25396 | 25400000 | 123379000 |  | qtr 3 2021‑22 | 2021–22 | 2022-03-31 | Department of Transport | Department of Transport | Alphington, Kew | Metropolitan |  |  | GG | Transport | TEI has increased by $25.400 million due to unexpected asbestos contaminated materials.
Chandler Highway upgrade (Alphington, Kew) | Chandler Highway upgrade | Existing | 100015000 | -0.088461 | -9706000 | 59264000 | 8215000 | qtr 2 2018-19 | 2018–19 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Alphington, Kew | Metropolitan |  |  | GG | Transport | TEI has decreased with $9.706 million identified project savings.
Chandler Highway upgrade (Alphington, Kew) | Chandler Highway upgrade | Existing | 109721000 | -0.0025364 | -279000 | 19331000 | 51039000 | qtr 2 2018-19 | 2017–18 | 2018-12-31 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Alphington, Kew | Metropolitan |  |  | GG | Transport | TEI excludes corporate costs.
Plenty Road Upgrade (Mill Park) | Plenty Road upgrade – Stage 2 | New | 139410000 | 0 | 0 | 0 | 0 | tbc | 2016–17 | 2089-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Mill Park | Metropolitan | Outer suburban arterial roads package: |  | GG | Transport
Plenty Road upgrade – Stage 2 (South Morang) | Plenty Road upgrade – Stage 2 | Existing | 114209000 | -0.18077 | -25201000 | 0 | 84479000 | qtr 4 2019-20 | 2017–18 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | South Morang | Metropolitan |  |  | GG | Transport
Plenty Road upgrade – Stage 2 (South Morang) | Plenty Road upgrade – Stage 2 | Existing | 143409000 | 0.38681 | 40000000 | 11297000 | 95388000 | qtr 2 2020‑21 | 2019–20 | 2020-12-31 | Department of Transport | Department of Transport | South Morang | Metropolitan |  |  | GG | Transport | TEI has increased by $40.000 million due to market escalation. The estimated completion date has been revised to quarter 2 2020‑21 due to procurement requirements.
Plenty Road upgrade – Stage 2 (South Morang) | Plenty Road upgrade – Stage 2 | Completed | 144188000 | 0.005432 | 779000 | 126036000 |  | qtr 4 2022‑23 | 2021–22 | 2023-06-30 | Department of Transport | Department of Transport | South Morang | Metropolitan |  |  | GG | Transport | TEI has increased by $0.779 million due to increased scope funded by a developer contribution.
Plenty Road upgrade – Stage 2 (South Morang) | Plenty Road upgrade – Stage 2 | Existing | 103409000 | -0.094563 | -10800000 | 9030000 | 37869000 | qtr 4 2019-20 | 2018–19 | 2020-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | South Morang | Metropolitan |  |  | GG | Transport | TEI reflects allocation of $10.004 million from Plenty Road upgrade – Stage 2 towards Plenty Road upgrade – Stage 1 and an identified project savings of $0.800 million.
Rural and Regional Roads Package – Improving the South Gippsland Highway (Gippsland region) | Rural and Regional Roads Package – Improving the South Gippsland Highway | Existing | 110474000 | 0 | 0 | 55278000 | 17541000 | qtr 4 2021‑22 | 2021–22 | 2022-06-30 | Department of Transport | Department of Transport | Gippsland Region | Regional | Rural and Regional Roads Package |  | GG | Transport | TEI has increased by $62.394 million due to market escalation and includes $56.590 million of Commonwealth funding. TEI excludes $2.706 million due to certain expenditure being reclassified as operating instead of capital in line with accounting standards.

## Discont. & Completed Projects
VAGO name | Status | Budget year_discontinuedCompleted
40 New trains for Melbourne commuters – stage 1 | Completed | 2016–17
Building confidence in corrections – Construction/asset enhancement | Completed | 2016–17
Improving hospital services – sub‑acute | Completed | 2015–16
Melbourne Rail Link | Discontinued | 2015–16
Melbourne Wholesale Markets redevelopment | Completed | 2016–17
New stations in growth areas | Completed | 2016–17
New trains for Melbourne commuters | Completed | 2016–17
Port Capacity Expansion project | Discontinued | 2017–18
Port of Hastings development | Discontinued | 2015–16
Princes Highway West – stage 1 Waurn Ponds to Winchelsea | Completed | 2015–16
Regional Rail Link | Completed | 2015–16
Regional rail network major periodic maintenance (passenger and freight) | Completed | 2016–17
Regional rolling stock – new tranche | Completed | 2017–18
State Coronial Services redevelopment | Completed | 2016–17
Regional rolling stock | Completed | 2015–16
Targeted Road restoration | Completed | 2016–17
Cranbourne‑Pakenham rail corridor project | Discontinued | 2015–16
Box Hill Hospital – Redevelopment | Completed | 2017–18
Dingley Bypass between Warrigal Road to Westall Road | Completed | 2016–17
East West Link – Eastern section | Discontinued | 2015–16
East West Link – Western section | Discontinued | 2015–16
M80 Upgrade | Completed | 2015–16
Major periodic maintenance | Completed | 2017–18
Metropolitan rolling stock | Completed | 2016–17