## VAGO BP4 data set
Project | VAGO name | Project_type_VAGO | TEI_VAGO | TEI_Change_Per | TEI_Change_$ | Est exp to date_VAGO | Remaining exp_VAGO | Est completion date | Budget Year | BudgetYear_VAGO | Completion_date_VAGO | Agency | VAGO Agency | Location | Project Location | VAGO Location | Program | VAGO Program Name | Notes | Project type | Sector | Vago Sector | Fixed Notes
Additional VLocity trains (regional various) | Additional VLocity trains | New | 340000000 | 0% | 0 | 0 | 161600000 | tbc | 2019–20 | 1/07/2019 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | 0 | New | PNFC | Transport | N/A
Additional X’Trapolis Metropolitan Trains (metropolitan various) | Additional X’Trapolis Metropolitan Trains | New | 103501000 | 0% | 0 | 28079000 | 26522000 | qtr22019-20 | 2018–19 | 1/07/2018 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | New | PNFC | Transport | N/A
Ballarat Base Hospital expansion and redevelopment (Ballarat) | Ballarat Health Services expansion and redevelopment | New | 461600000 | 0% | 0 | 0 | 460800000 | qtr42025-26 | 2018–19 | 1/07/2018 | 2026-04-01 | Department of Health and Human Services | Department of Health | Ballarat | Ballarat | Regional | 0 | 0 | 0 | New | GG | Health and human services | N/A
Barwon Heads Road upgrade (Barwon Heads) | Barwon Heads Road upgrade | New | 318300000 | 0% | 0 | 0 | 317900000 | tbc | 2019–20 | 1/07/2019 | 2089-06-30 | Department of Transport | Department of Transport | Barwon Heads | Barwon Heads | Regional | 0 | 0 | 0 | New | GG | Transport | N/A
Bendigo Law Courts Redevelopment (Bendigo) | Bendigo Law Courts Redevelopment | New | 152396000 | 0% | 0 | 0 | 132496000 | qtr12022‑23 | 2019–20 | 1/07/2019 | 2022-07-01 | Court Services Victoria | Court Services Victoria | Bendigo | Bendigo | Regional | 0 | 0 | 0 | New | GG | Justice and emergency services | N/A
Building a better hospital for Melbourne’s inner west (Footscray) | Building a better hospital for Melbourne’s inner west | New | 1495000000 | 0% | 0 | 0 | 0 | qtr42024‑25 | 2019–20 | 1/07/2019 | 2025-04-01 | Department of Health and Human Services | Department of Health | Footscray | Footscray | Metropolitan | 0 | 0 | Cash flows to be confirmed. TEI includes $65 million provided in previous budgets and excludes financing costs. | New | GG | Health and human services | Cash flows to be confirmed. TEI includes $65 million provided in previous budgets and excludes financing costs.
Building a world‑class Geelong Performing Arts Centre (Geelong) | Building a world‑class Geelong Performing Arts Centre | New | 128000000 | 0% | 0 | 0 | 112480000 | qtr42022‑23 | 2019–20 | 1/07/2019 | 2023-04-01 | Other public non-financial corporations | Development Victoria | Geelong | Geelong | Regional | 0 | 0 | 0 | New | PNFC | Culture, sport and community | N/A
Building new homes to fight homelessness (statewide) | Building new homes to fight homelessness | New | 209099000 | 0% | 0 | 0 | 175639000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Director of Housing | Department of Families, Fairness and Housing | statewide | Statewide | Statewide | 0 | 0 | 0 | New | PNFC | Health and human services | N/A
Car Parks for Commuters (statewide) | Car Parks for Commuters | New | 150000000 | 0% | 0 | 0 | 137500000 | qtr42022‑23 | 2019–20 | 1/07/2019 | 2023-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | statewide | Statewide | Statewide | 0 | 0 | 0 | New | PNFC | Transport | N/A
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | New | 106300000 | 0% | 0 | 0 | 105900000 | qtr42019‑20 | 2015–16 | 1/07/2015 | 2020-04-01 | Department of Health and Human Services | Department of Health | Berwick | Berwick | Metropolitan | 0 | 0 | The TEI includes funding held in contingency pending completion of business planning and development. | New | GG | Health and human services | The TEI includes funding held in contingency pending completion of business planning and development.
Chisholm Road prison project (Chisholm Road) | Chisholm Road prison project | New | 689450000 | 0% | 0 | 36199000 | 400215000 | qtr42021‑22 | 2019–20 | 1/07/2019 | 2022-04-01 | Department of Justice and Community Safety | Department of Justice and Community Safety | Chisholm Road | Chisholm Road | Regional | 0 | 0 | Previously known as Lara Prison precinct expansion published in 2018‑19 budget papers. Cash flow has been revised in line with a revised project schedule. | Existing | GG | Justice and emergency services | Previously known as Lara Prison precinct expansion published in 2018‑19 budget papers. Cash flow has been revised in line with a revised project schedule.
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | City Loop fire and safety (upgrade stage 2) and intruder alarm | New | 132863000 | 0% | 0 | 0 | 128460000 | qtr42019‑20 | 2016–17 | 1/07/2016 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Melbourne | Metropolitan | 0 | 0 | 0 | New | PNFC | Transport | N/A
CityLink-Tulla widening project – Tullamarine Freeway widening (Tullamarine) | CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport | New | 272800000 | 0% | 0 | 27400000 | 199800000 | qtr22018‑19 | 2015–16 | 1/07/2015 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Tullamarine | Tullamarine | Metropolitan | 0 | 0 | State Government contribution (including anticipated Commonwealth Government funding of $200 million) to widen the Tullamarine Freeway between Bulla Road and Melbourne Airport. This project is part of the broader $1.3 billion CityLink-Tulla widening project funded by Transurban in conjunction with the State and Commonwealth Governments. | Existing | GG | Transport | State Government contribution (including anticipated Commonwealth Government funding of $200 million) to widen the Tullamarine Freeway between Bulla Road and Melbourne Airport. This project is part of the broader $1.3 billion CityLink-Tulla widening project funded by Transurban in conjunction with the State and Commonwealth Governments.
Community Safety Statement (statewide) | Community Safety Statement | New | 390564000 | 0% | 0 | 0 | 283880000 | various | 2017–18 | 1/07/2017 | 2089-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | The TEI includes $6.300 million of funding redirected from the Public Safety – Police Response initiative for the purchase of land for the Specialist Training Facility. | New | GG | Justice and emergency services | The TEI includes $6.300 million of funding redirected from the Public Safety – Police Response initiative for the purchase of land for the Specialist Training Facility.
Continuing Towards Zero (regional various) | Continuing Towards Zero | New | 149200000 | 0% | 0 | 0 | 118000000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | regional various | Regional | Regional | 0 | 0 | 0 | New | GG | Transport | N/A
Conventional signalling upgrade – Caulfield to Dandenong (metro various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | New | 360000000 | 0% | 0 | 0 | 315000000 | qtr22018‑19 | 2015–16 | 1/07/2015 | 2018-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | New | PNFC | Transport | N/A
Corrections system expansion (statewide) | Corrections system expansion | New | 140760000 | 0% | 0 | 19460000 | 73950000 | qtr42016‑17 | 2014–15 | 1/07/2014 | 2017-04-01 | Department of Justice | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | Includes previously approved funding of $19.460 million. | New | GG | Justice and emergency services | Includes previously approved funding of $19.460 million.
Cranbourne Line Duplication planning and development (metropolitan various) | Cranbourne Line Duplication planning and development | New | 750000000 | 0% | 0 | 0 | 737800000 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | New | PNFC | Transport | N/A
Cranbourne Pakenham and Sunbury Line upgrades (metropolitan various) | Cranbourne Pakenham and Sunbury Line Upgrades | New | 539540000 | 0% | 0 | 113104000 | 51368000 | qtr22019-20 | 2018–19 | 1/07/2018 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | New | PNFC | Transport | N/A
Cranbourne‑Pakenham rail corridor project (metro various) | Cranbourne‑Pakenham rail corridor project | New | 2500000000 | 0% | 0 | 5000000 | 2475000000 | 2018‑19 | 2014–15 | 1/07/2014 | 2018-07-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | New | GG | Transport | N/A
Drysdale bypass (Drysdale) | Drysdale bypass | New | 102560000 | 0% | 0 | 0 | 98140000 | qtr42019‑20 | 2016–17 | 1/07/2016 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Drysdale | Drysdale | Regional | 0 | 0 | Balance of election commitment was delivered in the 2015‑16 Budget. | New | GG | Transport | Balance of election commitment was delivered in the 2015‑16 Budget.
East West Link – Western section (metro) | East West Link – Western section | New | 10000000000 | 0% | 0 | 4000000 | 9896000000 | 2022‑23 | 2014–15 | 1/07/2014 | 2022-07-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | metro | Metropolitan | Metropolitan | 0 | 0 | The TEI includes Commonwealth funding of $1.500 billion. The capital cost of this project is estimated to be between $8 billion and $10 billion. | New | GG | Transport | The TEI includes Commonwealth funding of $1.500 billion. The capital cost of this project is estimated to be between $8 billion and $10 billion.
Echuca-Moama bridge (Echuca) | Echuca-Moama bridge | New | 134903000 | 0% | 0 | 7692000 | 74423000 | qtr42021-22 | 2017–18 | 1/07/2017 | 2022-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Echuca | Echuca | Regional | 0 | 0 | TEI includes $46.000 million of Commonwealth funding and excludes contribution from New South Wales. | Existing | GG | Transport | TEI includes $46.000 million of Commonwealth funding and excludes contribution from New South Wales.
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | New | 100000000 | 0% | 0 | 1000000 | 76600000 | qtr42018‑19 | 2015–16 | 1/07/2015 | 2019-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Melbourne | Metropolitan | 0 | 0 | The TEI includes funding announced in Getting On With It. | New | PNFC | Transport | The TEI includes funding announced in Getting On With It.
Frankston Line stabling (Seaford) | Frankston Line stabling | New | 187400000 | 0% | 0 | 0 | 116600000 | tbc | 2017–18 | 1/07/2017 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Seaford | Seaford | Metropolitan | 0 | 0 | 0 | New | PNFC | Transport | N/A
Geelong City Deal (Geelong) | Geelong City Deal | New | 139216000 | 0% | 0 | 0 | 128423000 | qtr22022-23 | 2018–19 | 1/07/2018 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Jobs, Precincts and Regions | Geelong | Geelong | Regional | 0 | 0 | This is the Victorian Government’s share of the Geelong City Deal. This initiative is listed as a whole of government initiative in Budget Paper No. 3. | New | GG | Culture, sport and community | This is the Victorian Government’s share of the Geelong City Deal. This initiative is listed as a whole of government initiative in Budget Paper No. 3.
Geelong Hospital – major upgrade (Geelong) | Geelong Hospital – major upgrade | New | 118170000 | 0% | 0 | 69465000 | 5493000 | qtr22015‑16 | 2015–16 | 1/07/2015 | 2015-10-01 | Department of Health and Human Services | Department of Health | Geelong | Geelong | Regional | 0 | 0 | The TEI of this initiative has changed to reflect additional improvements at Geelong Hospital including relocation of the current helipad to the rooftop of the acute services tower block. | Existing | GG | Health and human services | The TEI of this initiative has changed to reflect additional improvements at Geelong Hospital including relocation of the current helipad to the rooftop of the acute services tower block.
Goulburn Valley Health redevelopment (Shepparton) | Goulburn Valley Health redevelopment – planning and development | New | 168525000 | 0% | 0 | 0 | 163525000 | qtr42020‑21 | 2016–17 | 1/07/2016 | 2021-04-01 | Department of Health and Human Services | Department of Health | Shepparton | Shepparton | Regional | 0 | 0 | Additional funding of $1.000 million was provided in 2015‑16 for planning and development, bringing the Government’s contribution to $169.525 million. | New | GG | Health and human services | Additional funding of $1.000 million was provided in 2015‑16 for planning and development, bringing the Government’s contribution to $169.525 million.
Hall Road Upgrade (Skye) | Hall Road Upgrade | New | 169000000 | 0% | 0 | 0 | 168600000 | tbc | 2019–20 | 1/07/2019 | 2089-06-30 | Department of Transport | Department of Transport | Skye | Skye | Metropolitan | 0 | 0 | 0 | New | GG | Transport | N/A
Hurstbridge Line Upgrade Stage 2 (metropolitan various) | Hurstbridge Line Upgrade Stage 2 | New | 530000000 | 0% | 0 | 0 | 508500000 | tbc | 2019–20 | 1/07/2019 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The completion date is subject to the completion of planning for the project. | New | PNFC | Transport | The completion date is subject to the completion of planning for the project.
Hurstbridge Corridor Upgrade (non‑metro various) | Hurstbridge rail line upgrade | New | 135905000 | 0% | 0 | 1000000 | 127930000 | qtr42018‑19 | 2016–17 | 1/07/2016 | 2019-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | 0 | 0 | New | PNFC | Transport | N/A
Western Women’s and Children’s Hospital (St Albans) | Joan Kirner Women’s and Children’s Hospital | New | 200000000 | 0% | 0 | 0 | 185270000 | qtr42019‑20 | 2015–16 | 1/07/2015 | 2020-04-01 | Department of Health and Human Services | Department of Health | St Albans | St Albans | Metropolitan | 0 | 0 | 0 | New | GG | Health and human services | N/A
Lara Prison precinct expansion (Bacchus Marsh) | Lara Prison precinct expansion | New | 689450000 | 0% | 0 | 10373000 | 623728000 | qtr42021-22 | 2018–19 | 1/07/2018 | 2022-04-01 | Department of Justice and Regulation | Department of Justice and Community Safety | Bacchus Marsh | Bacchus Marsh | Regional | 0 | 0 | 0 | New | GG | Justice and emergency services | N/A
M80 Ring Road upgrade (north and west metropolitan region) | M80 Ring Road upgrade | New | 673077000 | 0% | 0 | 0 | 639423000 | qtr32020-21 | 2017–18 | 1/07/2017 | 2021-01-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | north and west metropolitan region | Metropolitan | Metropolitan | 0 | 0 | TEI includes $336.538 million of Commonwealth funding for the capital component of this initiative. | New | GG | Transport | TEI includes $336.538 million of Commonwealth funding for the capital component of this initiative.
M80 Upgrade – EJ Whitten Bridge to Sunshine Avenue (Sunshine North) | M80 Upgrade – EJ Whitten Bridge to Sunshine Avenue | New | 150000000 | 0% | 0 | 0 | 110000000 | qtr42017‑18 | 2015–16 | 1/07/2015 | 2018-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Sunshine North | Sunshine North | Metropolitan | 0 | 0 | 0 | New | GG | Transport | N/A
M80 upgrade – Sunshine Avenue to Calder Fwy (Sunshine North) | M80 Ring Road upgrade Sunshine Avenue to Calder Freeway | New | 300000000 | 0% | 0 | 3015000 | 171600000 | qtr22018‑19 | 2016–17 | 1/07/2016 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Sunshine North | Sunshine North | Metropolitan | 0 | 0 | TEI includes $150 million of Commonwealth funding. | Existing | GG | Transport | TEI includes $150 million of Commonwealth funding.
Major periodic maintenance on the regional rail network (regional various) | Major periodic maintenance on the regional rail network | New | 287913000 | 0% | 0 | 0 | 184533000 | qtr42020-21 | 2017–18 | 1/07/2017 | 2021-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | 0 | New | PNFC | Transport | N/A
Melbourne Airport Rail | Melbourne Airport Rail | New | 680680000 | 0% | 0 | 10000000 | 620680000 | tbc | 2019–20 | 1/07/2019 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Unspecified | Unspecified | Unspecified | 0 | 0 | This funding represents the Commonwealth contribution to the project. The Government has made a substantial provision in the Victorian Transport Fund for this project. The project is in its planning phase. | New | PNFC | Transport | This funding represents the Commonwealth contribution to the project. The Government has made a substantial provision in the Victorian Transport Fund for this project. The project is in its planning phase.
Melbourne Arts Precinct transformation (Melbourne) | Melbourne Arts Precinct transformation | New | 101500000 | 0% | 0 | 26738000 | 2000000 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Department of Jobs, Precincts and Regions | Department of Jobs, Precincts and Regions | Melbourne | Melbourne | Metropolitan | 0 | 0 | This project incorporates the Reimagining Arts Centre Melbourne project and the National Gallery of Victoria Contemporary initiative. This project also incorporates the previously published Arts Centre Melbourne critical works project. | Existing | GG | Culture, sport and community | This project incorporates the Reimagining Arts Centre Melbourne project and the National Gallery of Victoria Contemporary initiative. This project also incorporates the previously published Arts Centre Melbourne critical works project.
Melbourne Exhibition Centre – stage 2 development (Southbank) | Melbourne Exhibition Centre Stage 2 Development | New | 168700000 | 0% | 0 | 71000000 | 0 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Jobs, Precincts and Regions | Southbank | Southbank | Metropolitan | 0 | 0 | TEI reflects State capital construction component only. | Existing | GG | Culture, sport and community | TEI reflects State capital construction component only.
Melbourne Park Redevelopment – stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | New | 366141000 | 0% | 0 | 5060000 | 330282000 | qtr42019‑20 | 2014–15 | 1/07/2014 | 2020-04-01 | Other public non‑financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Melbourne | Metropolitan | 0 | 0 | TEI includes anticipated Commonwealth funding of $27.99 million and a contribution of $40.00 million from the Melbourne and Olympic Parks Trust. | New | PNFC | Culture, sport and community | TEI includes anticipated Commonwealth funding of $27.99 million and a contribution of $40.00 million from the Melbourne and Olympic Parks Trust.
Melbourne Park Redevelopment – Stage 3 (Melbourne) | Melbourne Park Redevelopment – stage 3 | New | 271555000 | 0% | 0 | 0 | 253450000 | qtr42020-21 | 2017–18 | 1/07/2017 | 2021-04-01 | Department of Health and Human Services | Department of Jobs, Precincts and Regions | Melbourne | Melbourne | Metropolitan | 0 | 0 | The TEI includes funding of $40.000 million from the Melbourne and Olympic Parks Trust. | New | GG | Culture, sport and community | The TEI includes funding of $40.000 million from the Melbourne and Olympic Parks Trust.
Melbourne Rail Link (metro various) | Melbourne Rail Link | New | 11000000000 | 0% | 0 | 0 | 10960000000 | from2023‑24 | 2014–15 | 1/07/2014 | 2023-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | Includes the remaining funding from the Melbourne Metro Rail Tunnel. | New | PNFC | Transport | Includes the remaining funding from the Melbourne Metro Rail Tunnel.
Men’s prison system capacity (statewide) | Men’s prison system capacity | New | 1255372000 | 0% | 0 | 37000000 | 728918000 | qtr42022‑23 | 2019–20 | 1/07/2019 | 2023-04-01 | Department of Justice and Community Safety | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | 0 | New | GG | Justice and emergency services | N/A
Mernda rail extension project (Mernda) | Mernda rail extension project | New | 587714000 | 0% | 0 | 12466000 | 475448000 | qtr22018‑19 | 2016–17 | 1/07/2016 | 2018-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Mernda | Mernda | Metropolitan | 0 | 0 | $9.000 million in development funding was provided in the 2015‑16 Budget. | New | PNFC | Transport | $9.000 million in development funding was provided in the 2015‑16 Budget.
Metro Level Crossing Blitz program (metro various) | Metro Level Crossing Blitz program | New | 68810000 | 0% | 0 | 42336000 | 1527000 | qtr42016‑17 | 2015–16 | 1/07/2015 | 2017-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | GG | Transport | N/A
Melbourne Metro Rail Project (metro various) | Metro Tunnel | New | 11000000000 | 0% | 0 | 40000000 | 10837600000 | 2026 | 2015–16 | 1/07/2015 | 2026-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | The TEI includes funding announced in Getting On With It. | New | PNFC | Transport | The TEI includes funding announced in Getting On With It.
Metropolitan and regional restoration and maintenance (statewide) | Metropolitan and regional restoration and maintenance | New | 195200000 | 0% | 0 | 0 | 87200000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | TEI consolidates both the metropolitan and regional components. Budget Paper No. 3 reports these components separately. | New | GG | Transport | TEI consolidates both the metropolitan and regional components. Budget Paper No. 3 reports these components separately.
Monash Freeway upgrade – Stage 2 (South-East Melbourne) | Monash Freeway upgrade – Stage 2 | New | 684424000 | 0% | 0 | 1442000 | 665582000 | qtr42022-23 | 2018–19 | 1/07/2018 | 2023-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | South-East Melbourne | South-East Melbourne | Metropolitan | 0 | 0 | TEI includes Commonwealth funding of $483.800 million for the capital component of this initiative. | New | GG | Transport | TEI includes Commonwealth funding of $483.800 million for the capital component of this initiative.
Mordialloc Bypass (Braeside) | Mordialloc Freeway | New | 300000000 | 0% | 0 | 0 | 296700000 | qtr42022-23 | 2017–18 | 1/07/2017 | 2023-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Braeside | Braeside | Metropolitan | 0 | 0 | 0 | New | GG | Transport | N/A
More E-Class trams and infrastructure (metropolitan various) | More E-Class trams and infrastructure | New | 215462000 | 0% | 0 | 0 | 187292000 | qtr32018-19 | 2017–18 | 1/07/2017 | 2019-01-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | New | PNFC | Transport | N/A
More regional trains (regional various) | More regional trains – Regional Network Development Plan | New | 287885000 | 0% | 0 | 3630000 | 247171000 | qtr32018-19 | 2017–18 | 1/07/2017 | 2019-01-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | 0 | New | PNFC | Transport | N/A
New E‑Class trams (metro various) | New E‑Class trams | New | 294770000 | 0% | 0 | 0 | 257470000 | qtr22018‑19 | 2015–16 | 1/07/2015 | 2018-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | New | PNFC | Transport | N/A
New Trams (metropolitan various) | New Trams | New | 144720000 | 0% | 0 | 0 | 76200000 | tbc | 2019–20 | 1/07/2019 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | New | PNFC | Transport | N/A
New VLocity carriages for the regional network (non‑metro various) | New VLocity carriages for the regional network | New | 257078000 | 0% | 0 | 0 | 169682000 | qtr12018‑19 | 2015–16 | 1/07/2015 | 2018-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | 0 | 0 | New | PNFC | Transport | N/A
New trains for Sunbury (metropolitan various) | New trains for Sunbury | New | 2050365000 | 0% | 0 | 0 | 1848299000 | qtr22024‑25 | 2019–20 | 1/07/2019 | 2024-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | New | PNFC | Transport | N/A
New youth justice facility (Werribee) | New youth justice facility | New | 288700000 | 0% | 0 | 1000000 | 260700000 | qtr42020-21 | 2017–18 | 1/07/2017 | 2021-04-01 | Department of Justice and Regulation | Department of Justice and Community Safety | Werribee | Werribee | Metropolitan | 0 | 0 | 0 | New | GG | Justice and emergency services | N/A
Northern Hospital inpatient expansion – Stage 2 (Epping) | Northern Hospital inpatient expansion – Stage 2 | New | 162672000 | 0% | 0 | 0 | 156000000 | qtr42020-21 | 2017–18 | 1/07/2017 | 2021-04-01 | Department of Health and Human Services | Department of Health | Epping | Epping | Metropolitan | 0 | 0 | 0 | New | GG | Health and human services | N/A
O'Herns Road upgrade (Epping) | O’Herns Road upgrade | New | 77750000 | 0% | 0 | 0 | 70350000 | qtr42018‑19 | 2016–17 | 1/07/2016 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Epping | Epping | Metropolitan | 0 | 0 | The TEI represents total value of the project and is subject to matching Commonwealth Government funding. | New | GG | Transport | The TEI represents total value of the project and is subject to matching Commonwealth Government funding.
Princes Highway duplication project – Winchelsea to Colac (non‑metro various) | Princes Highway duplication project – Winchelsea to Colac | New | 349490000 | 0% | 0 | 0 | 304770000 | qtr42018‑19 | 2014–15 | 1/07/2014 | 2019-04-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | non‑metro various | Regional | Regional | 0 | 0 | The TEI includes anticipated Commonwealth funding of $167.755 million. The TEI does not include planning funding of $12.000 million, of which $7.000 million was Commonwealth funding. | New | GG | Transport | The TEI includes anticipated Commonwealth funding of $167.755 million. The TEI does not include planning funding of $12.000 million, of which $7.000 million was Commonwealth funding.
Public Safety – Police Response (statewide) | Public Safety – Police Response | New | 149066000 | 0% | 0 | 0 | 90837000 | qtr42020‑21 | 2016–17 | 1/07/2016 | 2021-04-01 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | 0 | New | GG | Justice and emergency services | N/A
Public housing renewal program (statewide) | Public housing renewal program | New | 185000000 | 0% | 0 | 5000000 | 120000000 | ongoing | 2017–18 | 1/07/2017 | 2099-06-30 | Director of Housing | Department of Families, Fairness and Housing | statewide | Statewide | Statewide | 0 | 0 | The final budget and cashflow will be available following execution of a project development agreement with the private sector. This is anticipated to be executed by March 2018. | New | PNFC | Health and human services | The final budget and cashflow will be available following execution of a project development agreement with the private sector. This is anticipated to be executed by March 2018.
Regional Rail Revival – Gippsland Rail Upgrade (regional various) | Regional Rail Revival – Gippsland Rail Upgrade | New | 435000000 | 0% | 0 | 0 | 421500000 | qtr42021-22 | 2017–18 | 1/07/2017 | 2022-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | 0 | New | PNFC | Transport | N/A
Road Safety (statewide) | Road Safety Towards Zero | New | 266000000 | 0% | 0 | 0 | 217000000 | qtr42020‑21 | 2016–17 | 1/07/2016 | 2021-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | Initiative is to be funded and delivered by the Transport Accident Commission. | New | GG | Transport | Initiative is to be funded and delivered by the Transport Accident Commission.
Shepparton line upgrade – Stage 2 (Shepparton) | Shepparton Corridor Upgrade – Stage 2 | New | 312909000 | 0% | 0 | 0 | 307909000 | qtr42021-22 | 2018–19 | 1/07/2018 | 2022-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Shepparton | Shepparton | Regional | 0 | 0 | 0 | New | PNFC | Transport | N/A
Streamlining Hoddle Street (Richmond) | Streamlining Hoddle Street | New | 56210000 | 0% | 0 | 0 | 44970000 | qtr42018‑19 | 2016–17 | 1/07/2016 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Richmond | Richmond | Metropolitan | 0 | 0 | Balance of election commitment was delivered in the 2015‑16 Budget. | New | GG | Transport | Balance of election commitment was delivered in the 2015‑16 Budget.
Suburban Rail Loop | Suburban Rail Loop | New | 250000000 | 0% | 0 | 0 | 0 | tbc | 2019–20 | 1/07/2019 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Unspecified | Unspecified | Unspecified | 0 | 0 | Funding is for detailed planning and development activities. | New | PNFC | Transport | Funding is for detailed planning and development activities.
Suburban Roads Upgrade (metropolitan various) | Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade | New | 2268800000 | 0% | 0 | 2770000 | 2208800000 | qtr22022-23 | 2018–19 | 1/07/2018 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | Yan Yean Road upgrade – Stage 2, will be delivered as part of this initiative. TEI includes estimated PPP finance lease liabilities. | New | GG | Transport | Yan Yean Road upgrade – Stage 2, will be delivered as part of this initiative. TEI includes estimated PPP finance lease liabilities.
Thompsons Road duplication (Lyndhurst) | Thompsons Road duplication | New | 148300000 | 0% | 0 | 0 | 117600000 | qtr42018‑19 | 2016–17 | 1/07/2016 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Lyndhurst | Lyndhurst | Metropolitan | 0 | 0 | Balance of election commitment was delivered in the 2015‑16 Budget. | New | GG | Transport | Balance of election commitment was delivered in the 2015‑16 Budget.
Western Roads upgrade (metropolitan various) | Western Roads upgrade | New | 936810000 | 0% | 0 | 120114000 | 771271000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI includes estimated PPP finance lease liability. This was previously reported as Western Suburbs Roads Package. | Existing | GG | Transport | TEI includes estimated PPP finance lease liability. This was previously reported as Western Suburbs Roads Package.
Women’s prison system capacity (statewide) | Women’s prison system capacity | New | 188900000 | 0% | 0 | 0 | 173900000 | qtr42021‑22 | 2019–20 | 1/07/2019 | 2022-04-01 | Department of Justice and Community Safety | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | 0 | New | GG | Justice and emergency services | N/A
Wonthaggi Hospital expansion (Wonthaggi) | Wonthaggi Hospital emergency department expansion | New | 115000000 | 0% | 0 | 0 | 113000000 | qtr42022-23 | 2018–19 | 1/07/2018 | 2023-04-01 | Department of Health and Human Services | Department of Health | Wonthaggi | Wonthaggi | Regional | 0 | 0 | 0 | New | GG | Health and human services | N/A
Regional rail infrastructure and new regional trains (regional various) | Wyndham Vale Stabling Yard | New | 172900000 | 0% | 0 | 0 | 10800000 | tbc | 2018–19 | 1/07/2018 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | 0 | New | PNFC | Transport | N/A
Yan Yean Road duplication (Plenty) | Yan Yean Road duplication – Stage 1 | New | 126160000 | 0% | 0 | 0 | 113540000 | qtr42019‑20 | 2016–17 | 1/07/2016 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Plenty | Plenty | Metropolitan | 0 | 0 | Balance of election commitment was delivered in the 2015‑16 Budget. | New | GG | Transport | Balance of election commitment was delivered in the 2015‑16 Budget.
40 New trains for Melbourne commuters – stage 1 (metro various) | 40 New trains for Melbourne commuters – stage 1 | Existing | 210360000 | 0% | 0 | 147146000 | 2559000 | qtr42015‑16 | 2014–15 | 1/07/2014 | 2016-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Bayside rail improvements (metro various) | Bayside rail improvements | Existing | 115000000 | 0% | 0 | 10000000 | 37400000 | qtr42016‑17 | 2014–15 | 1/07/2014 | 2017-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | TEI has been increased by $15.000 million due to a change in project scope. | Existing | PNFC | Transport | TEI has been increased by $15.000 million due to a change in project scope.
Box Hill Hospital – Redevelopment (Box Hill) | Box Hill Hospital – Redevelopment | Existing | 447500000 | 0% | 0 | 302800000 | 35700000 | qtr22015‑16 | 2014–15 | 1/07/2014 | 2015-10-01 | Department of Health | Department of Health | Box Hill | Box Hill | Metropolitan | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Building confidence in corrections – Construction/asset enhancement (statewide) | Building confidence in corrections – Construction/asset enhancement | Existing | 108736000 | 0% | 0 | 89704000 | 2000000 | qtr22014‑15 | 2014–15 | 1/07/2014 | 2014-10-01 | Department of Justice | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | GG | Justice and emergency services | N/A
Carlton redevelopment – 246 units/ sites (Carlton) | Carlton redevelopment – 246 units/ sites | Existing | 146422000 | 0% | 0 | 139632000 | 5350000 | qtr22018‑19 | 2014–15 | 1/07/2014 | 2018-10-01 | Director of Housing | Department of Families, Fairness and Housing | Carlton | Carlton | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Connections project (non‑metro various) | Connections project | Existing | 845106000 | 0% | 0 | 530543000 | 232964000 | ongoing | 2014–15 | 1/07/2014 | 2099-06-30 | Goulburn–Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | non‑metro various | Regional | Regional | 0 | 0 | Change in nature of expenditure between capital and operating expenditure. | Existing | PNFC | Water | Change in nature of expenditure between capital and operating expenditure.
Dingley Bypass between Warrigal Road to Westall Road (Dingley) | Dingley Bypass between Warrigal Road to Westall Road | Existing | 155700000 | 0% | 0 | 41103000 | 82002000 | qtr12016‑17 | 2014–15 | 1/07/2014 | 2016-07-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Dingley | Dingley | Metropolitan | 0 | 0 | 0 | Existing | GG | Transport | N/A
East West Link – Eastern section (metro various) | East West Link – Eastern section | Existing | 8000000000 | 0% | 0 | 191000000 | 7519000000 | qtr22019‑20 | 2014–15 | 1/07/2014 | 2019-10-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | 0 | Project previously reported as East West Link – Stage 1 (metro various). | Existing | GG | Transport | Project previously reported as East West Link – Stage 1 (metro various).
Heidelberg redevelopment – 600 units/ sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0% | 0 | 12386000 | 128614000 | qtr42021‑22 | 2014–15 | 1/07/2014 | 2022-04-01 | Director of Housing | Department of Families, Fairness and Housing | Heidelberg | Heidelberg | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Improving hospital services – sub‑acute (statewide) | Improving hospital services – sub‑acute | Existing | 186900000 | 0% | 0 | 174400000 | 0 | qtr42014‑15 | 2014–15 | 1/07/2014 | 2015-04-01 | Department of Health | Department of Health | statewide | Statewide | Statewide | 0 | 0 | This initiative is being delivered as an integrated project with additional funding provided from the Commonwealth’s Health and Hospital Fund – Round 3. | Existing | GG | Health and human services | This initiative is being delivered as an integrated project with additional funding provided from the Commonwealth’s Health and Hospital Fund – Round 3.
Increase Prison Capacity (statewide) | Increase Prison Capacity | Existing | 241814000 | 0% | 0 | 142626000 | 29308000 | qtr22017‑18 | 2014–15 | 1/07/2014 | 2017-10-01 | Department of Justice | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | This initiative includes additional prison beds and new male prison. The TEI reflects reprioritisation of funding to Prison capacity expansion and the application of public private partnership policy. | Existing | GG | Justice and emergency services | This initiative includes additional prison beds and new male prison. The TEI reflects reprioritisation of funding to Prison capacity expansion and the application of public private partnership policy.
M80 Upgrade (metro various) | M80 Upgrade | Existing | 864610000 | 0% | 0 | 844214000 | 14088000 | qtr22014‑15 | 2014–15 | 1/07/2014 | 2014-10-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | 0 | Funding provided by the Commonwealth. TEI has decreased by $35.390 million due to lower than anticipated construction costs. | Existing | GG | Transport | Funding provided by the Commonwealth. TEI has decreased by $35.390 million due to lower than anticipated construction costs.
Melbourne Park redevelopment stage three (Melbourne) | Melbourne Park Redevelopment – stage 3 | Existing | 271555000 | 0% | 0 | 18105000 | 190769000 | qtr42020-21 | 2018–19 | 1/07/2018 | 2021-04-01 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Melbourne | Metropolitan | 0 | 0 | The TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust. | Existing | PNFC | Culture, sport and community | The TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust.
Melbourne Wholesale Markets – redevelopment (Epping) | Melbourne Wholesale Markets redevelopment | Existing | 492418000 | 0% | 0 | 414394000 | 0 | qtr42014‑15 | 2014–15 | 1/07/2014 | 2015-04-01 | Department of State Development, Business and Innovation | Department of Jobs, Precincts and Regions | Epping | Epping | Metropolitan | 0 | 0 | TEI has increased by $39.000 million from the 2013‑14 Budget to facilitate current contracted obligations for construction works prior to return of these funds by the Melbourne Market Authority via a debt facility. | Existing | GG | Culture, sport and community | TEI has increased by $39.000 million from the 2013‑14 Budget to facilitate current contracted obligations for construction works prior to return of these funds by the Melbourne Market Authority via a debt facility.
Melbourne strategic assessment (metro various) | Melbourne strategic assessment | Existing | 334300000 | 0% | 0 | 25170000 | 304130000 | qtr22053‑54 | 2014–15 | 1/07/2014 | 2053-10-01 | Department of Environment and Primary Industries | Department of Environment, Land, Water and Planning | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | GG | Environment | N/A
Metropolitan rail infrastructure renewal program (metro various) | Metropolitan rail infrastructure renewal program | Existing | 748695000 | 0% | 0 | 283624000 | 338205000 | qtr42017‑18 | 2014–15 | 1/07/2014 | 2018-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2012‑13 to 2017‑18. The TEI has reduced, as this is a rolling program of works and the TEI varies from year to year. | Existing | PNFC | Transport | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2012‑13 to 2017‑18. The TEI has reduced, as this is a rolling program of works and the TEI varies from year to year.
Metropolitan rolling stock (metro various) | Metropolitan rolling stock | Existing | 1175317000 | 0% | 0 | 1092139000 | 42428000 | qtr42015‑16 | 2014–15 | 1/07/2014 | 2016-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Monash Children’s Hospital (Clayton) | Monash Children's Hospital | Existing | 250000000 | 0% | 0 | 18500000 | 184500000 | qtr22016‑17 | 2014–15 | 1/07/2014 | 2016-10-01 | Department of Health | Department of Health | Clayton | Clayton | Metropolitan | 0 | 0 | This initiative includes funds allocated in 2011‑12 and 2012‑13 for the planning and development of this project. | Existing | GG | Health and human services | This initiative includes funds allocated in 2011‑12 and 2012‑13 for the planning and development of this project.
New stations in growth areas (metro various) | New stations in growth areas | Existing | 188500000 | 0% | 0 | 164783000 | 0 | qtr42014‑15 | 2014–15 | 1/07/2014 | 2015-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
New trains for Melbourne commuters (metro various) | New trains for Melbourne commuters | Existing | 178068000 | 0% | 0 | 28863000 | 52032000 | qtr42015‑16 | 2014–15 | 1/07/2014 | 2016-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Port Capacity Expansion project | Port Capacity Expansion project | Existing | 892073000 | 0% | 0 | 144223000 | 420924000 | qtr42016‑17 | 2014–15 | 1/07/2014 | 2017-04-01 | Port of Melbourne Corporation | Port of Melbourne Corporation | Unspecified | Unspecified | Unspecified | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Port of Hastings development (Hastings) | Port of Hastings development | Existing | 110000000 | 0% | 0 | 20000000 | 60000000 | qtr42016‑17 | 2014–15 | 1/07/2014 | 2017-04-01 | Port of Hastings Development Authority | Port of Hastings Development Authority | Hastings | Hastings | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Regional Rail Link (various) | Regional Rail Link | Existing | 4101813000 | 0% | 0 | 3264813000 | 259984000 | qtr42014‑15 | 2014–15 | 1/07/2014 | 2015-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | various | Statewide | Statewide | 0 | 0 | TEI revised by $705.331 million based on current project delivery progress. Scope of project expanded to include removal of level crossing at Main Road, St Albans. Estimated completion date reflects the original scope of the project excluding Main Road, St Albans level crossing removal. The estimated completion date for Main Road, St Albans is quarter 4, 2016‑17. | Existing | PNFC | Transport | TEI revised by $705.331 million based on current project delivery progress. Scope of project expanded to include removal of level crossing at Main Road, St Albans. Estimated completion date reflects the original scope of the project excluding Main Road, St Albans level crossing removal. The estimated completion date for Main Road, St Albans is quarter 4, 2016‑17.
Regional rail network major periodic maintenance (passenger and freight) (non‑metro various) | Regional rail network major periodic maintenance (passenger and freight) | Existing | 171865000 | 0% | 0 | 76125000 | 48460000 | qtr42015‑16 | 2014–15 | 1/07/2014 | 2016-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Regional rolling stock (non‑metro various) | Regional rolling stock | Existing | 315150000 | 0% | 0 | 272989000 | 0 | qtr42014‑15 | 2014–15 | 1/07/2014 | 2015-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Regional rolling stock – new tranche (non‑metro various) | Regional rolling stock – new tranche | Existing | 261153000 | 0% | 0 | 150418000 | 70925000 | qtr22017‑18 | 2014–15 | 1/07/2014 | 2017-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Road restoration and road surface replacement (statewide) | Road restoration and road surface replacement | Completed | 122812000 | 0% | 0 | 120015000 | 0 | qtr42018-19 | 2018–19 | 1/07/2018 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | 0 | Completed | GG | Transport | N/A
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 165000000 | 0% | 0 | 30200000 | 111500000 | qtr22017‑18 | 2014–15 | 1/07/2014 | 2017-10-01 | Department of Health | Department of Health | Melbourne | Melbourne | Metropolitan | 0 | 0 | This initiative includes funds allocated in 2012‑13 of $2.000 million for the planning and development of this project. | Existing | GG | Health and human services | This initiative includes funds allocated in 2012‑13 of $2.000 million for the planning and development of this project.
State Coronial Services redevelopment (statewide) | State Coronial Services redevelopment | Existing | 102676000 | 0% | 0 | 90013000 | 0 | qtr22014‑15 | 2014–15 | 1/07/2014 | 2014-10-01 | Department of Justice | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | GG | Justice and emergency services | N/A
Targeted Road restoration (statewide) | Targeted Road restoration | Existing | 90000000 | 0% | 0 | 30000000 | 30000000 | qtr42015‑16 | 2014–15 | 1/07/2014 | 2016-04-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | GG | Transport | N/A
Tram procurement and supporting infrastructure (metro various) | Tram procurement and supporting infrastructure | Existing | 804456000 | 0% | 0 | 242646000 | 326905000 | qtr42017‑18 | 2014–15 | 1/07/2014 | 2018-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
75 by 2025 (Level Crossing Removal) (metropolitan various) | 75 by 2025 (Level Crossing Removal) | New | 6550000000 | 0% | 0 | 0 | 6319979000 | qtr22025‑26 | 2019–20 | 1/07/2019 | 2025-10-01 | Department of Transport | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | LXRP | 0 | New | GG | Transport | N/A
Metro Level Crossing Blitz program | Level crossing removal projects | New | 457319000 | 0% | 0 | 0 | 422919000 | qtr42017‑18 | 2014–15 | 1/07/2014 | 2018-04-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | Unspecified | Unspecified | Unspecified | 0 | LXRP | 0 | New | GG | Transport | N/A
Metropolitan Network Modernisation Program (metropolitan various) | Metropolitan Network Modernisation Program | New | 1392221000 | 0% | 0 | 458453000 | 640982000 | qtr22022-23 | 2017–18 | 1/07/2017 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | LXRP | These comprise a range of network improvements, such as station works, power and other infrastructure upgrades and future proofing works, that are being delivered jointly with the Level Crossing Removal Program. | Existing | GG | Transport | These comprise a range of network improvements, such as station works, power and other infrastructure upgrades and future proofing works, that are being delivered jointly with the Level Crossing Removal Program.
Murray Basin Rail Project (non‑metro various) | Murray Basin Rail Project | New | 220000000 | 0% | 0 | 0 | 209000000 | qtr42017‑18 | 2014–15 | 1/07/2014 | 2018-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | MBRP | 0 | New | PNFC | Transport | N/A
Ballarat rail upgrade (non‑metro various) | Ballarat Line Upgrade | New | 516724000 | 0% | 0 | 0 | 485721000 | qtr42019‑20 | 2016–17 | 1/07/2016 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | Regional Public Transport | 0 | 0 | New | PNFC | Transport | N/A
Chandler Highway Bridge duplication (Alphington/Kew) | Chandler Highway upgrade | New | 110000000 | 0% | 0 | 0 | 107850000 | qtr22018‑19 | 2015–16 | 1/07/2015 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Alphington/Kew | Alphington, Kew | Metropolitan | Better Roads – Metropolitan (including outer metropolitan) | 0 | 0 | New | GG | Transport | N/A
Geelong Line Upgrade – Waurn Ponds Duplication (Stage 1) (regional various) | Geelong Line Upgrade – Waurn Ponds Duplication (stage 1) | New | 110000000 | 0% | 0 | 4491000 | 64412000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | Regional Rail Revival | 0 | TEI includes $99.000 million of Commonwealth funding. | Existing | PNFC | Transport | TEI includes $99.000 million of Commonwealth funding.
Gippsland Line Upgrade Stage 1 (regional various) | Gippsland Line Upgrade Stage 1 | New | 435000000 | 0% | 0 | 5000000 | 407600000 | qtr42021-22 | 2018–19 | 1/07/2018 | 2022-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | Regional Rail Revival (regional various) | 0 | TEI includes $418.000 million of Commonwealth funding. | Existing | PNFC | Transport | TEI includes $418.000 million of Commonwealth funding.
Major periodic maintenance (non‑metro various) | Major periodic maintenance | New | 141207000 | 0% | 0 | 23278000 | 0 | qtr42016‑17 | 2016–17 | 1/07/2016 | 2017-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | Regional Public Transport | 0 | 0 | New | PNFC | Transport | N/A
Monash Freeway upgrade – EastLink to Clyde Road (metropolitan various) | Monash Freeway upgrade – EastLink to Clyde Road | New | 282978000 | 0% | 0 | 126261000 | 32154000 | qtr22018-19 | 2017–18 | 1/07/2017 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | West Gate Tunnel Project (metropolitan various) | West Gate Tunnel Whole(metropolitan various) | TEI excludes corporate costs. | Existing | GG | Transport | TEI excludes corporate costs.
More regional trains (non‑metro various) | More regional trains – New Vlocity Trains | New | 228835000 | 0% | 0 | 0 | 116016000 | qtr42019‑20 | 2016–17 | 1/07/2016 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | Regional Public Transport | 0 | 0 | New | PNFC | Transport | N/A
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | New | 79750000 | 0% | 0 | 0 | 74412000 | qtr42017‑18 | 2015–16 | 1/07/2015 | 2018-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | Better Roads – statewide | 0 | Total package of $90.000 million includes $10.250 million in output funding. | New | GG | Transport | Total package of $90.000 million includes $10.250 million in output funding.
Plenty Road Upgrade (Mill Park) | Plenty Road upgrade – Stage 2 | New | 139410000 | 0% | 0 | 0 | 0 | tbc | 2016–17 | 1/07/2016 | 2089-06-30 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Mill Park | Mill Park | Metropolitan | Outer suburban arterial roads package: | 0 | 0 | New | GG | Transport | N/A
Princes Highway East – Traralgon to Sale duplication (non‑metro various) | Princes Highway East – Traralgon to Sale duplication | Existing | 175000000 | 0% | 0 | 95122000 | 35110000 | qtr32015‑16 | 2014–15 | 1/07/2014 | 2016-01-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | non‑metro various | Regional | Regional | Better Roads – Rural Arterial Roads projects | 0 | Project TEI includes $140.000 million of Commonwealth funding. | Existing | GG | Transport | Project TEI includes $140.000 million of Commonwealth funding.
Princes Highway West – stage 1 Waurn Ponds to Winchelsea (non‑metro various) | Princes Highway West – stage 1 Waurn Ponds to Winchelsea | Existing | 171000000 | 0% | 0 | 101309000 | 47855000 | qtr42014‑15 | 2014–15 | 1/07/2014 | 2015-04-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | non‑metro various | Regional | Regional | Better Roads – Rural Arterial Roads projects | 0 | The TEI has decreased by $49.000 million due to lower than anticipated construction costs. This project includes $85.500 million of Commonwealth funding. | Existing | GG | Transport | The TEI has decreased by $49.000 million due to lower than anticipated construction costs. This project includes $85.500 million of Commonwealth funding.
Relocatable Buildings Program – providing relocatable buildings to meet growing demand (statewide) | Relocatable Buildings Program – providing relocatable buildings to meet growing demand | New | 101273000 | 0% | 0 | 0 | 0 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Department of Education and Training | Department of Education and Training | statewide | Statewide | Statewide | School education | 0 | 0 | New | GG | Education | N/A
Road Safety Strategy 2013‑22 (statewide) | Road Safety Strategy 2013-22 | Existing | 541169000 | 0% | 0 | 52941000 | 410228000 | qtr22022‑23 | 2014–15 | 1/07/2014 | 2022-10-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | statewide | Statewide | Statewide | Transport Accident Commission | 0 | TEI has increased by $41.169 million as a result of a reassessment of the mix of projects between capital and operating based on recent trends. However, the overall program spend remains the same. | Existing | GG | Transport | TEI has increased by $41.169 million as a result of a reassessment of the mix of projects between capital and operating based on recent trends. However, the overall program spend remains the same.
Trade training centres – government schools (statewide) | Trade training centres – government schools | Existing | 248160000 | 0% | 0 | 209729000 | 19000000 | qtr22016‑17 | 2014–15 | 1/07/2014 | 2016-10-01 | Department of Education and Early Childhood Development | Department of Education and Training | statewide | Statewide | Statewide | Commonwealth funding | 0 | TEI increase is due to increased Commonwealth funding. | Existing | GG | Education | TEI increase is due to increased Commonwealth funding.
Warrnambool Line Upgrade (regional various) | Warrnambool Line Upgrade | New | 114000000 | 0% | 0 | 15636000 | 42377000 | qtr42021‑22 | 2019–20 | 1/07/2019 | 2022-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | Regional Rail Revival | Regional Rail Revival | TEI includes $104.000 million of Commonwealth funding. | Existing | PNFC | Transport | TEI includes $104.000 million of Commonwealth funding.
West Gate Tunnel (metropolitan various) | West Gate Tunnel | New | 6344432000 | 0% | 0 | 279761000 | 5774286000 | qtr22022-23 | 2018–19 | 1/07/2018 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | West Gate Tunnel Project | West Gate Tunnel Whole(metropolitan various) | 0 | Existing | GG | Transport | N/A
Western Highway duplication – Ballarat to Stawell (non‑metro various) | Western Highway duplication – Ballarat to Stawell | Existing | 505000000 | 0% | 0 | 225050000 | 162750000 | qtr32015‑16 | 2014–15 | 1/07/2014 | 2016-01-01 | Department of Transport, Planning and Local Infrastructure | Department of Transport | non‑metro various | Regional | Regional | Better Roads – Rural Arterial Roads projects | 0 | Project TEI includes $404.000 million of Commonwealth funding. | Existing | GG | Transport | Project TEI includes $404.000 million of Commonwealth funding.
28 more high capacity metro trains (metro various) | 28 more high capacity metro trains | New | 875000000 | 0% | 0 | 0 | 0 | qtr12023‑24 | 2016–17 | 1/07/2016 | 2023-07-01 | Victorian Rail Track (VicTrack) | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | High Capacity Metro Trains | The TEI is additional to funding of $1.301 billion in the 2015‑16 Budget. The new trains and depot will be procured as a public private partnership and the final financial impacts will be confirmed following the conclusion of the procurement process. | New | PNFC | Transport | The TEI is additional to funding of $1.301 billion in the 2015‑16 Budget. The new trains and depot will be procured as a public private partnership and the final financial impacts will be confirmed following the conclusion of the procurement process.
Bendigo Hospital – Redevelopment (Bendigo) | Bendigo Hospital – Redevelopment | Existing | 129460000 | 0% | 0 | 83560000 | 31300000 | qtr22016‑17 | 2014–15 | 1/07/2014 | 2016-10-01 | Department of Health | Department of Health | Bendigo | Bendigo | Regional | 0 | 0 | The TEI has changed to reflect the public private partnership contract with the remaining capital for State retained associated project costs. The revised TEI for this initiative includes Stage 1 Enabling Works funding of $55.000 million provided in 2009‑10. | Existing | GG | Health and human services | The TEI has changed to reflect the public private partnership contract with the remaining capital for State retained associated project costs. The revised TEI for this initiative includes Stage 1 Enabling Works funding of $55.000 million provided in 2009‑10.
High‑capacity metro trains (metro various) | High Capacity Metro Trains | New | 1301000000 | 0% | 0 | 0 | 1279078000 | qtr42021‑22 | 2015–16 | 1/07/2015 | 2022-04-01 | Victorian Rail Track (VicTrack) | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | High Capacity Metro Trains | Includes procurement of 37 high capacity metropolitan trains, new maintenance depot and associated network upgrades. New trains and depot to be procured as a public private partnership. The total estimated investment includes estimated capital costs only. | New | PNFC | Transport | Includes procurement of 37 high capacity metropolitan trains, new maintenance depot and associated network upgrades. New trains and depot to be procured as a public private partnership. The total estimated investment includes estimated capital costs only.
Level Crossing Removal Program (metro various) | Level Crossing Removal Program | New | 6000000000 | 0% | 0 | 3000000 | 0 | qtr22022‑23 | 2015–16 | 1/07/2015 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | LXRP | The TEI includes funding announced in Getting On With It, February 2015. TEI relates to funding for the full eight year program. Funding will be released progressively as planning for packages of work is completed and projects released to market for tender. Includes the remaining funding for Metro Level Crossing Blitz (metro various). | New | GG | Transport | The TEI includes funding announced in Getting On With It, February 2015. TEI relates to funding for the full eight year program. Funding will be released progressively as planning for packages of work is completed and projects released to market for tender. Includes the remaining funding for Metro Level Crossing Blitz (metro various).
Network Transition Plan – Phase A (Statewide) | Network Transition Plan – Phase A | New | 255838000 | 0% | 0 | 118773000 | 22029000 | qtr22019-20 | 2018–19 | 1/07/2018 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | statewide | Statewide | Statewide | 0 | 0 | TEI includes an additional $33.518 million for power and platform and substation works, funded from savings on other projects. | Existing | PNFC | Transport | TEI includes an additional $33.518 million for power and platform and substation works, funded from savings on other projects.
Nine additional X’Trapolis trains (statewide) | Nine additional X’Trapolis trains | New | 175000000 | 0% | 0 | 63000000 | 49000000 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
North East Link (from Greensborough) | North East Link Planning | New | 100000000 | 0% | 0 | 19993000 | 0 | qtr42026-27 | 2017–18 | 1/07/2017 | 2027-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | from Greensborough | Greensborough | Metropolitan | 0 | 0 | 0 | New | GG | Transport | N/A
North East Link | North East Link Whole | New | 15640286000 | 0% | 0 | 0 | 0 | qtr42026‑27 | 2019–20 | 1/07/2019 | 2027-04-01 | Department of Transport | Department of Transport | Unspecified | Unspecified | Unspecified | 0 | 0 | TEI includes $143.765 million in funding announced in previous budgets and excludes $150.011 million due to certain expenditure being recognised as expensed State costs (rather than capitalised) in accordance with relevant accounting standards. TEI excludes financing costs. Funding profile is not reported at this time due to commercial sensitivity of the live tender process. | New | GG | Transport | TEI includes $143.765 million in funding announced in previous budgets and excludes $150.011 million due to certain expenditure being recognised as expensed State costs (rather than capitalised) in accordance with relevant accounting standards. TEI excludes financing costs. Funding profile is not reported at this time due to commercial sensitivity of the live tender process.
Prison capacity expansion (Melbourne) | Prison capacity expansion | New | 143228000 | 0% | 0 | 50513000 | 16132000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Department of Justice and Regulation | Department of Justice and Community Safety | Melbourne | Melbourne | Metropolitan | 0 | 0 | TEI includes $30.100 million from the Corrections System Expansion, $6.800 million from Corrections Remand upgrade and $0.750 million from Corrections Annual Provisions. | Existing | GG | Justice and emergency services | TEI includes $30.100 million from the Corrections System Expansion, $6.800 million from Corrections Remand upgrade and $0.750 million from Corrections Annual Provisions.
Rail Infrastructure Upgrades from Maryborough and Ararat to Ballarat (statewide) | Rail Infrastructure Upgrades from Maryborough and Ararat to Ballarat | New | 130000000 | 0% | 0 | 0 | 0 | qtr22019-20 | 2018–19 | 1/07/2018 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | statewide | Statewide | Statewide | 0 | MBRP | TEI includes $35.000 million of Commonwealth funding, and $10.000 million redirected from savings from other projects. This project forms part of the Regional Rail Revival program. | New | PNFC | Transport | TEI includes $35.000 million of Commonwealth funding, and $10.000 million redirected from savings from other projects. This project forms part of the Regional Rail Revival program.
Victorian Heart Hospital (Clayton) | Victorian Heart Hospital | New | 135000000 | 0% | 0 | 0 | 135000000 | tbc | 2016–17 | 1/07/2016 | 2089-06-30 | Department of Health and Human Services | Department of Health | Clayton | Clayton | Metropolitan | 0 | 0 | Additional funding of $15.000 million was provided in 2015‑16 for planning and development, bringing the Government’s contribution to $150.000 million. Final project TEI and completion date will be determined following completion of business planning and development, and confirmation of funding contributions from project partners. | New | GG | Health and human services | Additional funding of $15.000 million was provided in 2015‑16 for planning and development, bringing the Government’s contribution to $150.000 million. Final project TEI and completion date will be determined following completion of business planning and development, and confirmation of funding contributions from project partners.
Melbourne Exhibition Centre Stage 2 Development (Southbank) | Melbourne Exhibition Centre Stage 2 Development | Completed | 168700000 | 0% | 0 | 168700000 | 0 | qtr12018‑19 | 2019–20 | 1/07/2019 | 2018-07-01 | Department of Jobs, Precincts and Regions | Department of Jobs, Precincts and Regions | Southbank | Southbank | Metropolitan | 0 | 0 | The estimated completion date has been revised. TEI reflects the state capital construction component only. | Completed | GG | Culture, sport and community | The estimated completion date has been revised. TEI reflects the state capital construction component only.
Bayside rail improvements (metropolitan various) | Bayside rail improvements | Existing | 115000000 | 0% | 0 | 110094000 | 0 | qtr42017-18 | 2017–18 | 1/07/2017 | 2018-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The project completion date has been revised to include the additional scope of the X’Trapolis Train Maintenance facility at Newport with completion expected in 2017-18. | Existing | PNFC | Transport | The project completion date has been revised to include the additional scope of the X’Trapolis Train Maintenance facility at Newport with completion expected in 2017-18.
Bayside rail improvements (metropolitan various) | Bayside rail improvements | Existing | 115000000 | 0% | 0 | 113395000 | 0 | qtr22018-19 | 2018–19 | 1/07/2018 | 2018-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated completion date has been revised. The estimated completion date has been revised due to additional scope at the Newport Maintenance Facility. | Existing | PNFC | Transport | The estimated completion date has been revised. The estimated completion date has been revised due to additional scope at the Newport Maintenance Facility.
Bayside rail improvements (metropolitan various) | Bayside rail improvements | Existing | 115000000 | 0% | 0 | 111995000 | 0 | qtr22019‑20 | 2019–20 | 1/07/2019 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated completion date has been revised to quarter 2 2019‑20 to integrate train operational requirements, including at the Newport Maintenance Facility. | Existing | PNFC | Transport | The estimated completion date has been revised to quarter 2 2019‑20 to integrate train operational requirements, including at the Newport Maintenance Facility.
Geelong Hospital – major upgrade (Geelong) | Geelong Hospital – major upgrade | Completed | 118170000 | 0% | 0 | 114362000 | 0 | qtr42018‑19 | 2019–20 | 1/07/2019 | 2019-04-01 | Department of Health and Human Services | Department of Health | Geelong | Geelong | Regional | 0 | 0 | The project’s cashflow has been revised in line with a revised project schedule. | Completed | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Hurstbridge rail line upgrade (metropolitan various) | Hurstbridge rail line upgrade | Completed | 135905000 | 0% | 0 | 135905000 | 0 | qtr12020‑21 | 2019–20 | 1/07/2019 | 2020-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | Completed | PNFC | Transport | N/A
Melbourne Exhibition Centre – stage 2 development (Southbank) | Melbourne Exhibition Centre Stage 2 Development | Existing | 168700000 | 0% | 0 | 168700000 | 0 | qtr42017-18 | 2018–19 | 1/07/2018 | 2018-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Jobs, Precincts and Regions | Southbank | Southbank | Metropolitan | 0 | 0 | The estimated completion date has been revised. TEI reflects the state capital construction component only. | Existing | GG | Culture, sport and community | The estimated completion date has been revised. TEI reflects the state capital construction component only.
Monash Freeway upgrade – EastLink to Clyde Road (metropolitan various) | Monash Freeway upgrade – EastLink to Clyde Road | Completed | 282879000 | 0% | 0 | 263173000 | 0 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Department of Transport | Department of Transport | metropolitan various | Metropolitan | Metropolitan | West Gate Tunnel Project | West Gate Tunnel Whole(metropolitan various) | 0 | Completed | GG | Transport | N/A
Trade training centres – government schools (statewide) | Trade training centres – government schools | Completed | 252838000 | 0% | 0 | 252838000 | 0 | qtr32019-20 | 2018–19 | 1/07/2018 | 2020-01-01 | Department of Education and Training | Department of Education and Training | statewide | Statewide | Statewide | 0 | 0 | 0 | Completed | GG | Education | N/A
Additional X’Trapolis Metropolitan Trains (metropolitan various) | Additional X’Trapolis Metropolitan Trains | Existing | 103501000 | 0% | 0 | 47949000 | 4306000 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated completion date has been extended to quarter 4 2019‑20 to accommodate the updated delivery schedule of the Digital Train Radio System. | Existing | PNFC | Transport | The estimated completion date has been extended to quarter 4 2019‑20 to accommodate the updated delivery schedule of the Digital Train Radio System.
Box Hill Hospital – Redevelopment (Box Hill) | Box Hill Hospital – Redevelopment | Existing | 447500000 | 0% | 0 | 429891000 | 9037000 | qtr42016‑17 | 2016–17 | 1/07/2016 | 2017-04-01 | Department of Health and Human Services | Department of Health | Box Hill | Box Hill | Metropolitan | 0 | 0 | The project completion date has been revised to reflect the separate ICT component of the project. | Existing | GG | Health and human services | The project completion date has been revised to reflect the separate ICT component of the project.
Building confidence in corrections – Construction/asset enhancement (statewide) | Building confidence in corrections – Construction/asset enhancement | Existing | 108736000 | 0% | 0 | 106736000 | 0 | qtr12015‑16 | 2015–16 | 1/07/2015 | 2015-07-01 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | GG | Justice and emergency services | N/A
Carlton redevelopment – 246 units/ sites (North‑West metropolitan) | Carlton redevelopment – 246 units/ sites | Existing | 146570000 | 0% | 0 | 144064000 | 2000000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Director of Housing | Department of Families, Fairness and Housing | North‑West metropolitan | Metropolitan | Metropolitan | 0 | 0 | The project’s estimated completion date has been extended to quarter 2 2022‑23 due to poor pre‑sales of the private apartments. | Existing | PNFC | Health and human services | The project’s estimated completion date has been extended to quarter 2 2022‑23 due to poor pre‑sales of the private apartments.
Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | Existing | 608281000 | 0% | 0 | 550170000 | 0 | qtr22019-20 | 2018–19 | 1/07/2018 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Chandler Highway upgrade (Alphington, Kew) | Chandler Highway upgrade | Existing | 100015000 | 0% | 0 | 91801000 | 529000 | qtr12019‑20 | 2019–20 | 1/07/2019 | 2019-07-01 | Department of Transport | Department of Transport | Alphington, Kew | Alphington, Kew | Metropolitan | 0 | 0 | The estimated completion date has been revised to quarter 1 2019‑20 due to unexpected asbestos. | Existing | GG | Transport | The estimated completion date has been revised to quarter 1 2019‑20 due to unexpected asbestos.
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | City Loop fire and safety (upgrade stage 2) and intruder alarm | Existing | 151743000 | 0% | 0 | 41176000 | 89343000 | tbc | 2019–20 | 1/07/2019 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Melbourne | Metropolitan | 0 | 0 | The main delivery contractor has been put into administration, and work is progressing to assess the impact to cost and schedule. | Existing | PNFC | Transport | The main delivery contractor has been put into administration, and work is progressing to assess the impact to cost and schedule.
Continuing Towards Zero (regional various) | Continuing Towards Zero | Existing | 149200000 | 0% | 0 | 6000000 | 24999000 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Department of Transport | Department of Transport | regional various | Regional | Regional | 0 | 0 | This initiative is funded by the Transport Accident Commission. The estimated completion date has been revised to quarter 4 2020‑21 due to extended community engagement. | Existing | GG | Transport | This initiative is funded by the Transport Accident Commission. The estimated completion date has been revised to quarter 4 2020‑21 due to extended community engagement.
Conventional signalling upgrade – Caulfield to Dandenong (metro various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | Existing | 360000000 | 0% | 0 | 45000000 | 213000000 | qtr42018‑19 | 2016–17 | 1/07/2016 | 2019-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | Existing | 100000000 | 0% | 0 | 84709000 | 9891000 | qtr22018-19 | 2018–19 | 1/07/2018 | 2018-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Melbourne | Metropolitan | 0 | 0 | The estimated completion date has been revised. The estimated completion date has been brought forward due to acceleration of works. | Existing | PNFC | Transport | The estimated completion date has been revised. The estimated completion date has been brought forward due to acceleration of works.
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | Existing | 100000000 | 0% | 0 | 98753000 | 0 | qtr12019‑20 | 2019–20 | 1/07/2019 | 2019-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Melbourne | Metropolitan | 0 | 0 | The estimated completion date has been revised to quarter 1 2019‑20 to implement signage and pathing improvements. | Existing | PNFC | Transport | The estimated completion date has been revised to quarter 1 2019‑20 to implement signage and pathing improvements.
Geelong Hospital – major upgrade (Geelong) | Geelong Hospital – major upgrade | Existing | 118170000 | 0% | 0 | 97019000 | 11297000 | qtr12018‑19 | 2016–17 | 1/07/2016 | 2018-07-01 | Department of Health and Human Services | Department of Health | Geelong | Geelong | Regional | 0 | 0 | The project completion date has been revised to reflect the additional separate scope funded in 2014‑15. | Existing | GG | Health and human services | The project completion date has been revised to reflect the additional separate scope funded in 2014‑15.
Geelong Hospital – major upgrade (Geelong) | Geelong Hospital – major upgrade | Existing | 118170000 | 0% | 0 | 112620000 | 0 | qtr22018-19 | 2018–19 | 1/07/2018 | 2018-10-01 | Department of Health and Human Services | Department of Health | Geelong | Geelong | Regional | 0 | 0 | The estimated completion date has been revised to reflect project delivery and cashflows approved by Government. | Existing | GG | Health and human services | The estimated completion date has been revised to reflect project delivery and cashflows approved by Government.
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0% | 0 | 30608000 | 115683000 | qtr42022‑23 | 2015–16 | 1/07/2015 | 2023-04-01 | Director of Housing | Department of Families, Fairness and Housing | Heidelberg | Heidelberg | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Hurstbridge rail line upgrade (metropolitan various) | Hurstbridge rail line upgrade | Existing | 135905000 | 0% | 0 | 125283000 | 0 | qtr12018-19 | 2018–19 | 1/07/2018 | 2018-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated completion date has been revised. | Existing | PNFC | Transport | The estimated completion date has been revised.
M80 Ring Road upgrade (north and west metropolitan region) | M80 Ring Road upgrade | Existing | 673077000 | 0% | 0 | 66244000 | 553993000 | qtr32022‑23 | 2019–20 | 1/07/2019 | 2023-01-01 | Department of Transport | Department of Transport | north and west metropolitan region | Metropolitan | Metropolitan | 0 | 0 | TEI includes $336.540 million of Commonwealth funding. The estimated completion date has been revised to quarter 3 2022‑23 due to procurement timing. | Existing | GG | Transport | TEI includes $336.540 million of Commonwealth funding. The estimated completion date has been revised to quarter 3 2022‑23 due to procurement timing.
M80 Ring Road upgrade Sunshine Avenue to Calder Freeway (Sunshine North) | M80 Ring Road upgrade Sunshine Avenue to Calder Freeway | Completed | 293762000 | 0% | 0 | 172416000 | 0 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Department of Transport | Department of Transport | Sunshine North | Sunshine North | Metropolitan | 0 | 0 | TEI includes $150.000 million of Commonwealth funding. | Completed | GG | Transport | TEI includes $150.000 million of Commonwealth funding.
Major periodic maintenance on the regional rail network (regional various) | Major periodic maintenance on the regional rail network | Existing | 287913000 | 0% | 0 | 184913000 | 0 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | The estimated completion date has been revised to quarter 4 2019‑20 to prioritise critical asset maintenance works. | Existing | PNFC | Transport | The estimated completion date has been revised to quarter 4 2019‑20 to prioritise critical asset maintenance works.
Melbourne Park Redevelopment – stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Existing | 338151000 | 0% | 0 | 87000000 | 155548000 | qtr22019‑20 | 2016–17 | 1/07/2016 | 2019-10-01 | Other public non‑financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Melbourne | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Culture, sport and community | N/A
Melbourne Park redevelopment stage three (Melbourne) | Melbourne Park Redevelopment – stage 3 | Existing | 271555000 | 0% | 0 | 80786000 | 82462000 | qtr42021‑22 | 2019–20 | 1/07/2019 | 2022-04-01 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Melbourne | Metropolitan | 0 | 0 | The TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust. The estimated completion date has been revised. | Existing | PNFC | Culture, sport and community | The TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust. The estimated completion date has been revised.
More E-Class trams and infrastructure (metropolitan various) | More E-Class trams and infrastructure | Existing | 215462000 | 0% | 0 | 20366000 | 122070000 | qtr42020-21 | 2018–19 | 1/07/2018 | 2021-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated completion date has been revised. | Existing | PNFC | Transport | The estimated completion date has been revised.
More E‑Class trams and infrastructure (metropolitan various) | More E-Class trams and infrastructure | Existing | 215462000 | 0% | 0 | 56358000 | 89752000 | qtr42021‑22 | 2019–20 | 1/07/2019 | 2022-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated completion date has been revised to quarter 4 2021‑22 as works are progressing to secure land holdings for the power substations. | Existing | PNFC | Transport | The estimated completion date has been revised to quarter 4 2021‑22 as works are progressing to secure land holdings for the power substations.
Murray Basin Rail Project (non‑metro various) | Murray Basin Rail Project | Existing | 220000000 | 0% | 0 | 50500000 | 53500000 | qtr22017‑18 | 2016–17 | 1/07/2016 | 2017-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | MBRP | TEI represents the State Government’s funding commitment. Additional funds to complete the project is being sought from the Commonwealth. | Existing | PNFC | Transport | TEI represents the State Government’s funding commitment. Additional funds to complete the project is being sought from the Commonwealth.
New E-Class trams (metropolitan various) | New E‑Class trams | Existing | 294770000 | 0% | 0 | 75550000 | 149830000 | qtr22019-20 | 2017–18 | 1/07/2017 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated project completion date reflects the revised scope of the project in line with the network development strategy. | Existing | PNFC | Transport | The estimated project completion date reflects the revised scope of the project in line with the network development strategy.
New E‑Class trams (metropolitan various) | New E‑Class trams | Existing | 280204000 | 0% | 0 | 160836000 | 82865000 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated completion date has been revised to quarter 4 2020‑21 as works are progressing to secure land holdings for the power substations. | Existing | PNFC | Transport | The estimated completion date has been revised to quarter 4 2020‑21 as works are progressing to secure land holdings for the power substations.
Northern Hospital inpatient expansion – Stage 2 (Epping) | Northern Hospital inpatient expansion – Stage 2 | Existing | 162672000 | 0% | 0 | 26268000 | 86404000 | qtr12021‑22 | 2019–20 | 1/07/2019 | 2021-07-01 | Department of Health and Human Services | Department of Health | Epping | Epping | Metropolitan | 0 | 0 | The project’s cashflow has been revised in line with a revised project schedule. | Existing | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | Existing | 79750000 | 0% | 0 | 13259000 | 36154000 | qtr22018‑19 | 2016–17 | 1/07/2016 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | GG | Transport | N/A
Princes Highway East – Traralgon to Sale duplication (regional various) | Princes Highway East – Traralgon to Sale duplication | Completed | 259067000 | 0% | 0 | 245849000 | 0 | qtr42021‑22 | 2019–20 | 1/07/2019 | 2022-04-01 | Department of Transport | Department of Transport | regional various | Regional | Regional | 0 | 0 | TEI includes $210.000 million of Commonwealth funding. | Completed | GG | Transport | TEI includes $210.000 million of Commonwealth funding.
Princes Highway duplication project – Winchelsea to Colac (regional various) | Princes Highway duplication project – Winchelsea to Colac | Existing | 349193000 | 0% | 0 | 281830000 | 44063000 | qtr22019‑20 | 2019–20 | 1/07/2019 | 2019-10-01 | Department of Transport | Department of Transport | regional various | Regional | Regional | 0 | 0 | TEI includes $181.735 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2019‑20 due to design changes and archaeological discoveries. | Existing | GG | Transport | TEI includes $181.735 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2019‑20 due to design changes and archaeological discoveries.
Public housing renewal program (statewide) | Public housing renewal program | Existing | 185000000 | 0% | 0 | 6800000 | 162474000 | various | 2018–19 | 1/07/2018 | 2089-06-30 | Director of Housing | Department of Families, Fairness and Housing | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Public housing renewal program (statewide) | Public housing renewal program | Existing | 185000000 | 0% | 0 | 23065000 | 151679000 | qtr42028‑29 | 2019–20 | 1/07/2019 | 2029-04-01 | Director of Housing | Department of Families, Fairness and Housing | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 165000000 | 0% | 0 | 45800000 | 87900000 | qtr22018‑19 | 2015–16 | 1/07/2015 | 2018-10-01 | Department of Health and Human Services | Department of Health | Melbourne | Melbourne | Metropolitan | 0 | 0 | This initiative includes funds allocated in 2012‑13 of $2.000 million for the planning and development of this project. | Existing | GG | Health and human services | This initiative includes funds allocated in 2012‑13 of $2.000 million for the planning and development of this project.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 201000000 | 0% | 0 | 155542000 | 0 | qtr22019-20 | 2018–19 | 1/07/2018 | 2019-10-01 | Department of Health and Human Services | Department of Health | Melbourne | Melbourne | Metropolitan | 0 | 0 | The estimated completion date has been revised to reflect project delivery and cashflows approved by Government. | Existing | GG | Health and human services | The estimated completion date has been revised to reflect project delivery and cashflows approved by Government.
Streamlining Hoddle Street (Richmond) | Streamlining Hoddle Street | Completed | 108554000 | 0% | 0 | 95182000 | 0 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Department of Transport | Department of Transport | Richmond | Richmond | Metropolitan | 0 | 0 | 0 | Completed | GG | Transport | N/A
Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade (metropolitan) | Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade | Existing | 2268800000 | 0% | 0 | 63430000 | 1964208000 | qtr22023‑24 | 2019–20 | 1/07/2019 | 2023-10-01 | Department of Transport | Department of Transport | metropolitan | Metropolitan | Metropolitan | 0 | 0 | TEI includes estimated PPP financial liabilities. TEI includes $1,140 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2023‑24. Yan Yean Road has been funded under this initiative but will be delivered separately to the PPP. | Existing | GG | Transport | TEI includes estimated PPP financial liabilities. TEI includes $1,140 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2023‑24. Yan Yean Road has been funded under this initiative but will be delivered separately to the PPP.
Thompsons Road duplication (Lyndhurst) | Thompsons Road duplication | Completed | 123243000 | 0% | 0 | 122979000 | 0 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Department of Transport | Department of Transport | Lyndhurst | Lyndhurst | Metropolitan | 0 | 0 | 0 | Completed | GG | Transport | N/A
Trade training centres – government schools (statewide) (various) | Trade training centres – government schools | Existing | 248160000 | 0% | 0 | 238160000 | 0 | qtr42016‑17 | 2016–17 | 1/07/2016 | 2017-04-01 | Department of Education and Training | Department of Education and Training | various | Statewide | Statewide | Commonwealth funding | 0 | 0 | Existing | GG | Education | N/A
Tram procurement and supporting infrastructure (metropolitan various) | Tram procurement and supporting infrastructure | Existing | 804456000 | 0% | 0 | 673724000 | 25514000 | qtr22018-19 | 2017–18 | 1/07/2017 | 2018-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The project completion date has been revised to reflect the impact of the unavailability of suitable land to support the tram traction power upgrade project. | Existing | PNFC | Transport | The project completion date has been revised to reflect the impact of the unavailability of suitable land to support the tram traction power upgrade project.
Tram procurement and supporting infrastructure (metropolitan various) | Tram procurement and supporting infrastructure | Existing | 804456000 | 0% | 0 | 648564000 | 38824000 | qtr22019-20 | 2018–19 | 1/07/2018 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated completion date has been revised. | Existing | PNFC | Transport | The estimated completion date has been revised.
Western Highway duplication – Ballarat to Stawell (non‑metro various) | Western Highway duplication – Ballarat to Stawell | Existing | 662300000 | 0% | 0 | 429815000 | 183115000 | qtr32018‑19 | 2016–17 | 1/07/2016 | 2019-01-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | non‑metro various | Regional | Regional | 0 | 0 | TEI includes $501.300 million of Commonwealth funding. | Existing | GG | Transport | TEI includes $501.300 million of Commonwealth funding.
Wyndham Vale Stabling Yard (regional various) | Wyndham Vale Stabling Yard | Existing | 172900000 | 0% | 0 | 82936000 | 13389000 | qtr32019‑20 | 2019–20 | 1/07/2019 | 2020-01-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | Project name changed from ’Regional rail infrastructure and new regional trains’ published in 2018-19 Budget. | Existing | PNFC | Transport | Project name changed from ’Regional rail infrastructure and new regional trains’ published in 2018-19 Budget.
Ballarat Health Services expansion and redevelopment (Ballarat) | Ballarat Health Services expansion and redevelopment | Existing | 461600000 | 0% | 0 | 800000 | 455000000 | qtr42025‑26 | 2019–20 | 1/07/2019 | 2026-04-01 | Department of Health and Human Services | Department of Health | Ballarat | Ballarat | Regional | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Ballarat Line upgrade (regional various) | Ballarat Line Upgrade | Existing | 516724000 | 0% | 0 | 28074000 | 351845000 | qtr42019-20 | 2017–18 | 1/07/2017 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Bayside rail improvements (metro various) | Bayside rail improvements | Existing | 115000000 | 0% | 0 | 69287000 | 12334000 | qtr42016‑17 | 2015–16 | 1/07/2015 | 2017-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Bayside rail improvements (metro various) | Bayside rail improvements | Existing | 115000000 | 0% | 0 | 102666000 | 0 | qtr42016‑17 | 2016–17 | 1/07/2016 | 2017-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Bendigo Hospital – Redevelopment (Bendigo) | Bendigo Hospital – Redevelopment | Existing | 129460000 | 0% | 0 | 97545000 | 16615000 | qtr22016‑17 | 2015–16 | 1/07/2015 | 2016-10-01 | Department of Health and Human Services | Department of Health | Bendigo | Bendigo | Regional | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Bendigo Hospital – Redevelopment (Bendigo) | Bendigo Hospital – Redevelopment | Existing | 129460000 | 0% | 0 | 97386000 | 16738000 | qtr22016‑17 | 2016–17 | 1/07/2016 | 2016-10-01 | Department of Health and Human Services | Department of Health | Bendigo | Bendigo | Regional | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Box Hill Hospital – Redevelopment (Box Hill) | Box Hill Hospital – Redevelopment | Existing | 447500000 | 0% | 0 | 411800000 | 0 | qtr22015‑16 | 2015–16 | 1/07/2015 | 2015-10-01 | Department of Health and Human Services | Department of Health | Box Hill | Box Hill | Metropolitan | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Carlton redevelopment – 246 units/sites (North‑West metro) | Carlton redevelopment – 246 units/ sites | Existing | 146401000 | 0% | 0 | 141186000 | 2990000 | qtr42018‑19 | 2016–17 | 1/07/2016 | 2019-04-01 | Director of Housing | Department of Families, Fairness and Housing | North‑West metro | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Carlton redevelopment – 246 units/sites (North-West metro) | Carlton redevelopment – 246 units/ sites | Existing | 146401000 | 0% | 0 | 143966000 | 87000 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Director of Housing | Department of Families, Fairness and Housing | North-West metro | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | Existing | 106300000 | 0% | 0 | 400000 | 103900000 | qtr42019‑20 | 2016–17 | 1/07/2016 | 2020-04-01 | Department of Health and Human Services | Department of Health | Berwick | Berwick | Metropolitan | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | Existing | 139780000 | 0% | 0 | 120277000 | 0 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Department of Health and Human Services | Department of Health | Berwick | Berwick | Metropolitan | 0 | 0 | The project’s cashflow has been revised in line with a revised project schedule. | Existing | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Chandler Highway upgrade (Alphington, Kew) | Chandler Highway upgrade | Existing | 110000000 | 0% | 0 | 4020000 | 90779000 | qtr22018‑19 | 2016–17 | 1/07/2016 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Alphington, Kew | Alphington, Kew | Metropolitan | 0 | 0 | 0 | Existing | GG | Transport | N/A
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | City Loop fire and safety (upgrade stage 2) and intruder alarm | Existing | 132863000 | 0% | 0 | 4403000 | 81984000 | qtr42019-20 | 2017–18 | 1/07/2017 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Melbourne | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Cranbourne Pakenham and Sunbury Line Upgrades(metropolitan various) | Cranbourne Pakenham and Sunbury Line Upgrades | Existing | 539540000 | 0% | 0 | 456926000 | 0 | qtr22019‑20 | 2019–20 | 1/07/2019 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Dingley Bypass between Warrigal Road to Westall Road (Dingley) | Dingley Bypass between Warrigal Road to Westall Road | Existing | 155700000 | 0% | 0 | 83659000 | 26139000 | qtr12016‑17 | 2015–16 | 1/07/2015 | 2016-07-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Dingley | Dingley | Metropolitan | 0 | 0 | 0 | Existing | GG | Transport | N/A
Drysdale bypass (Drysdale) | Drysdale bypass | Existing | 117377000 | 0% | 0 | 66563000 | 7311000 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Department of Transport | Department of Transport | Drysdale | Drysdale | Regional | 0 | 0 | 0 | Existing | GG | Transport | N/A
Echuca-Moama bridge (Echuca) | Echuca-Moama bridge | Existing | 134903000 | 0% | 0 | 13975000 | 96542000 | qtr42021-22 | 2018–19 | 1/07/2018 | 2022-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Echuca | Echuca | Regional | Rural and Regional Roads Package | 0 | TEI includes $46.000 million of Commonwealth funding and excludes contribution from New South Wales. | Existing | GG | Transport | TEI includes $46.000 million of Commonwealth funding and excludes contribution from New South Wales.
Echuca‑Moama bridge (Echuca) | Echuca-Moama bridge | Existing | 134903000 | 0% | 0 | 33414000 | 69354000 | qtr42021‑22 | 2019–20 | 1/07/2019 | 2022-04-01 | Department of Transport | Department of Transport | Echuca | Echuca | Regional | Rural and Regional Roads Package | 0 | TEI includes $46.000 million of Commonwealth funding and excludes contribution from New South Wales. | Existing | GG | Transport | TEI includes $46.000 million of Commonwealth funding and excludes contribution from New South Wales.
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | Existing | 100000000 | 0% | 0 | 12400000 | 43760000 | qtr42018‑19 | 2016–17 | 1/07/2016 | 2019-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Melbourne | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Flinders Street Station Redevelopment (Melbourne) | Flinders Street Station Redevelopment | Existing | 100000000 | 0% | 0 | 43733000 | 36267000 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Melbourne | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Geelong Hospital – major upgrade (Geelong) | Geelong Hospital – major upgrade | Existing | 118170000 | 0% | 0 | 98183000 | 11487000 | qtr12018-19 | 2017–18 | 1/07/2017 | 2018-07-01 | Department of Health and Human Services | Department of Health | Geelong | Geelong | Regional | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Goulburn Valley Health redevelopment – planning and development (Shepparton) | Goulburn Valley Health redevelopment – planning and development | Existing | 171234000 | 0% | 0 | 63349000 | 27749000 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Department of Health and Human Services | Department of Health | Shepparton | Shepparton | Regional | 0 | 0 | The project’s cashflow has been revised in line with a revised project schedule. | Existing | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule.
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0% | 0 | 49219000 | 94781000 | qtr42022‑23 | 2016–17 | 1/07/2016 | 2023-04-01 | Director of Housing | Department of Families, Fairness and Housing | Heidelberg | Heidelberg | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0% | 0 | 63214000 | 76204000 | qtr42022-23 | 2017–18 | 1/07/2017 | 2023-04-01 | Director of Housing | Department of Families, Fairness and Housing | Heidelberg | Heidelberg | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0% | 0 | 75625000 | 68375000 | qtr42022-23 | 2018–19 | 1/07/2018 | 2023-04-01 | Director of Housing | Department of Families, Fairness and Housing | Heidelberg | Heidelberg | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Heidelberg redevelopment – 600 units/sites (Heidelberg) | Heidelberg redevelopment – 600 units/ sites | Existing | 160000000 | 0% | 0 | 86974000 | 51972000 | qtr42022‑23 | 2019–20 | 1/07/2019 | 2023-04-01 | Director of Housing | Department of Families, Fairness and Housing | Heidelberg | Heidelberg | Metropolitan | 0 | 0 | The project’s cashflow has been revised due to town planning permit issues and inclement weather conditions. The project’s TEI remains unchanged. | Existing | PNFC | Health and human services | The project’s cashflow has been revised due to town planning permit issues and inclement weather conditions. The project’s TEI remains unchanged.
High Capacity Metro Trains (metro various) | High Capacity Metro Trains | Existing | 1301000000 | 0% | 0 | 27303000 | 1238606000 | qtr42021‑22 | 2016–17 | 1/07/2016 | 2022-04-01 | Victorian Rail Track (VicTrack) | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | High Capacity Metro Trains | 0 | Existing | PNFC | Transport | N/A
High Capacity Metro Trains (metropolitan various) | High Capacity Metro Trains | Existing | 2176000000 | 0% | 0 | 595958000 | 1284018000 | qtr12023‑24 | 2019–20 | 1/07/2019 | 2023-07-01 | Victorian Rail Track (VicTrack) | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | High Capacity Metro Trains | TEI includes financing costs. | Existing | PNFC | Transport | TEI includes financing costs.
Hurstbridge rail line upgrade (regional various) | Hurstbridge rail line upgrade | Existing | 135905000 | 0% | 0 | 25075000 | 10624000 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Increase Prison Capacity (statewide) | Increase Prison Capacity | Existing | 256132000 | 0% | 0 | 236585000 | 5000000 | qtr22017-18 | 2017–18 | 1/07/2017 | 2017-10-01 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | GG | Justice and emergency services | N/A
Joan Kirner Women’s and Children’s Hospital (St Albans) | Joan Kirner Women’s and Children’s Hospital | Existing | 200000000 | 0% | 0 | 4765000 | 166053000 | qtr42019‑20 | 2016–17 | 1/07/2016 | 2020-04-01 | Department of Health and Human Services | Department of Health | St Albans | St Albans | Metropolitan | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Joan Kirner Women’s and Children’s Hospital (St. Albans) | Joan Kirner Women’s and Children’s Hospital | Existing | 200000000 | 0% | 0 | 20655000 | 66662000 | qtr42019-20 | 2017–18 | 1/07/2017 | 2020-04-01 | Department of Health and Human Services | Department of Health | St. Albans | St Albans | Metropolitan | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Joan Kirner Women’s and Children’s Hospital (St Albans) | Joan Kirner Women’s and Children’s Hospital | Existing | 200000000 | 0% | 0 | 102124000 | 2507000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Department of Health and Human Services | Department of Health | St Albans | St Albans | Metropolitan | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Joan Kirner Women’s and Children’s Hospital (St Albans) | Joan Kirner Women’s and Children’s Hospital | Existing | 200000000 | 0% | 0 | 184897000 | 0 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Department of Health and Human Services | Department of Health | St Albans | St Albans | Metropolitan | 0 | 0 | The project’s cashflow has been revised in line with a revised project schedule. Construction of the hospital is now complete and is scheduled to open in May 2019. | Existing | GG | Health and human services | The project’s cashflow has been revised in line with a revised project schedule. Construction of the hospital is now complete and is scheduled to open in May 2019.
Level Crossing Removal Program (metro various) | Level Crossing Removal Program | Existing | 6000000000 | 0% | 0 | 302700000 | 5061300000 | qtr22022‑23 | 2016–17 | 1/07/2016 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | LXRP | The TEI includes funding approved as part of the Getting On With It Initiative. Funding will be released progressively as planning for packages of work are completed and projects released to market for tender. | Existing | GG | Transport | The TEI includes funding approved as part of the Getting On With It Initiative. Funding will be released progressively as planning for packages of work are completed and projects released to market for tender.
Level crossing removal projects (metro various) | Level crossing removal projects | Existing | 659319000 | 0% | 0 | 344766000 | 67753000 | qtr42016‑17 | 2016–17 | 1/07/2016 | 2017-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | LXRP | TEI represents funding provided for level crossing removals Blackburn Road (Blackburn), Burke Road (Glen Iris), Main Road (St Albans) and North Road (Ormond). Burke Road (Glen Iris) level crossing removal is expected to be completed before 30 June 2016. TEI includes $151.000 million of Commonwealth funding for Main Road (St Albans). | Existing | GG | Transport | TEI represents funding provided for level crossing removals Blackburn Road (Blackburn), Burke Road (Glen Iris), Main Road (St Albans) and North Road (Ormond). Burke Road (Glen Iris) level crossing removal is expected to be completed before 30 June 2016. TEI includes $151.000 million of Commonwealth funding for Main Road (St Albans).
M80 Ring Road upgrade (north and west metropolitan region) | M80 Ring Road upgrade | Existing | 673077000 | 0% | 0 | 26093000 | 498205000 | qtr32020-21 | 2018–19 | 1/07/2018 | 2021-01-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | north and west metropolitan region | Metropolitan | Metropolitan | 0 | 0 | TEI includes $336.540 million of Commonwealth funding for the capital component of this initiative. | Existing | GG | Transport | TEI includes $336.540 million of Commonwealth funding for the capital component of this initiative.
Major periodic maintenance on the regional rail network (regional various) | Major periodic maintenance on the regional rail network | Existing | 287913000 | 0% | 0 | 103380000 | 103000000 | qtr42020-21 | 2018–19 | 1/07/2018 | 2021-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Melbourne Park redevelopment stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Existing | 338121000 | 0% | 0 | 326551000 | 0 | qtr22020‑21 | 2019–20 | 1/07/2019 | 2020-10-01 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Melbourne | Metropolitan | 0 | 0 | TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust. | Existing | PNFC | Culture, sport and community | TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust.
Melbourne strategic assessment (metro various) | Melbourne strategic assessment | Existing | 334300000 | 0% | 0 | 21693000 | 307607000 | qtr22053‑54 | 2015–16 | 1/07/2015 | 2053-10-01 | Department of Environment, Land, Water and Planning | Department of Environment, Land, Water and Planning | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | GG | Environment | N/A
Melbourne strategic assessment (metro various) | Melbourne strategic assessment | Existing | 334300000 | 0% | 0 | 27316000 | 296984000 | qtr22053‑54 | 2016–17 | 1/07/2016 | 2053-10-01 | Department of Environment Land Water and Planning | Department of Environment, Land, Water and Planning | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | GG | Environment | N/A
Melbourne strategic assessment (metropolitan various) | Melbourne strategic assessment | Existing | 334300000 | 0% | 0 | 30368000 | 293932000 | qtr22053-54 | 2017–18 | 1/07/2017 | 2053-10-01 | Department of Environment, Land, Water and Planning | Department of Environment, Land, Water and Planning | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | GG | Environment | N/A
Melbourne strategic assessment (metropolitan various) | Melbourne strategic assessment | Existing | 330900000 | 0% | 0 | 36914000 | 283986000 | qtr22053‑54 | 2019–20 | 1/07/2019 | 2053-10-01 | Department of Environment, Land, Water and Planning | Department of Environment, Land, Water and Planning | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | GG | Environment | N/A
Metro Level Crossing Blitz program (metro various) | Metro Level Crossing Blitz program | Existing | 68810000 | 0% | 0 | 63670000 | 0 | qtr42016‑17 | 2016–17 | 1/07/2016 | 2017-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | GG | Transport | N/A
Metropolitan Network Modernisation Program (metropolitan various) | Metropolitan Network Modernisation Program | Existing | 1392221000 | 0% | 0 | 707670000 | 493787000 | qtr22022-23 | 2018–19 | 1/07/2018 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | LXRP | These works comprise a range of network improvements, such as station works, power, signalling and other infrastructure upgrades and future-proofing works, that are being delivered jointly with the Level Crossing Removal Program. | Existing | GG | Transport | These works comprise a range of network improvements, such as station works, power, signalling and other infrastructure upgrades and future-proofing works, that are being delivered jointly with the Level Crossing Removal Program.
Metropolitan Network Modernisation Program (metropolitan various) | Metropolitan Network Modernisation Program | Existing | 1392221000 | 0% | 0 | 802075000 | 381199000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Department of Transport | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | LXRP | These works comprise a range of network improvements, such as station works, power, signalling and other infrastructure upgrades and future‑proofing works, that are being delivered jointly with the Level Crossing Removal Program. | Existing | GG | Transport | These works comprise a range of network improvements, such as station works, power, signalling and other infrastructure upgrades and future‑proofing works, that are being delivered jointly with the Level Crossing Removal Program.
Metropolitan and regional restoration and maintenance (statewide) | Metropolitan and regional restoration and maintenance | Existing | 195200000 | 0% | 0 | 100440000 | 1896000 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Department of Transport | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | GG | Transport | N/A
Metropolitan rolling stock (metro various) | Metropolitan rolling stock | Existing | 1175317000 | 0% | 0 | 1111712000 | 22346000 | qtr42015‑16 | 2015–16 | 1/07/2015 | 2016-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Monash Children's Hospital (Clayton) | Monash Children's Hospital | Existing | 250000000 | 0% | 0 | 45600000 | 94400000 | qtr22016‑17 | 2015–16 | 1/07/2015 | 2016-10-01 | Department of Health and Human Services | Department of Health | Clayton | Clayton | Metropolitan | 0 | 0 | This initiative includes funds allocated in 2011‑12 and 2012‑13 for the planning and development of this project. | Existing | GG | Health and human services | This initiative includes funds allocated in 2011‑12 and 2012‑13 for the planning and development of this project.
Monash Freeway upgrade – Stage 2 (South East Melbourne) | Monash Freeway upgrade – Stage 2 | Existing | 684424000 | 0% | 0 | 35313000 | 441984000 | qtr42022‑23 | 2019–20 | 1/07/2019 | 2023-04-01 | Department of Transport | Department of Transport | South East Melbourne | South-East Melbourne | Metropolitan | 0 | 0 | TEI includes $483.800 million of Commonwealth funding. | Existing | GG | Transport | TEI includes $483.800 million of Commonwealth funding.
Mordialloc Freeway (Braeside) | Mordialloc Freeway | Existing | 375000000 | 0% | 0 | 57651000 | 107423000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Department of Transport | Department of Transport | Braeside | Braeside | Metropolitan | 0 | 0 | 0 | Existing | GG | Transport | N/A
More regional trains (regional various) | More regional trains – New Vlocity Trains | Existing | 228835000 | 0% | 0 | 77207000 | 75640000 | qtr42019-20 | 2017–18 | 1/07/2017 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
More regional trains – Regional Network Development Plan (regional various) | More regional trains – New Vlocity Trains | Existing | 228835000 | 0% | 0 | 157645000 | 66956000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | This project was previously reported as More regional trains. | Existing | PNFC | Transport | This project was previously reported as More regional trains.
Murray Basin Rail Project (non‑metro various) | Murray Basin Rail Project | Existing | 220000000 | 0% | 0 | 16000000 | 174000000 | qtr42017‑18 | 2015–16 | 1/07/2015 | 2018-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | MBRP | TEI is estimated to be between $180 million and $220 million. The TEI includes funding announced in Getting On With It. The business case is currently being finalised and will provide options for how best to progress the next stage. | Existing | PNFC | Transport | TEI is estimated to be between $180 million and $220 million. The TEI includes funding announced in Getting On With It. The business case is currently being finalised and will provide options for how best to progress the next stage.
Murray Basin Rail Project (regional various) | Murray Basin Rail Project | Existing | 426500000 | 0% | 0 | 399500000 | 0 | qtr22018-19 | 2018–19 | 1/07/2018 | 2018-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | MBRP | TEI includes $220.000 million of Commonwealth funding. The estimated completion date has been extended due to the delivery of the project aligning with delivery of Ballarat Line Upgrade. | Existing | PNFC | Transport | TEI includes $220.000 million of Commonwealth funding. The estimated completion date has been extended due to the delivery of the project aligning with delivery of Ballarat Line Upgrade.
Network Transition Plan – Phase A (Statewide) | Network Transition Plan – Phase A | Existing | 255838000 | 0% | 0 | 236091000 | 0 | qtr22019‑20 | 2019–20 | 1/07/2019 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
New E‑Class trams (metro various) | New E‑Class trams | Existing | 294770000 | 0% | 0 | 26700000 | 206720000 | qtr22018‑19 | 2016–17 | 1/07/2016 | 2018-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
New VLocity carriages for the regional network (non‑metro various) | New VLocity carriages for the regional network | Existing | 257078000 | 0% | 0 | 72094000 | 57155000 | qtr12018‑19 | 2016–17 | 1/07/2016 | 2018-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
New VLocity carriages for the regional network (regional various) | New VLocity carriages for the regional network | Existing | 257078000 | 0% | 0 | 130723000 | 102509000 | qtr12018-19 | 2017–18 | 1/07/2017 | 2018-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
New youth justice facility (Cherry Creek) | New youth justice facility | Existing | 278409000 | 0% | 0 | 41228000 | 90000000 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Department of Justice and Community Safety | Department of Justice and Community Safety | Cherry Creek | Cherry Creek | Regional | 0 | 0 | 0 | Existing | GG | Justice and emergency services | N/A
Nine additional X’Trapolis trains (metropolitan various) | Nine additional X’Trapolis trains | Existing | 175000000 | 0% | 0 | 130800000 | 0 | qtr42018-19 | 2018–19 | 1/07/2018 | 2019-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Northern Hospital inpatient expansion – Stage 2 (Epping) | Northern Hospital inpatient expansion – Stage 2 | Existing | 162672000 | 0% | 0 | 2472000 | 130200000 | qtr42020-21 | 2018–19 | 1/07/2018 | 2021-04-01 | Department of Health and Human Services | Department of Health | Epping | Epping | Metropolitan | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Princes Highway East – Traralgon to Sale duplication (non‑metro various) | Princes Highway East – Traralgon to Sale duplication | Existing | 260000000 | 0% | 0 | 166280000 | 62817000 | qtr42018‑19 | 2016–17 | 1/07/2016 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | non‑metro various | Regional | Regional | 0 | 0 | TEI includes $210.000 million of Commonwealth funding. | Existing | GG | Transport | TEI includes $210.000 million of Commonwealth funding.
Princes Highway duplication project – Winchelsea to Colac (non‑metro various) | Princes Highway duplication project – Winchelsea to Colac | Existing | 349490000 | 0% | 0 | 5058000 | 311012000 | qtr42018‑19 | 2015–16 | 1/07/2015 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | non‑metro various | Regional | Regional | 0 | 0 | TEI includes $181.735 million of Commonwealth funding. | Existing | GG | Transport | TEI includes $181.735 million of Commonwealth funding.
Princes Highway duplication project – Winchelsea to Colac (non‑metro various) | Princes Highway duplication project – Winchelsea to Colac | Existing | 349490000 | 0% | 0 | 27363000 | 247590000 | qtr42018‑19 | 2016–17 | 1/07/2016 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | non‑metro various | Regional | Regional | 0 | 0 | TEI includes $181.735 million of Commonwealth funding. | Existing | GG | Transport | TEI includes $181.735 million of Commonwealth funding.
Public Safety – Police Response (statewide) | Public Safety – Police Response | Existing | 121956000 | 0% | 0 | 117807000 | 0 | various | 2019–20 | 1/07/2019 | 2089-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | GG | Justice and emergency services | N/A
Regional rail network major periodic maintenance (passenger and freight) (non‑metro various) | Regional rail network major periodic maintenance (passenger and freight) | Existing | 171865000 | 0% | 0 | 123405000 | 0 | qtr42015‑16 | 2015–16 | 1/07/2015 | 2016-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Regional rolling stock – new tranche (non‑metro various) | Regional rolling stock – new tranche | Existing | 251153000 | 0% | 0 | 231337000 | 0 | qtr22017‑18 | 2016–17 | 1/07/2016 | 2017-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Road Safety Strategy 2013‑22 (statewide) | Road Safety Strategy 2013-22 | Existing | 710643000 | 0% | 0 | 203798000 | 414828000 | qtr22022‑23 | 2016–17 | 1/07/2016 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | GG | Transport | N/A
Road Safety Strategy 2013-22 (statewide) | Road Safety Strategy 2013-22 | Existing | 711333000 | 0% | 0 | 397300000 | 131913000 | qtr22022-23 | 2018–19 | 1/07/2018 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | Initiative is funded by the Transport Accident Commission. | Existing | GG | Transport | Initiative is funded by the Transport Accident Commission.
Road Safety Towards Zero (statewide) | Road Safety Towards Zero | Existing | 266000000 | 0% | 0 | 15000000 | 179500000 | qtr42020-21 | 2017–18 | 1/07/2017 | 2021-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | Project name changed from Road Safety (statewide) published in the 2016-17 Budget. | Existing | GG | Transport | Project name changed from Road Safety (statewide) published in the 2016-17 Budget.
Road Safety Towards Zero (statewide) | Road Safety Towards Zero | Existing | 266000000 | 0% | 0 | 103773000 | 119535000 | qtr42020-21 | 2018–19 | 1/07/2018 | 2021-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | Initiative is funded by the Transport Accident Commission. | Existing | GG | Transport | Initiative is funded by the Transport Accident Commission.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 201000000 | 0% | 0 | 103452000 | 33548000 | qtr22018-19 | 2017–18 | 1/07/2017 | 2018-10-01 | Department of Health and Human Services | Department of Health | Melbourne | Melbourne | Metropolitan | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Trade training centres – government schools (statewide) | Trade training centres – government schools | Existing | 248160000 | 0% | 0 | 226500000 | 3660000 | qtr22016‑17 | 2015–16 | 1/07/2015 | 2016-10-01 | Department of Education and Training | Department of Education and Training | statewide | Statewide | Statewide | Commonwealth funding | 0 | 0 | Existing | GG | Education | N/A
Tram procurement and supporting infrastructure (metro various) | Tram procurement and supporting infrastructure | Existing | 804456000 | 0% | 0 | 421273000 | 207504000 | qtr42017‑18 | 2015–16 | 1/07/2015 | 2018-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Tram procurement and supporting infrastructure (metro various) | Tram procurement and supporting infrastructure | Existing | 804456000 | 0% | 0 | 605094000 | 40087000 | qtr42017‑18 | 2016–17 | 1/07/2016 | 2018-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Western Roads upgrade (metropolitan various) | Western Roads upgrade | Existing | 936810000 | 0% | 0 | 718604000 | 0 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Department of Transport | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI includes estimated PPP financial liability. | Existing | GG | Transport | TEI includes estimated PPP financial liability.
Wonthaggi Hospital emergency department expansion (Wonthaggi) | Wonthaggi Hospital emergency department expansion | Existing | 115000000 | 0% | 0 | 2000000 | 83000000 | qtr42022‑23 | 2019–20 | 1/07/2019 | 2023-04-01 | Department of Health and Human Services | Department of Health | Wonthaggi | Wonthaggi | Regional | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Yan Yean Road duplication – Stage 1 (Plenty) | Yan Yean Road duplication – Stage 1 | Existing | 125958000 | 0% | 0 | 117737000 | 1966000 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Department of Transport | Department of Transport | Plenty | Plenty | Metropolitan | 0 | 0 | 0 | Existing | GG | Transport | N/A
40 New trains for Melbourne commuters – stage 1 (metro various) | 40 New trains for Melbourne commuters – stage 1 | Existing | 207360000 | -1.426% | -3000000 | 185672000 | 5694000 | qtr42015‑16 | 2015–16 | 1/07/2015 | 2016-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | TEI has decreased by $3.000 million. This is due to project savings. | Existing | PNFC | Transport | TEI has decreased by $3.000 million. This is due to project savings.
Ballarat Line Upgrade Stage 1 (regional various) | Ballarat Line Upgrade | Existing | 549455000 | 6.334% | 32731000 | 98076000 | 20563000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | Regional Rail Revival (regional various) | 0 | TEI includes $467.000 million of Commonwealth funding. TEI includes additional funding of $33.700 million to build a new train station at Toolern and excludes $0.969 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. | Existing | PNFC | Transport | TEI includes $467.000 million of Commonwealth funding. TEI includes additional funding of $33.700 million to build a new train station at Toolern and excludes $0.969 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
Ballarat Line Upgrade Stage 1 (regional various) | Ballarat Line Upgrade | Existing | 545014000 | -0.8083% | -4441000 | 370472000 | 16177000 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | Regional Rail Revival | 0 | TEI includes $467.000 million of Commonwealth funding, and excludes $4.441 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. | Existing | PNFC | Transport | TEI includes $467.000 million of Commonwealth funding, and excludes $4.441 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
Carlton redevelopment – 246 units/sites (North-West metropolitan) | Carlton redevelopment – 246 units/ sites | Existing | 146570000 | 0.1154% | 169000 | 144170000 | 1500000 | qtr42018-19 | 2018–19 | 1/07/2018 | 2019-04-01 | Director of Housing | Department of Families, Fairness and Housing | North-West metropolitan | Metropolitan | Metropolitan | 0 | 0 | The project TEI has increased to $146.57 million due to latent site conditions. | Existing | PNFC | Health and human services | The project TEI has increased to $146.57 million due to latent site conditions.
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | Existing | 139910000 | 31.62% | 33610000 | 5507000 | 81534000 | qtr42019-20 | 2017–18 | 1/07/2017 | 2020-04-01 | Department of Health and Human Services | Department of Health | Berwick | Berwick | Metropolitan | 0 | 0 | The TEI for this project has increased by $28.610 million to provide an additional 64 multi-day beds and includes a funding contribution of $5.000 million from Monash University for accommodation space. | Existing | GG | Health and human services | The TEI for this project has increased by $28.610 million to provide an additional 64 multi-day beds and includes a funding contribution of $5.000 million from Monash University for accommodation space.
Casey Hospital Expansion (Berwick) | Casey Hospital Expansion | Existing | 139780000 | -0.09292% | -130000 | 58743000 | 3612000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Department of Health and Human Services | Department of Health | Berwick | Berwick | Metropolitan | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | Existing | 608121000 | -0.0263% | -160000 | 561183000 | 0 | qtr22019‑20 | 2019–20 | 1/07/2019 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI excludes $0.160 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. | Existing | PNFC | Transport | TEI excludes $0.160 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
Chandler Highway upgrade (Alphington, Kew) | Chandler Highway upgrade | Existing | 109721000 | -0.2536% | -279000 | 19331000 | 51039000 | qtr22018-19 | 2017–18 | 1/07/2017 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Alphington, Kew | Alphington, Kew | Metropolitan | 0 | 0 | TEI excludes corporate costs. | Existing | GG | Transport | TEI excludes corporate costs.
Chandler Highway upgrade (Alphington, Kew) | Chandler Highway upgrade | Existing | 100015000 | -8.846% | -9706000 | 59264000 | 8215000 | qtr22018-19 | 2018–19 | 1/07/2018 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Alphington, Kew | Alphington, Kew | Metropolitan | 0 | 0 | TEI has decreased with $9.706 million identified project savings. | Existing | GG | Transport | TEI has decreased with $9.706 million identified project savings.
Community Safety Statement (statewide) | Community Safety Statement | Existing | 362864000 | -7.092% | -27700000 | 39476000 | 236358000 | various | 2018–19 | 1/07/2018 | 2089-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | TEI has reduced due to $27.700 million having been redirected to output funding to correctly reflect the expenditure for the BlueConnect project. A number of components were initially planned to be purchased (capital expenditure) but have been changed to a lease arrangement (output expenditure). Cash flow has been revised in line with project schedule. Cash flow has been revised in line with project schedule. | Existing | GG | Justice and emergency services | TEI has reduced due to $27.700 million having been redirected to output funding to correctly reflect the expenditure for the BlueConnect project. A number of components were initially planned to be purchased (capital expenditure) but have been changed to a lease arrangement (output expenditure). Cash flow has been revised in line with project schedule. Cash flow has been revised in line with project schedule.
Community Safety Statement (statewide) | Community Safety Statement | Existing | 327564000 | -9.728% | -35300000 | 126506000 | 70762000 | various | 2019–20 | 1/07/2019 | 2089-06-30 | Department of Justice and Community Safety | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | TEI has been revised due to changes in project scope, with additional resources allocated to police operations. | Existing | GG | Justice and emergency services | TEI has been revised due to changes in project scope, with additional resources allocated to police operations.
Connections project (non‑metro various) | Connections project | Existing | 927357000 | 12.7% | 104521000 | 716198000 | 133149000 | qtr42017‑18 | 2016–17 | 1/07/2016 | 2018-04-01 | Goulburn‑Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | non‑metro various | Regional | Regional | 0 | 0 | TEI has increased compared to the 2015‑16 Budget due to a change in accounting treatment of capital and output expenditure. | Existing | PNFC | Water | TEI has increased compared to the 2015‑16 Budget due to a change in accounting treatment of capital and output expenditure.
Connections project (regional various) | Connections project | Existing | 1104678000 | 8.831% | 89640000 | 902235000 | 51662000 | qtr22020-21 | 2018–19 | 1/07/2018 | 2020-10-01 | Goulburn Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | regional various | Regional | Regional | 0 | 0 | The capital component of the overall project TEI has increased from prior year, however this is offset with a decrease in output expenditure. Overall project forecast remains unchanged. This is in alignment with the Reset Delivery Plan and the Stage 1 Completion Plan. | Existing | PNFC | Water | The capital component of the overall project TEI has increased from prior year, however this is offset with a decrease in output expenditure. Overall project forecast remains unchanged. This is in alignment with the Reset Delivery Plan and the Stage 1 Completion Plan.
Connections project (regional various) | Connections project | Existing | 1099986000 | -0.4247% | -4692000 | 1053016000 | 0 | qtr22020‑21 | 2019–20 | 1/07/2019 | 2020-10-01 | Goulburn Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | regional various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Water | N/A
Corrections system expansion (statewide) | Corrections system expansion | Existing | 108360000 | -23.02% | -32400000 | 21410000 | 25900000 | qtr42016‑17 | 2015–16 | 1/07/2015 | 2017-04-01 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | The TEI includes previously approved funding of $19.460 million and reflects a reprioritisation of $22.400 million to Critical infrastructure and services. | Existing | GG | Justice and emergency services | The TEI includes previously approved funding of $19.460 million and reflects a reprioritisation of $22.400 million to Critical infrastructure and services.
Drysdale bypass (Drysdale) | Drysdale bypass | Existing | 102377000 | -0.1784% | -183000 | 8878000 | 74440000 | qtr42019-20 | 2017–18 | 1/07/2017 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Drysdale | Drysdale | Regional | 0 | 0 | TEI excludes corporate costs. | Existing | GG | Transport | TEI excludes corporate costs.
Drysdale bypass (Drysdale) | Drysdale bypass | Existing | 117377000 | 14.65% | 15000000 | 22018000 | 60479000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Drysdale | Drysdale | Regional | 0 | 0 | TEI has increased by $15.000 million due to market conditions, and is funded by savings achieved on other projects. | Existing | GG | Transport | TEI has increased by $15.000 million due to market conditions, and is funded by savings achieved on other projects.
Frankston Line stabling (Kananook) | Frankston Line stabling | Existing | 236683000 | -0.000845% | -2000 | 109994000 | 2616000 | qtr32019‑20 | 2019–20 | 1/07/2019 | 2020-01-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Kananook | Kananook | Regional | 0 | 0 | TEI excludes $0.002 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. | Existing | PNFC | Transport | TEI excludes $0.002 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards.
Goulburn Valley Health redevelopment – planning and development (Shepparton) | Goulburn Valley Health redevelopment – planning and development | Existing | 170525000 | 1.187% | 2000000 | 4649000 | 136477000 | qtr42020-21 | 2017–18 | 1/07/2017 | 2021-04-01 | Department of Health and Human Services | Department of Health | Shepparton | Shepparton | Regional | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Goulburn Valley Health redevelopment – planning and development (Shepparton) | Goulburn Valley Health redevelopment – planning and development | Existing | 171234000 | 0.4158% | 709000 | 19485000 | 98749000 | qtr42020-21 | 2018–19 | 1/07/2018 | 2021-04-01 | Department of Health and Human Services | Department of Health | Shepparton | Shepparton | Regional | 0 | 0 | Additional funding of $1.709 million was provided in 2017-18 through internal prioritisation. | Existing | GG | Health and human services | Additional funding of $1.709 million was provided in 2017-18 through internal prioritisation.
Increase Prison Capacity (statewide) | Increase Prison Capacity | Existing | 246414000 | 1.902% | 4600000 | 161807000 | 22607000 | qtr22017‑18 | 2015–16 | 1/07/2015 | 2017-10-01 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | This initiative includes additional prison beds and the new male prison. The TEI reflects previously reprioritised funding, the application of public private partnership policy and a reprioritisation of $5.400 million to Critical infrastructure and services in the current budget. | Existing | GG | Justice and emergency services | This initiative includes additional prison beds and the new male prison. The TEI reflects previously reprioritised funding, the application of public private partnership policy and a reprioritisation of $5.400 million to Critical infrastructure and services in the current budget.
Increase Prison Capacity (statewide) | Increase Prison Capacity | Existing | 256132000 | 3.944% | 9718000 | 233525000 | 13307000 | qtr22017‑18 | 2016–17 | 1/07/2016 | 2017-10-01 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | This initiative includes $9.152 million reprioritised funding from the Building confidence in corrections asset initiative, with $0.217 million redirected to Critical infrastructure and services. | Existing | GG | Justice and emergency services | This initiative includes $9.152 million reprioritised funding from the Building confidence in corrections asset initiative, with $0.217 million redirected to Critical infrastructure and services.
Level Crossing Removal Program (metropolitan various) | Level Crossing Removal Program | Existing | 6878756000 | 14.65% | 878756000 | 1942250000 | 3764260000 | qtr22022-23 | 2017–18 | 1/07/2017 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | LXRP | Estimated total cost of the program to remove 50 level crossings across metropolitan Melbourne. TEI includes the cost of the 10 level crossings removed, which were previously listed separately under the initiative titled ‘Level crossing removal projects’ in 2016-17 Budget Paper No. 4. TEI includes $151.000 million of Commonwealth funding for Main Road (St. Albans) | Existing | GG | Transport | Estimated total cost of the program to remove 50 level crossings across metropolitan Melbourne. TEI includes the cost of the 10 level crossings removed, which were previously listed separately under the initiative titled ‘Level crossing removal projects’ in 2016-17 Budget Paper No. 4. TEI includes $151.000 million of Commonwealth funding for Main Road (St. Albans)
Level Crossing Removal Program (metropolitan various) | Level Crossing Removal Program | Existing | 6761603000 | -1.703% | -117153000 | 3464267000 | 2371117000 | qtr22022-23 | 2018–19 | 1/07/2018 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | LXRP | TEI excludes $117.153 million now recognised as operating instead of capital in line with accounting standards. TEI includes the cost of level crossings removed to date, including four which were previously listed separately under the initiative titled Level crossing removal projects in 2017‑18 Budget Paper No. 4. TEI includes $151.000 million of Commonwealth funding for Main Road (St. Albans). | Existing | GG | Transport | TEI excludes $117.153 million now recognised as operating instead of capital in line with accounting standards. TEI includes the cost of level crossings removed to date, including four which were previously listed separately under the initiative titled Level crossing removal projects in 2017‑18 Budget Paper No. 4. TEI includes $151.000 million of Commonwealth funding for Main Road (St. Albans).
Level Crossing Removal Program (metropolitan various) | Level Crossing Removal Program | Existing | 6759019000 | -0.03822% | -2584000 | 3958293000 | 1785573000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Department of Transport | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | LXRP | TEI includes $151.000 million of Commonwealth funding for Main Road St Albans, and excludes $119.753 million recognised as operating instead of capital in line with accounting standards. | Existing | GG | Transport | TEI includes $151.000 million of Commonwealth funding for Main Road St Albans, and excludes $119.753 million recognised as operating instead of capital in line with accounting standards.
M80 Ring Road upgrade Sunshine Avenue to Calder Freeway (Sunshine North) | M80 Ring Road upgrade Sunshine Avenue to Calder Freeway | Existing | 294118000 | -1.961% | -5882000 | 66873000 | 144926000 | qtr22018-19 | 2017–18 | 1/07/2017 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Sunshine North | Sunshine North | Metropolitan | 0 | 0 | TEI excludes corporate costs. TEI includes $150.000 million of Commonwealth funding. Project name changed from M80 Upgrade Sunshine Avenue to Calder Freeway (Sunshine North) published in 2016-17 budget papers. | Existing | GG | Transport | TEI excludes corporate costs. TEI includes $150.000 million of Commonwealth funding. Project name changed from M80 Upgrade Sunshine Avenue to Calder Freeway (Sunshine North) published in 2016-17 budget papers.
M80 Ring Road upgrade Sunshine Avenue to Calder Freeway (Sunshine North) | M80 Ring Road upgrade Sunshine Avenue to Calder Freeway | Existing | 293762000 | -0.121% | -356000 | 158079000 | 115314000 | qtr22018-19 | 2018–19 | 1/07/2018 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Sunshine North | Sunshine North | Metropolitan | 0 | 0 | TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $150.000 million of Commonwealth funding. | Existing | GG | Transport | TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $150.000 million of Commonwealth funding.
Melbourne Park Redevelopment – stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Existing | 338151000 | -7.645% | -27990000 | 21760000 | 251151000 | qtr42019‑20 | 2015–16 | 1/07/2015 | 2020-04-01 | Other public non‑financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Melbourne | Metropolitan | 0 | 0 | TEI has reduced by $27.990 million due to clarification of funding sources. | Existing | PNFC | Culture, sport and community | TEI has reduced by $27.990 million due to clarification of funding sources.
Melbourne Park redevelopment stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Existing | 338150000 | -0.0002957% | -1000 | 169570000 | 63540000 | qtr22019-20 | 2017–18 | 1/07/2017 | 2019-10-01 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Melbourne | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Culture, sport and community | N/A
Melbourne strategic assessment (metropolitan various) | Melbourne strategic assessment | Existing | 330900000 | -1.017% | -3400000 | 27425000 | 293475000 | qtr22053-54 | 2018–19 | 1/07/2018 | 2053-10-01 | Department of Environment, Land, Water and Planning | Department of Environment, Land, Water and Planning | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The TEI has been revised from $334.300 million to $330.900 million. The decrease is the result of $3.400 million reclassified to output. | Existing | GG | Environment | The TEI has been revised from $334.300 million to $330.900 million. The decrease is the result of $3.400 million reclassified to output.
Metro Tunnel (metropolitan various) | Metro Tunnel | Existing | 11031000000 | 1.202% | 131000000 | 929391000 | 9246097000 | qtr42025-26 | 2017–18 | 1/07/2017 | 2026-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI has increased by $131.000 million due to a change in project scope. This includes a reallocation of the High Capacity Signalling Trial (HCST) funding provided in the 2015-16 Budget to support HCS implementation on the Metro Tunnel project. | Existing | PNFC | Transport | TEI has increased by $131.000 million due to a change in project scope. This includes a reallocation of the High Capacity Signalling Trial (HCST) funding provided in the 2015-16 Budget to support HCS implementation on the Metro Tunnel project.
Metro Tunnel (metropolitan various) | Metro Tunnel | Existing | 10883144000 | -0.995% | -109380000 | 4460097000 | 4832050000 | qtr22025‑26 | 2019–20 | 1/07/2019 | 2025-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI excludes $109.380 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. TEI excludes financing costs. | Existing | PNFC | Transport | TEI excludes $109.380 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. TEI excludes financing costs.
Metropolitan rail infrastructure renewal program (metropolitan various) | Metropolitan rail infrastructure renewal program | Existing | 1489361000 | -2.589% | -39577000 | 441697000 | 772800000 | qtr42024‑25 | 2019–20 | 1/07/2019 | 2025-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI has been reduced by $4.450 million due to savings, and $35.127 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. As a rolling program of works, the TEI varies from year to year. TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2016‑17 to 2024‑25, including funding provided in the 2017‑18 Budget Update for the management of the new train and tram franchise agreement that commenced on 30 November 2017. | Existing | PNFC | Transport | TEI has been reduced by $4.450 million due to savings, and $35.127 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. As a rolling program of works, the TEI varies from year to year. TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2016‑17 to 2024‑25, including funding provided in the 2017‑18 Budget Update for the management of the new train and tram franchise agreement that commenced on 30 November 2017.
Monash Children’s Hospital (Clayton) | Monash Children's Hospital | Existing | 258175000 | 3.27% | 8175000 | 163563000 | 0 | qtr22016‑17 | 2016–17 | 1/07/2016 | 2016-10-01 | Department of Health and Human Services | Department of Health | Clayton | Clayton | Metropolitan | 0 | 0 | The TEI for this project includes $3.800 million for the MCH Helipad, reported as a separate project in the 2015‑16 budget. The TEI has also increased due to $4.375 million in additional funding provided by Monash University for accommodation space. | Existing | GG | Health and human services | The TEI for this project includes $3.800 million for the MCH Helipad, reported as a separate project in the 2015‑16 budget. The TEI has also increased due to $4.375 million in additional funding provided by Monash University for accommodation space.
Monash Freeway upgrade – EastLink to Clyde Road (metropolitan various) | Monash Freeway upgrade – EastLink to Clyde Road | Existing | 282879000 | -0.03499% | -99000 | 253828000 | 0 | qtr22018-19 | 2018–19 | 1/07/2018 | 2018-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | West Gate Tunnel Project | West Gate Tunnel Whole(metropolitan various) | 0 | Existing | GG | Transport | N/A
More regional trains – Regional Network Development Plan (regional various) | More regional trains – New Vlocity Trains | Existing | 226335000 | -1.092% | -2500000 | 156192000 | 46102000 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | TEI has reduced by $2.500 million due to savings. | Existing | PNFC | Transport | TEI has reduced by $2.500 million due to savings.
More regional trains – New Vlocity Trains (regional various) | More regional trains – Regional Network Development Plan | Existing | 270424000 | -2.065% | -5701000 | 170817000 | 33535000 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | TEI has reduced by $5.701 million due to savings. | Existing | PNFC | Transport | TEI has reduced by $5.701 million due to savings.
New trains for Melbourne commuters (metro various) | New trains for Melbourne commuters | Existing | 145068000 | -18.53% | -33000000 | 108862000 | 8521000 | qtr42015‑16 | 2015–16 | 1/07/2015 | 2016-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | TEI has decreased by $33.000 million. This is due to project savings. | Existing | PNFC | Transport | TEI has decreased by $33.000 million. This is due to project savings.
New youth justice facility (Cherry Creek) | New youth justice facility | Existing | 278409000 | -3.565% | -10291000 | 17123000 | 192181000 | qtr42020-21 | 2018–19 | 1/07/2018 | 2021-04-01 | Department of Justice and Regulation | Department of Justice and Community Safety | Cherry Creek | Cherry Creek | Regional | 0 | 0 | TEI has reduced due to $10.291 million having been transferred to output funding for this initiative. | Existing | GG | Justice and emergency services | TEI has reduced due to $10.291 million having been transferred to output funding for this initiative.
North East Link (from Greensborough) | North East Link Planning | Existing | 143765000 | 43.77% | 43765000 | 20665000 | 0 | qtr42026-27 | 2018–19 | 1/07/2018 | 2027-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | from Greensborough | Greensborough | Metropolitan | 0 | 0 | TEI has increased by $104.000 million due to approval of additional funding to progress procurement and planning approvals, offset by a $60.235 million decrease due to certain expenditure being recognised as operating instead of capital in line with accounting standards | Existing | GG | Transport | TEI has increased by $104.000 million due to approval of additional funding to progress procurement and planning approvals, offset by a $60.235 million decrease due to certain expenditure being recognised as operating instead of capital in line with accounting standards
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | Existing | 82456000 | 2.307% | 1859000 | 76159000 | 0 | qtr42018-19 | 2018–19 | 1/07/2018 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | TEI includes additional funding of $1.859 million to deliver projects within the scope of the program. | Existing | GG | Transport | TEI includes additional funding of $1.859 million to deliver projects within the scope of the program.
O’Herns Road upgrade (Epping) | O’Herns Road upgrade | Existing | 77803000 | 0.02185% | 17000 | 13878000 | 28368000 | qtr22019-20 | 2018–19 | 1/07/2018 | 2019-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Epping | Epping | Metropolitan | Urban Congestion Package | 0 | TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes additional funding of $0.017 million for revised scope within this program. TEI includes $25.801 million of Commonwealth funding. | Existing | GG | Transport | TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes additional funding of $0.017 million for revised scope within this program. TEI includes $25.801 million of Commonwealth funding.
Plenty Road upgrade – Stage 2 (South Morang) | Plenty Road upgrade – Stage 2 | Existing | 103409000 | -9.456% | -10800000 | 9030000 | 37869000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | South Morang | South Morang | Metropolitan | 0 | 0 | TEI reflects allocation of $10.004 million from Plenty Road upgrade – Stage 2 towards Plenty Road upgrade – Stage 1 and an identified project savings of $0.800 million. | Existing | GG | Transport | TEI reflects allocation of $10.004 million from Plenty Road upgrade – Stage 2 towards Plenty Road upgrade – Stage 1 and an identified project savings of $0.800 million.
Port capacity expansion project (Melbourne) | Port Capacity Expansion project | Existing | 598109000 | -6.735% | -43189000 | 456886000 | 0 | ongoing | 2016–17 | 1/07/2016 | 2099-06-30 | Port of Melbourne Corporation | Port of Melbourne Corporation | Melbourne | Melbourne | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Transport | N/A
Princes Highway East – Traralgon to Sale duplication (regional various) | Princes Highway East – Traralgon to Sale duplication | Existing | 259284000 | -0.2754% | -716000 | 198576000 | 28677000 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | regional various | Regional | Regional | 0 | 0 | TEI includes $210.000 million of Commonwealth funding. | Existing | GG | Transport | TEI includes $210.000 million of Commonwealth funding.
Princes Highway East – Traralgon to Sale duplication (regional various) | Princes Highway East – Traralgon to Sale duplication | Existing | 259067000 | -0.08369% | -217000 | 237179000 | 11888000 | qtr42018-19 | 2018–19 | 1/07/2018 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | regional various | Regional | Regional | 0 | 0 | TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $210.000 million Commonwealth funding. | Existing | GG | Transport | TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $210.000 million Commonwealth funding.
Princes Highway duplication project – Winchelsea to Colac (regional various) | Princes Highway duplication project – Winchelsea to Colac | Existing | 349222000 | -0.07668% | -268000 | 84493000 | 157930000 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | regional various | Regional | Regional | 0 | 0 | TEI excludes corporate costs. TEI includes $181.735 million of Commonwealth funding. | Existing | GG | Transport | TEI excludes corporate costs. TEI includes $181.735 million of Commonwealth funding.
Princes Highway duplication project – Winchelsea to Colac (regional various) | Princes Highway duplication project – Winchelsea to Colac | Existing | 349193000 | -0.008304% | -29000 | 183177000 | 98263000 | qtr42018-19 | 2018–19 | 1/07/2018 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | regional various | Regional | Regional | 0 | 0 | The estimated completion date has been revised. TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $181.735 million of Commonwealth funding. TEI includes $29.120 million of identified project savings. | Existing | GG | Transport | The estimated completion date has been revised. TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $181.735 million of Commonwealth funding. TEI includes $29.120 million of identified project savings.
Public Safety – Police Response (statewide) | Public Safety – Police Response | Existing | 121956000 | -11.48% | -15810000 | 78713000 | 4149000 | various | 2018–19 | 1/07/2018 | 2089-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | TEI has reduced due to $17.710 million having been redirected to output funding for the Intelligence Capability project and $1.900 million having been redirected from output funding for the Mobile Technology Rollout project to correctly reflect the nature of the expenditure. Cash flow has been revised in line with project schedule. The estimated completion dates for the major components are: Intelligence Capability (quarter 4, 2018-19), Mobile Technology (quarter 4, 2018-19), Specialist Equipment (quarter 1, 2018-19) and Body Worn Cameras (quarter 4, 2018-19). | Existing | GG | Justice and emergency services | TEI has reduced due to $17.710 million having been redirected to output funding for the Intelligence Capability project and $1.900 million having been redirected from output funding for the Mobile Technology Rollout project to correctly reflect the nature of the expenditure. Cash flow has been revised in line with project schedule. The estimated completion dates for the major components are: Intelligence Capability (quarter 4, 2018-19), Mobile Technology (quarter 4, 2018-19), Specialist Equipment (quarter 1, 2018-19) and Body Worn Cameras (quarter 4, 2018-19).
Regional rolling stock – new tranche (non‑metro various) | Regional rolling stock – new tranche | Existing | 251153000 | -3.829% | -10000000 | 195887000 | 19816000 | qtr22017‑18 | 2015–16 | 1/07/2015 | 2017-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | non‑metro various | Regional | Regional | 0 | 0 | TEI has decreased by $10.000 million. This is due to project savings. | Existing | PNFC | Transport | TEI has decreased by $10.000 million. This is due to project savings.
Road Safety Strategy 2013‑22 (statewide) | Road Safety Strategy 2013-22 | Existing | 710643000 | 31.32% | 169474000 | 138379000 | 497299000 | qtr22022‑23 | 2015–16 | 1/07/2015 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | Transport Accident Commission | 0 | TEI has increased by $169.474 million. This is due to a reassessment of the estimated mix of projects between capital and output. The total program spend remains the same. | Existing | GG | Transport | TEI has increased by $169.474 million. This is due to a reassessment of the estimated mix of projects between capital and output. The total program spend remains the same.
Road Safety Strategy 2013-22 (statewide) | Road Safety Strategy 2013-22 | Existing | 711333000 | 0.0971% | 690000 | 282873000 | 310517000 | qtr22022-23 | 2017–18 | 1/07/2017 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | Initiative is to be funded by the Transport Accident Commission. TEI has increased by $0.690 million. This is due to a reassessment of the estimated mix of projects between capital and output. The total program spend remains the same. | Existing | GG | Transport | Initiative is to be funded by the Transport Accident Commission. TEI has increased by $0.690 million. This is due to a reassessment of the estimated mix of projects between capital and output. The total program spend remains the same.
Road Safety Strategy 2013‑2022 (statewide) | Road Safety Strategy 2013-22 | Existing | 664092000 | -6.641% | -47241000 | 564933000 | 54875000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Department of Transport | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | TEI has reduced by $47.241 million, with $25.000 million transferred to the Road Safety Toward Zero program and $22.241 million to Active Transport program. Initiative is funded by the Transport Accident Commission. | Existing | GG | Transport | TEI has reduced by $47.241 million, with $25.000 million transferred to the Road Safety Toward Zero program and $22.241 million to Active Transport program. Initiative is funded by the Transport Accident Commission.
Road Safety Towards Zero (statewide) | Road Safety Towards Zero | Existing | 290999000 | 9.398% | 24999000 | 250955000 | 8353000 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Department of Transport | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | TEI has increased by $25.000 million due to funding transferred from the Road Safety Strategy 2013‑22 (statewide) program. Initiative is funded by the Transport Accident Commission. | Existing | GG | Transport | TEI has increased by $25.000 million due to funding transferred from the Road Safety Strategy 2013‑22 (statewide) program. Initiative is funded by the Transport Accident Commission.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 201000000 | 21.82% | 36000000 | 77100000 | 63800000 | qtr22018‑19 | 2016–17 | 1/07/2016 | 2018-10-01 | Department of Health and Human Services | Department of Health | Melbourne | Melbourne | Metropolitan | 0 | 0 | The TEI for this project has increased due to an additional $31.400 million provided in 2016‑17 (including a $10.000 million contribution from the health service) in order to complete the project. The health service has also separately funded $4.600 million for the addition of a new Education Centre, bringing the combined TEI to $201.000 million. | Existing | GG | Health and human services | The TEI for this project has increased due to an additional $31.400 million provided in 2016‑17 (including a $10.000 million contribution from the health service) in order to complete the project. The health service has also separately funded $4.600 million for the addition of a new Education Centre, bringing the combined TEI to $201.000 million.
Streamlining Hoddle Street (Richmond) | Streamlining Hoddle Street | Existing | 56180000 | -0.05337% | -30000 | 7357000 | 12676000 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Richmond | Richmond | Metropolitan | 0 | 0 | TEI excludes corporate costs. | Existing | GG | Transport | TEI excludes corporate costs.
Streamlining Hoddle Street (Richmond) | Streamlining Hoddle Street | Existing | 108554000 | 93.23% | 52374000 | 45117000 | 11240000 | qtr42018-19 | 2018–19 | 1/07/2018 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Richmond | Richmond | Metropolitan | 0 | 0 | TEI for project has changed as a result of corporate cost not being reported against this project. TEI has increased by $52.610 million funded by savings achieved on other projects. | Existing | GG | Transport | TEI for project has changed as a result of corporate cost not being reported against this project. TEI has increased by $52.610 million funded by savings achieved on other projects.
Targeted Road restoration (statewide) | Targeted Road restoration | Existing | 140000000 | 55.56% | 50000000 | 86820000 | 445000 | qtr42015‑16 | 2015–16 | 1/07/2015 | 2016-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | Includes previously reported Arterial road restoration (statewide). | Existing | GG | Transport | Includes previously reported Arterial road restoration (statewide).
Thompsons Road duplication (Lyndhurst) | Thompsons Road duplication | Existing | 148173000 | -0.08564% | -127000 | 29475000 | 73013000 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Lyndhurst | Lyndhurst | Metropolitan | 0 | 0 | TEI excludes corporate costs. | Existing | GG | Transport | TEI excludes corporate costs.
Thompsons Road duplication (Lyndhurst) | Thompsons Road duplication | Existing | 123243000 | -16.82% | -24930000 | 58495000 | 17523000 | qtr42018-19 | 2018–19 | 1/07/2018 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Lyndhurst | Lyndhurst | Metropolitan | 0 | 0 | TEI has reduced by $24.930 million due to identified project savings. | Existing | GG | Transport | TEI has reduced by $24.930 million due to identified project savings.
Victorian Heart Hospital (Clayton) | Victorian Heart Hospital | Existing | 564000000 | 3.867% | 21000000 | 71773000 | 420000000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Department of Health and Human Services | Department of Health | Clayton | Clayton | Metropolitan | 0 | 0 | The project’s TEI has increased by $21.000 million to reflect change design requirements by Monash University. The cashflow has been revised in line with a new project schedule. | Existing | GG | Health and human services | The project’s TEI has increased by $21.000 million to reflect change design requirements by Monash University. The cashflow has been revised in line with a new project schedule.
West Gate Tunnel (metropolitan various) | West Gate Tunnel | Existing | 6301924000 | -0.67% | -42508000 | 2529738000 | 2170407000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Department of Transport | Department of Transport | metropolitan various | Metropolitan | Metropolitan | West Gate Tunnel Project | West Gate Tunnel Whole(metropolitan various) | TEI excludes $42.508 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. | Existing | GG | Transport | TEI excludes $42.508 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
Western Highway duplication – Ballarat to Stawell (regional various) | Western Highway duplication – Ballarat to Stawell | Existing | 659437000 | -0.4323% | -2863000 | 468958000 | 150550000 | qtr32018-19 | 2017–18 | 1/07/2017 | 2019-01-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | regional various | Regional | Regional | 0 | 0 | TEI excludes corporate costs. TEI includes $501.300 million of Commonwealth funding. | Existing | GG | Transport | TEI excludes corporate costs. TEI includes $501.300 million of Commonwealth funding.
Yan Yean Road duplication (Plenty) | Yan Yean Road duplication – Stage 1 | Existing | 125827000 | -0.264% | -333000 | 12662000 | 75284000 | qtr42019-20 | 2017–18 | 1/07/2017 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Plenty | Plenty | Metropolitan | 0 | 0 | TEI excludes corporate costs. | Existing | GG | Transport | TEI excludes corporate costs.
Yan Yean Road duplication – Stage 1 (Plenty) | Yan Yean Road duplication – Stage 1 | Existing | 125958000 | 0.1041% | 131000 | 53975000 | 27543000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Plenty | Plenty | Metropolitan | 0 | 0 | TEI for project has changed as a result of corporate cost not being reported against this project. | Existing | GG | Transport | TEI for project has changed as a result of corporate cost not being reported against this project.
Carlton redevelopment – 246 units/sites (North‑West metro) | Carlton redevelopment – 246 units/ sites | Existing | 146401000 | -0.01434% | -21000 | 138871000 | 6880000 | qtr42018‑19 | 2015–16 | 1/07/2015 | 2019-04-01 | Director of Housing | Department of Families, Fairness and Housing | North‑West metro | Metropolitan | Metropolitan | 0 | 0 | 0 | Existing | PNFC | Health and human services | N/A
Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) | Caulfield to Dandenong conventional signalling and power infrastructure upgrade | Existing | 608281000 | 68.97% | 248281000 | 305480000 | 58110000 | qtr22018-19 | 2017–18 | 1/07/2017 | 2018-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) TEI incorporates $248.281 million for power and associated infrastructure works initially reported as part of High-capacity metro trains. The publication title is updated since 2016-17 Budget Paper No. 4. | Existing | PNFC | Transport | Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) TEI incorporates $248.281 million for power and associated infrastructure works initially reported as part of High-capacity metro trains. The publication title is updated since 2016-17 Budget Paper No. 4.
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | City Loop fire and safety (upgrade stage 2) and intruder alarm | Existing | 151743000 | 14.21% | 18880000 | 24719000 | 70488000 | qtr22019-20 | 2018–19 | 1/07/2018 | 2019-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Melbourne | Melbourne | Metropolitan | 0 | 0 | The estimated completion date has been revised. TEI has decreased by $4.894 million due to reallocation of capital to operating funding. TEI has increased by $23.774 million to meet additional scope and design requirements. | Existing | PNFC | Transport | The estimated completion date has been revised. TEI has decreased by $4.894 million due to reallocation of capital to operating funding. TEI has increased by $23.774 million to meet additional scope and design requirements.
CityLink‑Tulla widening project – CityLink Tunnel to Melbourne Airport (metro various) | CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport | Existing | 496924000 | 82.16% | 224124000 | 73605000 | 190415000 | qtr22017‑18 | 2016–17 | 1/07/2016 | 2017-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | 0 | TEI includes $200.000 million of Commonwealth funding and covers the total funding of the state delivered components of the project. | Existing | GG | Transport | TEI includes $200.000 million of Commonwealth funding and covers the total funding of the state delivered components of the project.
CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport (metropolitan various) | CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport | Existing | 496494000 | -0.08653% | -430000 | 286695000 | 61655000 | qtr42017-18 | 2017–18 | 1/07/2017 | 2018-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated completion date has been extended. TEI excludes corporate costs. TEI includes $200.000 million of Commonwealth funding and covers the total funding of the state delivered components of the project. | Existing | GG | Transport | The estimated completion date has been extended. TEI excludes corporate costs. TEI includes $200.000 million of Commonwealth funding and covers the total funding of the state delivered components of the project.
CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport (metropolitan various) | CityLink – Tulla widening project – CityLink Tunnel to Melbourne Airport | Completed | 496588000 | 0.01893% | 94000 | 428663000 | 0 | qtr42020-21 | 2018–19 | 1/07/2018 | 2021-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI for project has changed as a result of corporate cost adjustment. TEI includes $200.000 million Commonwealth funding. | Completed | GG | Transport | TEI for project has changed as a result of corporate cost adjustment. TEI includes $200.000 million Commonwealth funding.
Connections project (non‑metro various) | Connections project | Existing | 822836000 | -2.635% | -22270000 | 595456000 | 123792000 | qtr42017‑18 | 2015–16 | 1/07/2015 | 2018-04-01 | Goulburn‑Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | non‑metro various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Water | N/A
Connections project (regional various) | Connections project | Existing | 1015038000 | 9.455% | 87681000 | 775716000 | 108638000 | qtr22020-21 | 2017–18 | 1/07/2017 | 2020-10-01 | Goulburn-Murray Rural Water Corporation | Goulburn–Murray Rural Water Corporation | regional various | Regional | Regional | 0 | 0 | 0 | Existing | PNFC | Water | N/A
Frankston Line stabling (Seaford) | Frankston Line stabling | Existing | 236685000 | 26.3% | 49285000 | 34065000 | 69313000 | qtr32019-20 | 2018–19 | 1/07/2018 | 2020-01-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Seaford | Seaford | Metropolitan | 0 | 0 | TEI includes additional funding of $49.285 million to address site contamination and risk provisions. | Existing | PNFC | Transport | TEI includes additional funding of $49.285 million to address site contamination and risk provisions.
Geelong City Deal (Geelong) | Geelong City Deal | Existing | 312316000 | 124.3% | 173100000 | 4600000 | 269923000 | qtr42021‑23 | 2019–20 | 1/07/2019 | 2022-04-01 | Department of Jobs, Precincts and Regions | Department of Jobs, Precincts and Regions | Geelong | Geelong | Regional | 0 | 0 | This is the Victorian and Commonwealth Government’s share of the Geelong City Deal. Delays in expenditure partially due to negotiations with Commonwealth. | Existing | GG | Culture, sport and community | This is the Victorian and Commonwealth Government’s share of the Geelong City Deal. Delays in expenditure partially due to negotiations with Commonwealth.
Gippsland Line Upgrade Stage 1 (regional various) | Gippsland Line Upgrade Stage 1 | Existing | 433938000 | -0.2441% | -1062000 | 31335000 | 358216000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | Regional Rail Revival | 0 | TEI includes $418.000 million of Commonwealth funding, and excludes $1.062 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. The estimated completion date has been revised due to packaging of the Gippsland‑Shepparton‑Bendigo alliance. | Existing | PNFC | Transport | TEI includes $418.000 million of Commonwealth funding, and excludes $1.062 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. The estimated completion date has been revised due to packaging of the Gippsland‑Shepparton‑Bendigo alliance.
High Capacity Metro Trains (metropolitan various) | High Capacity Metro Trains | Existing | 2176000000 | 67.26% | 875000000 | 96720000 | 2007916000 | qtr12023-24 | 2018–19 | 1/07/2018 | 2023-07-01 | Victorian Rail Track (VicTrack) | Department of Transport | metropolitan various | Metropolitan | Metropolitan | 0 | High Capacity Metro Trains | TEI includes state costs, state contributions and financing costs. TEI reflects combined funding of $1 301.000 million in the 2015‑16 Budget and funding of $875.000 million in the 2016-17 Budget. | Existing | PNFC | Transport | TEI includes state costs, state contributions and financing costs. TEI reflects combined funding of $1 301.000 million in the 2015‑16 Budget and funding of $875.000 million in the 2016-17 Budget.
Increase Prison Capacity (statewide) | Increase Prison Capacity | Completed | 253632000 | -0.9761% | -2500000 | 236337000 | 0 | qtr22018-19 | 2018–19 | 1/07/2018 | 2018-10-01 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | TEI has reduced due to $2.500 million having been transferred to output funding for this initiative. | Completed | GG | Justice and emergency services | TEI has reduced due to $2.500 million having been transferred to output funding for this initiative.
Level crossing removal projects (metro various) | Level crossing removal projects | Existing | 659319000 | 44.17% | 202000000 | 34892000 | 325505000 | qtr42016‑17 | 2015–16 | 1/07/2015 | 2017-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | metro various | Metropolitan | Metropolitan | 0 | LXRP | Includes level crossing removals at Blackburn Road (Blackburn), Burke Road (Glen Iris) and North Road (Ormond). TEI includes $151.000 million of Commonwealth funding for Main Road (St Albans) previously reported within Regional Rail Link. Project renamed from Metro Level Crossing Blitz Program. | Existing | GG | Transport | Includes level crossing removals at Blackburn Road (Blackburn), Burke Road (Glen Iris) and North Road (Ormond). TEI includes $151.000 million of Commonwealth funding for Main Road (St Albans) previously reported within Regional Rail Link. Project renamed from Metro Level Crossing Blitz Program.
Melbourne Park redevelopment stage two (Melbourne) | Melbourne Park Redevelopment – stage 2 | Existing | 338121000 | -0.008576% | -29000 | 259470000 | 11570000 | qtr22020-21 | 2018–19 | 1/07/2018 | 2020-10-01 | Other public non-financial corporations | Department of Jobs, Precincts and Regions | Melbourne | Melbourne | Metropolitan | 0 | 0 | The TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust. This project was originally captured under Budget Paper No. 4, Chapter 2 in the 2017-18 Budget. | Existing | PNFC | Culture, sport and community | The TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust. This project was originally captured under Budget Paper No. 4, Chapter 2 in the 2017-18 Budget.
Melbourne Wholesale Markets redevelopment (Epping) | Melbourne Wholesale Markets redevelopment | Existing | 484436000 | -1.621% | -7982000 | 437436000 | 0 | qtr12015‑16 | 2015–16 | 1/07/2015 | 2015-07-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Jobs, Precincts and Regions | Epping | Epping | Metropolitan | 0 | 0 | TEI is reduced by $7.982 million. This is due to the transfer of funds from capital to output funding. Project has a revised estimated completion date. | Existing | GG | Culture, sport and community | TEI is reduced by $7.982 million. This is due to the transfer of funds from capital to output funding. Project has a revised estimated completion date.
Mernda rail extension project (Mernda) | Mernda rail extension project | Existing | 596714000 | 1.531% | 9000000 | 149824000 | 104050000 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Mernda | Mernda | Metropolitan | 0 | 0 | TEI increase of $9.000 million reflects project development funding provided in the 2015-16 Budget. The completion date reflects the scheduled program of works after the award of the contract in November 2016. | Existing | PNFC | Transport | TEI increase of $9.000 million reflects project development funding provided in the 2015-16 Budget. The completion date reflects the scheduled program of works after the award of the contract in November 2016.
Mernda rail extension project (Mernda) | Mernda rail extension project | Existing | 604114000 | 1.24% | 7400000 | 468101000 | 2349000 | qtr12018-19 | 2018–19 | 1/07/2018 | 2018-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Mernda | Mernda | Metropolitan | 0 | 0 | The estimated completion date has been revised. TEI includes additional funding of $7.400 million for Hawkstowe Station under GAIC. | Existing | PNFC | Transport | The estimated completion date has been revised. TEI includes additional funding of $7.400 million for Hawkstowe Station under GAIC.
Mernda rail extension project (Mernda) | Mernda rail extension project | Completed | 603027000 | -0.1799% | -1087000 | 591538000 | 0 | qtr12020‑21 | 2019–20 | 1/07/2019 | 2020-07-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Mernda | Mernda | Metropolitan | 0 | 0 | TEI has been reduced by $0.024 million due to savings and $1.063 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. | Completed | PNFC | Transport | TEI has been reduced by $0.024 million due to savings and $1.063 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards.
Melbourne Metro Tunnel (metro various) | Metro Tunnel | Existing | 10900000000 | -0.9091% | -100000000 | 244420000 | 9873500000 | qtr42025‑26 | 2016–17 | 1/07/2016 | 2026-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | The TEI includes funding announced as part of the 2015‑16 Budget Information Paper Getting On With It. This amount excludes financing costs. | Existing | PNFC | Transport | The TEI includes funding announced as part of the 2015‑16 Budget Information Paper Getting On With It. This amount excludes financing costs.
Metro Tunnel (metropolitan various) | Metro Tunnel | Existing | 10992524000 | -0.3488% | -38476000 | 1628769000 | 8793037000 | qtr22025-26 | 2018–19 | 1/07/2018 | 2025-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | The estimated completion date has been revised. TEI excludes $73.476 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. The TEI excludes financing costs. The TEI includes $35.000 million for High Capacity Signalling Equipment on board new trains allocated in 2017-18 Budget Update. | Existing | PNFC | Transport | The estimated completion date has been revised. TEI excludes $73.476 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. The TEI excludes financing costs. The TEI includes $35.000 million for High Capacity Signalling Equipment on board new trains allocated in 2017-18 Budget Update.
Metropolitan rail infrastructure renewal program (metro various) | Metropolitan rail infrastructure renewal program | Existing | 844454000 | 12.79% | 95759000 | 264535000 | 452189000 | qtr42019‑20 | 2015–16 | 1/07/2015 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2013‑14 to 2019‑20. The TEI has increased, as this is a rolling program of works and the TEI varies from year to year. | Existing | PNFC | Transport | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2013‑14 to 2019‑20. The TEI has increased, as this is a rolling program of works and the TEI varies from year to year.
Metropolitan rail infrastructure renewal program (metro various) | Metropolitan rail infrastructure renewal program | Existing | 821647000 | -2.701% | -22807000 | 249225000 | 452656000 | qtr42020‑21 | 2016–17 | 1/07/2016 | 2021-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2014‑15 to 2020‑21. The TEI has increased, as this is a rolling program of works and the TEI varies from year to year. | Existing | PNFC | Transport | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2014‑15 to 2020‑21. The TEI has increased, as this is a rolling program of works and the TEI varies from year to year.
Metropolitan rail infrastructure renewal program (metropolitan various) | Metropolitan rail infrastructure renewal program | Existing | 699891000 | -14.82% | -121756000 | 247236000 | 339696000 | qtr42021-22 | 2017–18 | 1/07/2017 | 2022-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2015-16 to 2020-21. As this is a rolling program of works, the TEI varies from year to year. | Existing | PNFC | Transport | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2015-16 to 2020-21. As this is a rolling program of works, the TEI varies from year to year.
Metropolitan rail infrastructure renewal program (metropolitan various) | Metropolitan rail infrastructure renewal program | Existing | 1528938000 | 118.5% | 829047000 | 297420000 | 960960000 | qtr42024-25 | 2018–19 | 1/07/2018 | 2025-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2016-17 to 2024-25, including funding provided in the 2017-18 Budget Update for the management of the new train and tram franchise agreement that commenced on 30 November 2017. | Existing | PNFC | Transport | TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2016-17 to 2024-25, including funding provided in the 2017-18 Budget Update for the management of the new train and tram franchise agreement that commenced on 30 November 2017.
Monash Children’s Hospital (Clayton) | Monash Children's Hospital | Existing | 271855000 | 5.299% | 13680000 | 247195000 | 22037000 | qtr42017-18 | 2017–18 | 1/07/2017 | 2018-04-01 | Department of Health and Human Services | Department of Health | Clayton | Clayton | Metropolitan | 0 | 0 | 0 | Existing | GG | Health and human services | N/A
Monash Children’s Hospital (Clayton) | Monash Children's Hospital | Completed | 271860000 | 0.001839% | 5000 | 270309000 | 0 | qtr42018-19 | 2018–19 | 1/07/2018 | 2019-04-01 | Department of Health and Human Services | Department of Health | Clayton | Clayton | Metropolitan | 0 | 0 | 0 | Completed | GG | Health and human services | N/A
Mordialloc Freeway (Braeside) | Mordialloc Freeway | Existing | 375000000 | 25% | 75000000 | 14300000 | 309600000 | qtr22022-23 | 2018–19 | 1/07/2018 | 2022-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Braeside | Braeside | Metropolitan | 0 | 0 | TEI includes a further $75.000 million for additional scope approved in the 2018-19 Budget. | Existing | GG | Transport | TEI includes a further $75.000 million for additional scope approved in the 2018-19 Budget.
More regional trains – New Vlocity Trains (regional various) | More regional trains – Regional Network Development Plan | Existing | 276125000 | -4.085% | -11760000 | 109563000 | 103405000 | qtr42020-21 | 2018–19 | 1/07/2018 | 2021-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | The estimated completion date has been revised. This project was previously reported as More regional trains. TEI has been decreased by $11.760 million due to savings in the VLocity train procurement. | Existing | PNFC | Transport | The estimated completion date has been revised. This project was previously reported as More regional trains. TEI has been decreased by $11.760 million due to savings in the VLocity train procurement.
Murray Basin Rail Project (regional various) | Murray Basin Rail Project | Existing | 426500000 | 93.86% | 206500000 | 80480000 | 110000000 | qtr22018-19 | 2017–18 | 1/07/2017 | 2018-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | MBRP | TEI increase due to addition of Commonwealth funding of $220.000 million. Stage 1 of the project is completed, with stage 2 and 3 in procurement. The completion date has been revised following the approval of Commonwealth funding. | Existing | PNFC | Transport | TEI increase due to addition of Commonwealth funding of $220.000 million. Stage 1 of the project is completed, with stage 2 and 3 in procurement. The completion date has been revised following the approval of Commonwealth funding.
Murray Basin Rail Project (regional various) | Murray Basin Rail Project | Existing | 567700000 | 33.11% | 141200000 | 371873000 | 17398000 | tbc | 2019–20 | 1/07/2019 | 2089-06-30 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | MBRP | $20.200 million has been reallocated to this project from the Regional Rail Revival – (Murray Basin Rail Project). The TEI includes funding for the ‘Rail Infrastructure Upgrades from Maryborough and Ararat to Ballarat’, a $1.000 million contribution from GrainCorp, and $35.000 million of Commonwealth funding for Ballarat Line Upgrade Stage 2. These projects have been combined for reporting purposes and the estimated completion date is to be confirmed. | Existing | PNFC | Transport | $20.200 million has been reallocated to this project from the Regional Rail Revival – (Murray Basin Rail Project). The TEI includes funding for the ‘Rail Infrastructure Upgrades from Maryborough and Ararat to Ballarat’, a $1.000 million contribution from GrainCorp, and $35.000 million of Commonwealth funding for Ballarat Line Upgrade Stage 2. These projects have been combined for reporting purposes and the estimated completion date is to be confirmed.
New E-Class trams (metropolitan various) | New E‑Class trams | Existing | 280204000 | -4.941% | -14566000 | 116714000 | 34259000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI has reduced by $14.566 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. | Existing | PNFC | Transport | TEI has reduced by $14.566 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
New VLocity carriages for the regional network (regional various) | New VLocity carriages for the regional network | Existing | 256144000 | -0.3633% | -934000 | 136024000 | 39704000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | The estimated completion date has been revised. TEI excludes $0.934 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. | Existing | PNFC | Transport | The estimated completion date has been revised. TEI excludes $0.934 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
New VLocity carriages for the regional network (regional various) | New VLocity carriages for the regional network | Existing | 252356000 | -1.479% | -3788000 | 144791000 | 15400000 | qtr42021‑22 | 2019–20 | 1/07/2019 | 2022-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | regional various | Regional | Regional | 0 | 0 | The estimated completion date has been revised due to revised scope. TEI excludes $2.150 million due to savings, and $1.638 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. | Existing | PNFC | Transport | The estimated completion date has been revised due to revised scope. TEI excludes $2.150 million due to savings, and $1.638 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards.
New stations in growth areas (metro various) | New stations in growth areas | Existing | 183500000 | -2.653% | -5000000 | 163160000 | 26000 | qtr42015‑16 | 2015–16 | 1/07/2015 | 2016-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metro various | Metropolitan | Metropolitan | 0 | 0 | TEI has decreased by $5.000 million. This is due to project savings. | Existing | PNFC | Transport | TEI has decreased by $5.000 million. This is due to project savings.
Nine additional X’Trapolis trains (metropolitan various) | Nine additional X’Trapolis trains | Completed | 174637000 | -0.2074% | -363000 | 147553000 | 0 | qtr42021‑22 | 2019–20 | 1/07/2019 | 2022-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI has reduced by $0.363 million due to savings. | Completed | PNFC | Transport | TEI has reduced by $0.363 million due to savings.
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | Existing | 80597000 | 1.062% | 847000 | 38119000 | 11392000 | qtr42018-19 | 2017–18 | 1/07/2017 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | The estimated completion date has been extended. TEI excludes corporate costs. TEI includes additional funding of $1.210 million for new project approved within this program. | Existing | GG | Transport | The estimated completion date has been extended. TEI excludes corporate costs. TEI includes additional funding of $1.210 million for new project approved within this program.
Optimising transport network performance – congestion package (statewide) | Optimising transport network performance – congestion package | Existing | 102543000 | 24.36% | 20087000 | 97386000 | 253000 | qtr42019‑20 | 2019–20 | 1/07/2019 | 2020-04-01 | Department of Transport | Department of Transport | statewide | Statewide | Statewide | 0 | 0 | TEI has increased by $20.083 million due to the complexity of delivering the project scope. The estimated completion date has been revised to quarter 4 2019‑20 due to extended community consultation and interface with other projects. | Existing | GG | Transport | TEI has increased by $20.083 million due to the complexity of delivering the project scope. The estimated completion date has been revised to quarter 4 2019‑20 due to extended community consultation and interface with other projects.
O’Herns Road upgrade (Epping) | O’Herns Road upgrade | Existing | 77786000 | 0.0463% | 36000 | 2591000 | 54655000 | qtr22019-20 | 2017–18 | 1/07/2017 | 2019-10-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | Epping | Epping | Metropolitan | 0 | 0 | The estimated completion date has been extended. TEI excludes corporate costs. TEI includes $25.800 million of Commonwealth funding. | Existing | GG | Transport | The estimated completion date has been extended. TEI excludes corporate costs. TEI includes $25.800 million of Commonwealth funding.
O’Herns Road upgrade (Epping) | O’Herns Road upgrade | Existing | 102803000 | 32.13% | 25000000 | 35391000 | 7613000 | qtr42020‑21 | 2019–20 | 1/07/2019 | 2021-04-01 | Department of Transport | Department of Transport | Epping | Epping | Metropolitan | Urban Congestion Package | 0 | TEI has increased by $25.000 million due to market escalation. TEI includes $25.801 million of Commonwealth funding. The estimated completion date has been revised to quarter 4 2020‑21 due to environmental approvals. | Existing | GG | Transport | TEI has increased by $25.000 million due to market escalation. TEI includes $25.801 million of Commonwealth funding. The estimated completion date has been revised to quarter 4 2020‑21 due to environmental approvals.
Plenty Road upgrade – Stage 2 (South Morang) | Plenty Road upgrade – Stage 2 | Existing | 114209000 | -18.08% | -25201000 | 0 | 84479000 | qtr42019-20 | 2017–18 | 1/07/2017 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | South Morang | South Morang | Metropolitan | 0 | 0 | 0 | Existing | GG | Transport | N/A
Plenty Road upgrade – Stage 2 (South Morang) | Plenty Road upgrade – Stage 2 | Existing | 143409000 | 38.68% | 40000000 | 11297000 | 95388000 | qtr22020‑21 | 2019–20 | 1/07/2019 | 2020-10-01 | Department of Transport | Department of Transport | South Morang | South Morang | Metropolitan | 0 | 0 | TEI has increased by $40.000 million due to market escalation. The estimated completion date has been revised to quarter 2 2020‑21 due to procurement requirements. | Existing | GG | Transport | TEI has increased by $40.000 million due to market escalation. The estimated completion date has been revised to quarter 2 2020‑21 due to procurement requirements.
Port capacity expansion project (Melbourne) | Port Capacity Expansion project | Existing | 641298000 | -28.11% | -250775000 | 416929000 | 0 | na | 2015–16 | 1/07/2015 | 2099-06-30 | Port of Melbourne Corporation | Port of Melbourne Corporation | Melbourne | Melbourne | Metropolitan | 0 | 0 | Due to the Port of Melbourne lease transaction, the budget does not take into account any Port of Melbourne Corporation financial data beyond 2015‑16. | Existing | PNFC | Transport | Due to the Port of Melbourne lease transaction, the budget does not take into account any Port of Melbourne Corporation financial data beyond 2015‑16.
Princes Highway East – Traralgon to Sale duplication (non‑metro various) | Princes Highway East – Traralgon to Sale duplication | Existing | 260000000 | 48.57% | 85000000 | 128103000 | 83834000 | qtr42018‑19 | 2015–16 | 1/07/2015 | 2019-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | non‑metro various | Regional | Regional | Better Roads – Rural Arterial Roads projects | 0 | TEI has increased by $85.000 million. This is due to an increase in project scope to include duplication east of Traralgon, east of Rosedale and west of Fulham. Project TEI includes $210.000 million of Commonwealth funding. | Existing | GG | Transport | TEI has increased by $85.000 million. This is due to an increase in project scope to include duplication east of Traralgon, east of Rosedale and west of Fulham. Project TEI includes $210.000 million of Commonwealth funding.
Prison capacity expansion (Melbourne) | Prison capacity expansion | Existing | 124356000 | -13.18% | -18872000 | 73329000 | 1000000 | qtr22020‑21 | 2019–20 | 1/07/2019 | 2020-10-01 | Department of Justice and Community Safety | Department of Justice and Community Safety | Melbourne | Melbourne | Metropolitan | 0 | 0 | TEI, cash flow and timing has been revised in line with a revised project scope. | Existing | GG | Justice and emergency services | TEI, cash flow and timing has been revised in line with a revised project scope.
Public Safety – Police Response (statewide) | Public Safety – Police Response | Existing | 137766000 | -7.581% | -11300000 | 30805000 | 39894000 | various | 2017–18 | 1/07/2017 | 2089-06-30 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | TEI has reduced by $11.300 million due to: the transfer of $5.000 million from capital to output funding to correctly reflect the nature of expenditure for the Intelligence Capability component; and the redirection of $6.300 million funding for land purchase for the Specialist Training Facility to the Community Safety Statement package. The estimated completion dates for the major components are: Intelligence Capability (quarter 4, 2018-19), Mobile Technology (quarter 4, 2018-19), Specialist Equipment (quarter 2, 2017-18) and Body Worn Cameras (quarter 3, 2019-20). | Existing | GG | Justice and emergency services | TEI has reduced by $11.300 million due to: the transfer of $5.000 million from capital to output funding to correctly reflect the nature of expenditure for the Intelligence Capability component; and the redirection of $6.300 million funding for land purchase for the Specialist Training Facility to the Community Safety Statement package. The estimated completion dates for the major components are: Intelligence Capability (quarter 4, 2018-19), Mobile Technology (quarter 4, 2018-19), Specialist Equipment (quarter 2, 2017-18) and Body Worn Cameras (quarter 3, 2019-20).
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Royal Victorian Eye and Ear Hospital redevelopment | Existing | 274557000 | 36.6% | 73557000 | 199588000 | 13030000 | qtr22021‑22 | 2019–20 | 1/07/2019 | 2021-10-01 | Department of Health and Human Services | Department of Health | Melbourne | Melbourne | Metropolitan | 0 | 0 | The project’s TEI has increased to reflect the additional joint funding between the department and the Royal Victorian Eye and Ear Hospital. The cashflow has been revised in line with a revised project schedule. | Existing | GG | Health and human services | The project’s TEI has increased to reflect the additional joint funding between the department and the Royal Victorian Eye and Ear Hospital. The cashflow has been revised in line with a revised project schedule.
Shepparton Corridor Upgrade – Stage 2 (Shepparton) | Shepparton Corridor Upgrade – Stage 2 | Existing | 312487000 | -0.1349% | -422000 | 10384000 | 283603000 | qtr22022‑23 | 2019–20 | 1/07/2019 | 2022-10-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | Shepparton | Shepparton | Regional | 0 | 0 | TEI excludes $0.422 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. Project name changed from ’Shepparton Line Upgrade – Stage 2’ published in 2018-19 Budget. The estimated completion date has been revised due to the packaging of the Gippsland‑Shepparton‑Bendigo alliance. | Existing | PNFC | Transport | TEI excludes $0.422 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. Project name changed from ’Shepparton Line Upgrade – Stage 2’ published in 2018-19 Budget. The estimated completion date has been revised due to the packaging of the Gippsland‑Shepparton‑Bendigo alliance.
State Coronial Services redevelopment (statewide) | State Coronial Services redevelopment | Existing | 114359000 | 11.38% | 11683000 | 111225000 | 0 | qtr22015‑16 | 2015–16 | 1/07/2015 | 2015-10-01 | Department of Justice and Regulation | Department of Justice and Community Safety | statewide | Statewide | Statewide | 0 | 0 | 0 | Existing | GG | Justice and emergency services | N/A
Trade training centres – government schools (statewide) | Trade training centres – government schools | Existing | 252838000 | 1.885% | 4678000 | 243160000 | 0 | qtr42017-18 | 2017–18 | 1/07/2017 | 2018-04-01 | Department of Education and Training | Department of Education and Training | statewide | Statewide | Statewide | Commonwealth funding | 0 | TEI includes co-contribution from TAFE. | Existing | GG | Education | TEI includes co-contribution from TAFE.
Tram procurement and supporting infrastructure (metropolitan various) | Tram procurement and supporting infrastructure | Existing | 804205000 | -0.0312% | -251000 | 700787000 | 34486000 | qtr42021‑22 | 2019–20 | 1/07/2019 | 2022-04-01 | Victorian Rail Track (VicTrack) | Victorian Rail Track | metropolitan various | Metropolitan | Metropolitan | 0 | 0 | TEI has reduced by $0.250 million due to savings. The estimated completion date has been revised to quarter 4 2021‑22 due to remediation works and the availability of land for substation sites. | Existing | PNFC | Transport | TEI has reduced by $0.250 million due to savings. The estimated completion date has been revised to quarter 4 2021‑22 due to remediation works and the availability of land for substation sites.
Victorian Heart Hospital (Clayton) | Victorian Heart Hospital | Existing | 543000000 | 302.2% | 408000000 | 12868000 | 511000000 | qtr22022-23 | 2018–19 | 1/07/2018 | 2022-10-01 | Department of Health and Human Services | Department of Health | Clayton | Clayton | Metropolitan | 0 | 0 | TEI includes contributions from Monash University of $65.000 million and funding provided in 2017‑18 and in the 2017-18 Budget. The estimated completion date has been revised to reflect the final project scope and timelines approved by Government. | New | GG | Health and human services | TEI includes contributions from Monash University of $65.000 million and funding provided in 2017‑18 and in the 2017-18 Budget. The estimated completion date has been revised to reflect the final project scope and timelines approved by Government.
Western Highway duplication – Ballarat to Stawell (non‑metro various) | Western Highway duplication – Ballarat to Stawell | Existing | 662300000 | 31.15% | 157300000 | 318596000 | 241022000 | qtr42017‑18 | 2015–16 | 1/07/2015 | 2018-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | non‑metro various | Regional | Regional | Better Roads – Rural Arterial Roads projects | 0 | TEI has increased by $157.300 million. This is due to an increase in project scope to include Buangor to Ararat duplication. Project TEI includes $501.300 million of Commonwealth funding. | Existing | GG | Transport | TEI has increased by $157.300 million. This is due to an increase in project scope to include Buangor to Ararat duplication. Project TEI includes $501.300 million of Commonwealth funding.
Western Highway duplication – Ballarat to Stawell (regional various) | Western Highway duplication – Ballarat to Stawell | Existing | 656356000 | -0.4672% | -3081000 | 490630000 | 157263000 | qtr42019-20 | 2018–19 | 1/07/2018 | 2020-04-01 | Department of Economic Development, Jobs, Transport and Resources | Department of Transport | regional various | Regional | Regional | 0 | 0 | The estimated completion date has been revised. TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $499.380 million of Commonwealth funding. | Existing | GG | Transport | The estimated completion date has been revised. TEI for project has changed as a result of corporate cost not being reported against this project. TEI includes $499.380 million of Commonwealth funding.
Western Highway duplication – Ballarat to Stawell (regional various) | Western Highway duplication – Ballarat to Stawell | Existing | 656357000 | 0.0001524% | 1000 | 512068000 | 104629000 | qtr22021‑22 | 2019–20 | 1/07/2019 | 2021-10-01 | Department of Transport | Department of Transport | regional various | Regional | Regional | 0 | 0 | TEI includes $499.380 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2021‑22 due to a change in scope. | Existing | GG | Transport | TEI includes $499.380 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2021‑22 due to a change in scope.

## Discont. & Completed Projects
VAGO name | Status | Budget year_discontinuedCompleted
40 New trains for Melbourne commuters – stage 1 | Completed | 2016–17
Building confidence in corrections – Construction/asset enhancement | Completed | 2016–17
Improving hospital services – sub‑acute | Completed | 2015–16
Melbourne Rail Link | Discontinued | 2015–16
Melbourne Wholesale Markets redevelopment | Completed | 2016–17
New stations in growth areas | Completed | 2016–17
New trains for Melbourne commuters | Completed | 2016–17
Port Capacity Expansion project | Discontinued | 2017–18
Port of Hastings development | Discontinued | 2015–16
Princes Highway West – stage 1 Waurn Ponds to Winchelsea | Completed | 2015–16
Regional Rail Link | Completed | 2015–16
Regional rail network major periodic maintenance (passenger and freight) | Completed | 2016–17
Regional rolling stock – new tranche | Completed | 2017–18
State Coronial Services redevelopment | Completed | 2016–17
Regional rolling stock | Completed | 2015–16
Targeted Road restoration | Completed | 2016–17
Cranbourne‑Pakenham rail corridor project | Discontinued | 2015–16
Box Hill Hospital – Redevelopment | Completed | 2017–18
Dingley Bypass between Warrigal Road to Westall Road | Completed | 2016–17
East West Link – Eastern section | Discontinued | 2015–16
East West Link – Western section | Discontinued | 2015–16
M80 Upgrade | Completed | 2015–16
Major periodic maintenance | Completed | 2017–18
Metropolitan rolling stock | Completed | 2016–17